## Summary Sheet
Summary of Capitalization
Sl. No. | Particulars | Truing up of FY 2024-25 |  | Annual Performance Review of FY 2025-26 |  | MYT of FY 2026-27
|  | Capex | Capitalization | Capex | Capitalization | Capex | Capitalization
1 | Projected Capitalization by P1 | 700.93 | 905.4986 | 1554.3888 | 409.4012 | 1999.738 | 1852.98
2 | Projected Capitalization by P2 | 207.5 | 813.192 | 575.347 | 1019.27 | 144.8 | 174.8
3 | Projected Capitalization by Other Deptt. and Direct Capitalization | 81.79 | 11.1003 | 67.24 | 67.24 | 2.4 | 2.4
4 | Total Projected Capitalization | 990.22 | 1729.7909 | 2196.9758 | 1495.9112 | 2146.938 | 2030.18

## Capex & Capitalization_Final
Details of Capitalization | [15 empty] | Truing Up of FY 2023-24 | [5 empty] | True Up of FY 2024-25 |  |  |  |  | APR of FY 2025-26 |  |  |  |  | MYT of FY 2026-27 |  |  |  |  | MYT of FY 2027-28
Sl. No. | NIT No. | Concerned Deptt. | Plan | Regulatory Approval Reference No. | Name of Element (Transmission line, Substation, Bay Extension, etc.) | Awarded through ICB/DCB/Department /Deposit Work | No. of Bids received | Date of Award | Actual date of Start of work | Original Schedule Date of Completion | Original Cost of Project | CAPEX Approved in Tariff Orders | Mode of Finance | Amended Cost of Project | Capitalised upto 31.03.2023 | Opening CWIP as on 01.04.2023 | CAPEX FY 2023-24 | Capitalization in FY 2023-24 | IDC Capitalization in FY 2023-24 | Capitalised upto 31.03.2024 | Closing CWIP as on 31.03.2024 | CAPEX FY 2024-25 | Capitalization in FY 2024-25 | IDC Capitalization in FY 2024-25 | Capitalised upto 31.03.2025 | Closing CWIP as on 31.03.2025 | CAPEX FY 2025-26 | Capitalization in FY 2025-26 | IDC Capitalization in FY 2025-26 | Capitalised upto 31.03.2026 | Closing CWIP as on 31.03.2026 | CAPEX FY 2026-27 | Capitalization in FY 2026-27 | IDC Capitalization in FY 2026-27 | Capitalised upto 31.03.2027 | Closing CWIP as on 31.03.2027 | CAPEX FY 2027-28 | Capitalization in FY 2027-28 | IDC Capitalization in FY 2027-28 | Capitalised upto 31.03.2028 | Closing CWIP as on 31.03.2028 | Grant | Loan | Equity | Grant | Loan | Equity | Grant | Loan | Equity | Grant
1 | 95/2014 | P1 | 12th Plan Ongoing Project | Page No. 158, Sl. No. 1 of MYT Order | Construction of 220KV D/C transmission line from BTPS to Hajipur, NIT-95/2014 | DCB | 2 | 2015-03-20 | 2015-03-20 | 2016-06-20 | 76.57 | 105.78 | BRGF | 105.78 | 108.27 | 0 |  |  |  | 108.27 | 0 |  |  |  | 108.27 | 0 |  |  |  | 108.27 | 0 |  |  |  | 108.27 | 0 |  |  |  | 108.27 | 0 |  |  | 0 |  |  | 0
2 | 93/2014 | P1 | 12th Plan Ongoing Project | Page No. 194, Sl. No. 2-5 of MYT Order | Construction of 132/33KV GSS Maharajganj- NIT/93/2014. Construction of 132/33KV GSS Narkatiyaganj - NIT-93/2014 Construction of 132/33KV GSS Hathua NIT-93/2014 Construction of 132/33KV GSS Areraj, NIT-93/2014 | DCB | 2 | 2015-03-20 | 2015-03-20 | 2016-03-20 | 79.24 | 79.24 | State Plan | 79.54 | 84.63 | 0 |  |  |  | 84.63 | 0 |  |  |  | 84.63 | 0 |  |  |  | 84.63 | 0 |  |  |  | 84.63 | 0 |  |  |  | 84.63 | 0 |  | 0 | 0 |  | 0 | 0
3 | 62/PR/BSPTCL/2014 pkg A | P1 | 12th Plan Ongoing Project | - | Construction of 132/33KV GSS Chakiya-NIT-62A/2014 Construction of 132/33KV GSS Jhanjharpur Construction of 132/33KV GSS Pakridayal | DCB | 2 | 2015-03-15 | 2015-03-15 | 2016-03-15 | 41.3 | 41.3 | State Plan | 44.21 | 42.2293 | 4.2207 |  |  |  | 42.2293 | 4.2207 |  |  |  | 42.2293 | 4.2207 |  |  |  | 42.2293 | 4.2207 |  |  |  | 42.2293 | 4.2207 |  |  |  | 42.2293 | 4.2207 |  | 0 | 0 |  | 0 | 0
4 | 38/2014 | P1 | 12th Plan Ongoing Project | Page No. 194, Sl. No. 10 of MYT Order | Construction of Loop In Loop Out arrangement of 132 KV Tx. line Madhepura- Sonebarsa 132 KV S/C Tx.line on D/C Tower at Saharsa Existing (CKM-40KM) under Special Plan of Phase-III against NIT 38/2014. | DCB | 2 | 2015-02-10 | 2015-02-10 | 2015-08-09 | 10.65 | 17.52 | BRGF | 15.03 | 15.44 | 0 |  |  |  | 15.44 | 0 |  |  |  | 15.44 | 0 |  |  |  | 15.44 | 0 |  |  |  | 15.44 | 0 |  |  |  | 15.44 | 0 |  |  | 0 |  |  | 0
5 | 63/2014 | P1 | 12th Plan Ongoing Project | Page No. 194, Sl. No. 11 of MYT Order | Construction of 132/33 KV, 2 x20MVA Nirmali, 2 x 20 MVA, 2 x 20 MVA Banmankhi, 2 x 20 MVA Manihari and 2 x 10 MVA Triveniganj against NIT 63/2014(Package B) | DCB | 3 | 2015-02-11 | 2015-02-11 | 04.04.2016(Ni rmali) 04.04.2016(Tr iveniganaj) 09.04.2016(Ba nmankhi) 31.07.2016(M anihari) | 73.24 | 79.04 | State Plan | 79.02 | 83.42 | 0 |  |  |  | 83.42 | 0 |  |  |  | 83.42 | 0 |  |  |  | 83.42 | 0 |  |  |  | 83.42 | 0 |  |  |  | 83.42 | 0 |  | 0 | 0 |  | 0 | 0
6 | 92/2014 | P1 | 12th Plan Ongoing Project | Page No. 195, Sl. No. 13 of MYT Order | Construction of 2 x50MVA , 132/33KV GSS Araria, Barsoi, Baisi and Dhamdaha AGAINST NIT 92/2014. | DCB | 2 | 2015-08-12 | 2015-08-12 | 2016-08-11 | 91.91 | 105.07 | State Plan | 109.88 | 112.19 | 0 |  |  |  | 112.19 | 0 |  |  |  | 112.19 | 0 |  |  |  | 112.19 | 0 |  |  |  | 112.19 | 0 |  |  |  | 112.19 | 0 |  | 0 | 0 |  | 0 | 0
7 | 07/PR/BSPTCL/2016 | - | 12th Plan Ongoing Project | Page No. 195, Sl. No. 14 of MYT Order | R&M of 132/33KV GSS at Kishanganj, Jamalpur and Purnea against NIT no. 07/PR/BSPTCL/2016 | DCB | 2 | 2016-03-02 | 2016-03-02 | 2017-03-02 | 26.19 | 34.28 | State Plan | 30.97 | 41.16 | 0 |  |  |  | 41.16 | 0 |  |  |  | 41.16 | 0 |  |  |  | 41.16 | 0 |  |  |  | 41.16 | 0 |  |  |  | 41.16 | 0 |  | 0 | 0 |  | 0 | 0
8 | 76/PR/BSPTCL/2015 | P1 | 12th Plan Ongoing Project | Page No. 195, Sl. No. 17 of MYT Order | Second circuit stringing of Existing 03 Nos. of 132 kV Double Circuit Single Strung Transmission Lines under Transmission Circle, Purnea on Turnkey Basis against NIT No 76/PR/BSPTCL/2015 | DCB | 4 | 2016-03-02 | 2016-03-02 | 2016-12-02 | 16.69 | 16.69 | State Plan | 16.69 | 0 | 15.19 |  |  |  | 0 | 15.19 |  |  |  | 0 | 15.19 |  |  |  | 0 | 15.19 |  |  |  | 0 | 15.19 |  |  |  | 0 | 15.19 |  | 0 | 0 |  | 0 | 0
9 | 403/PR/BSPTCL/2013 Pkg A | P1 | 12th Plan Ongoing Project | Page No. 195, Sl. No. 18 of MYT Order | Construction of 132 KV D/C T/L from Motihari (400 KV) to Motihari (BSPTCL) NIT 403/PR/BSPTCL/2013 Pkg A | DCB | 2 | 2014-02-13 | 2014-02-13 | 2015-02-12 | 8.54 | 8.54 | BRGF | 8.54 | 9.03 | 0 |  |  |  | 9.03 | 0 |  |  |  | 9.03 | 0 |  |  |  | 9.03 | 0 |  |  |  | 9.03 | 0 |  |  |  | 9.03 | 0 |  |  | 0 |  |  | 0
10 | 403/PR/BSPTCL/2013 Pkg B | P1 | 12th Plan Ongoing Project | Page No. 195, Sl. No. 19 of MYT Order | Construction of 132 KV D/C T/L from Motihari (400 KV) to Bettiah NIT 403/PR/BSPTCL/2013 Pkg B | DCB | 2 | 2014-02-13 | 2014-02-13 | 2015-02-12 | 18.69 | 18.69 | BRGF | 18.83 | 19.4 | 0 |  |  |  | 19.4 | 0 |  |  |  | 19.4 | 0 |  |  |  | 19.4 | 0 |  |  |  | 19.4 | 0 |  |  |  | 19.4 | 0 |  |  | 0 |  |  | 0
11 | 403/PR/BSPTCL/2013 Pkg C | P1 | 12th Plan Ongoing Project | Page No. 195, Sl. No. 20 of MYT Order | Construction of 132 KV D/C T/L from Motihari (400 KV) to Raxaul NIT 403/PR/BSPTCL/2013 Pkg C | DCB | 2 | 2014-02-13 | 2014-02-13 | 2016-03-16 | 27.42 | 27.42 | BRGF | 28.16 | 30.07 | 0 |  |  |  | 30.07 | 0 |  |  |  | 30.07 | 0 |  |  |  | 30.07 | 0 |  |  |  | 30.07 | 0 |  |  |  | 30.07 | 0 |  |  | 0 |  |  | 0
12 | 403/2013, VSPL | P1 | 12th Plan Ongoing Project | Page No. 195, Sl. No. 21 of MYT Order | construction of two numbers of 132 KV Line bays each at Bettiah (132/33 KV) GSS and Raxaul (132/33 KV) GSS, NIT-403/2013, VSPL | DCB | 2 | 2014-02-13 | 2014-02-13 | 2016-02-05 | 7.02 | 7.02 | BRGF | 7.02 | 7.55 | 0 |  |  |  | 7.55 | 0 |  |  |  | 7.55 | 0 |  |  |  | 7.55 | 0 |  |  |  | 7.55 | 0 |  |  |  | 7.55 | 0 |  |  | 0 |  |  | 0
13 | 08/2014, ABN | P1 | 12th Plan Ongoing Project | Page No. 196, Sl. No. 25 of MYT Order | Construction of 6 nos of 132/33KV Transformer Bay at Madhubani, Muzaffarpur, Dalsingsarai, Ramnagar, Hajipur and Jandaha , NIT- 08/2014, ABN | DCB | 2 | 2015-02-09 | 2015-02-09 | 2016-02-08 | 10.8 | 12.67 | BRGF | 12.67 | 12.57 | 0 |  |  |  | 12.57 | 0 |  |  |  | 12.57 | 0 |  |  |  | 12.57 | 0 |  |  |  | 12.57 | 0 |  |  |  | 12.57 | 0 |  |  | 0 |  |  | 0
14 | 02/2015, L&T Tx. Line | P1 | 12th Plan Ongoing Project | Page No. 196, Sl. No. 26 of MYT Order | Construction of 220 KV Kishanganj New- Madhepura D/C NIT-02/2015, L&T Tx. Line | DCB | 5 | 2015-03-21 | 2015-03-21 | 2016-03-20 | 110.8 | 129.79 | BRGF | 127.77 | 137.67 | 0 |  |  |  | 137.67 | 0 |  |  |  | 137.67 | 0 |  |  |  | 137.67 | 0 |  |  |  | 137.67 | 0 |  |  |  | 137.67 | 0 |  |  | 0 |  |  | 0
15 | 03/2015, L&T | P1 | 12th Plan Ongoing Project | Page No. 196, Sl. No. 27 of MYT Order | Construction of 220 KV (D/C) Line between Madhepura to Laukhi with AL-59 Conductor(75Km), NIT-03/2015, L&T | DCB | 4 | 2015-03-21 | 2015-03-21 | 2016-03-20 | 94.6 | 103.95 | BRGF | 103.84 | 107.83 | 0 |  |  |  | 107.83 | 0 |  |  |  | 107.83 | 0 |  |  |  | 107.83 | 0 |  |  |  | 107.83 | 0 |  |  |  | 107.83 | 0 |  |  | 0 |  |  | 0
16 | 27/2015 | P1 | 12th Plan Ongoing Project | Page No. 196, Sl. No. 28 of MYT Order | Construction of 220 KV Purnea (PG) – Begusarai D/C Tx. Line NIT-27/2015 | DCB | 2 | 2015-08-25 | 2015-08-25 | 2016-11-24 | 97.2 | 125.26 | State Plan | 115.75 | 123.89 | 0 |  |  |  | 123.89 | 0 |  |  |  | 123.89 | 0 |  |  |  | 123.89 | 0 |  |  |  | 123.89 | 0 |  |  |  | 123.89 | 0 |  | 0 | 0 |  | 0 | 0
17 | 22/PR/BSPTCL/2015 | P1 | 12th Plan Ongoing Project | Page No. 196, Sl. No. 29 of MYT Order | 132 KV LILO T/l on one of the CKT of 132 KV Betia--Dhanha to Ramanagar GSS against NIT No. 22/PR/BSPTCL/2015 | DCB | 2 | 2015-08-13 | 2015-08-13 | 2016-08-12 | 29.37 | 35.24 | BRGF | 34.38 | 36.86 | 0 |  |  |  | 36.86 | 0 |  |  |  | 36.86 | 0 |  |  |  | 36.86 | 0 |  |  |  | 36.86 | 0 |  |  |  | 36.86 | 0 |  |  | 0 |  |  | 0
18 | 30/PR/BSPTCL/2017 | P1 | 12th Plan Ongoing Project | Page No. 197, Sl. No. 30 of MYT Order | Construction of 3x50MVA , 132/33KV GSS Raghopur against NIT 30/PR/BSPTCL/2017. | DCB | 6 | 2018-01-05 | 2018-01-05 | 2018-01-04 | 32.3 | 32.3 | State Plan | 31.43 | 32.95 | 0 |  |  |  | 32.95 | 0 |  |  |  | 32.95 | 0 |  |  |  | 32.95 | 0 |  |  |  | 32.95 | 0 |  |  |  | 32.95 | 0 |  | 0 | 0 |  | 0 | 0
19 | 31/PR/BSPTCL/2017 | P1 | 12th Plan Ongoing Project | Page No. 197, Sl. No. 31 of MYT Order | Construction of LILO of one circuit of 132KV Laukahi-Supaul Transmission Line at 132/33 KV GSS Raghopur against NIT No. 31/PR/BSPTCL/2017 | DCB | 3 | 2017-12-18 | 2017-12-18 | 2018-12-17 | 14.94 | 15.28 | State Plan | 15.17 | 15.03 | 0 |  |  |  | 15.03 | 0 |  |  |  | 15.03 | 0 |  |  |  | 15.03 | 0 |  |  |  | 15.03 | 0 |  |  |  | 15.03 | 0 |  | 0 | 0 |  | 0 | 0
20 | 15/PR/BSPTCL/2017 | P1 | 12th Plan Ongoing Project | Page No. 197, Sl. No. 32 of MYT Order | Construction of 132KV S/C Transmission line on D/C Tower between 132/33KV GSS Rosera and Hasanpur Sugar Mill along- with 01 no. 132KV line bay at 132/33KV GSS Rosera against NIT No.-15/PR/BSPTCL/2017 | DCB | 2 | 2017-12-11 | 2017-12-11 | 2018-10-31 | 10.42 | 12.43 | IRF | 11.49 | 11.23 | 0.26 |  |  |  | 11.23 | 0.26 |  |  |  | 11.23 | 0.26 |  |  |  | 11.23 | 0.26 |  |  |  | 11.23 | 0.26 |  |  |  | 11.23 | 0.26 |  |  | 0 |  |  | 0
21 | 81/PR/BSPTCL/2014 | P1 | 12th Plan Ongoing Project | Page No. 197, Sl. No. 35 of MYT Order | Construction of New 132 KV S/C Transmission Line on D/C Tower from existing Kuseshwarsthan GSS to Benipur GSS (Line length-37 Km), construction of New 132 KV S/C Transmission Line on D/C Tower from 220/132 KV Samastipur GSS to Upcoming Shahpurpatori GSS (Line Length- 31 CKM), LILO of 132 KV S/C of Muzaffarpur –Sitamarhi at Belsand GSS under State Plan on turnkey basis against NIT No.- 81/PR/BSPTCL/2014 | DCB | 2 | 2015-03-21 | 2015-03-21 | 2016-09-30 | 28.46 | 39.18 | State Plan | 39.32 | 40.61 | 0 |  |  |  | 40.61 | 0 |  |  |  | 40.61 | 0 |  |  |  | 40.61 | 0 |  |  |  | 40.61 | 0 |  |  |  | 40.61 | 0 |  | 0 | 0 |  | 0 | 0
22 | 477/2013 | P1 | 12th Plan Ongoing Project | Page No. 198, Sl. No. 37 of MYT Order | Construction of 2 x160+3x50 MVA GSS Musahari(New), NIT-477/2013, Techno | DCB |  | 2015-01-31 | 2015-01-31 | 2016-06-04 | 73.95 | 85.07 | BRGF | 85.07 | 84.87 | 0 |  |  |  | 84.87 | 0 |  |  |  | 84.87 | 0 |  |  |  | 84.87 | 0 |  |  |  | 84.87 | 0 |  |  |  | 84.87 | 0 |  |  | 0 |  |  | 0
23 | 01/2014, L&T | P1 | 12th Plan Ongoing Project | Page No. 198, Sl. No. 38 of MYT Order | Construction of 220 KV & 132 KV D/C Transmission line for evacuation of power from upcoming Motipur GSS, NIT-01/2014, L&T | DCB |  | 2014-06-27 | 2014-06-27 | 2015-09-26 | 148.21 | 193.14 | BRGF | 193.14 | 193.05 | 0 |  |  |  | 193.05 | 0 |  |  |  | 193.05 | 0 |  |  |  | 193.05 | 0 |  |  |  | 193.05 | 0 |  |  |  | 193.05 | 0 |  |  | 0 |  |  | 0
24 | 01/2014, Pkg B | P1 | 12th Plan Ongoing Project | Page No. 198, Sl. No. 40 of MYT Order | Construction of 220 KV & 132 KV D/C Transmission line for evacuation of power from upcoming Musahari GSS NiT-01/2014, Pkg B | DCB |  | 2015-01-29 | 2015-01-29 | 2016-03-07 | 88.72 | 123.09 | BRGF | 123.09 | 92.85 | 14.77 |  |  |  | 92.85 | 14.77 |  |  |  | 92.85 | 14.77 |  |  |  | 92.85 | 14.77 |  |  |  | 92.85 | 14.77 |  |  |  | 92.85 | 14.77 |  |  | 0 |  |  | 0
25 | 15/2014 (pkg-D) | P1 | 12th Plan Ongoing Project | Page No. 198, Sl. No. 39 of MYT Order | Construction of (i) 220KV D/C Line from Darbhanga 400/200 KV GSS to to Laukahi (new)GSS (ii) 220KV D/C Line from Laukahi(new) GSS to Supaul (existing) Pkg-'D' GSS, NIT-15/2014 (pkg-D),. L&T | DCB |  | 2015-03-21 | 2015-03-21 | 2016-06-20 | 126.24 | 126.24 | BRGF | 102.2 | 108.37 | 0 |  |  |  | 108.37 | 0 |  |  |  | 108.37 | 0 |  |  |  | 108.37 | 0 |  |  |  | 108.37 | 0 |  |  |  | 108.37 | 0 |  |  | 0 |  |  | 0
26 | 03/PR/BSPTCL/2014 | P1 | 12th Plan Ongoing Project | Page No. 198, Sl. No. 45 of MYT Order | Construction of 220/132/33KV GSS Kishanganj (new) with bay extensions against NIT No. 03/PR/BSPTCL/2014 | DCB | 3 | 30.07.0214 | 30.07.0214 | 2015-10-30 | 84.46 | 89.51 | BRGF | 90.02 | 80.03 | 0.56 |  |  |  | 80.03 | 0.56 |  |  |  | 80.03 | 0.56 |  |  |  | 80.03 | 0.56 |  |  |  | 80.03 | 0.56 |  |  |  | 80.03 | 0.56 |  |  | 0 |  |  | 0
27 |  | P2 | 12th Plan Ongoing Project | Page No. 199, Sl. No. 46 of MYT Order | Capacity augmentation of 220/132/33 kV & 132/33 kV Grid Substation Madhepura, Naugachia, Vaishali, Gangwara, Jamui, Ara and Bihta | ICB | 2 | 2016-10-31 | 2016-10-31 | 2017-01-31 | 48.13 | 48.13 | ADB | 48.65 | 46.31 | 0 |  |  |  | 46.31 | 0 |  |  |  | 46.31 | 0 |  |  |  | 46.31 | 0 |  |  |  | 46.31 | 0 |  |  |  | 46.31 | 0
28 |  | P2 | 12th Plan Ongoing Project | Page No. 199, Sl. No. 47 of MYT Order | Procurement and construction of 33 KV line bays in form of Indoor VCB panels at 10 nos. of AIS sub-station under transmission circle, Purnea | ICB | 3 | 2016-10-29 | 2016-10-29 | 2017-10-28 | 28.28 | 28.28 | ADB | 34.57 | 33.11 | 0 |  |  |  | 33.11 | 0 |  |  |  | 33.11 | 0 |  |  |  | 33.11 | 0 |  |  |  | 33.11 | 0 |  |  |  | 33.11 | 0
29 |  | P2 | 12th Plan Ongoing Project | Page No. 199, Sl. No. 48 of MYT Order | Procurement and construction of 33 KV line bays in form of Indoor VCB panels at 21 nos. of AIS sub-station under transmission circle, Muzaffarpur | ICB | 1 | 2016-10-31 | 2016-10-31 | 2017-01-31 | 59.09 | 59.09 | ADB | 76.95 | 76.18 | 0.19 |  |  |  | 76.18 | 0.19 |  |  |  | 76.18 | 0.19 |  |  |  | 76.18 | 0.19 |  |  |  | 76.18 | 0.19 |  |  |  | 76.18 | 0.19
30 |  | P2 | 12th Plan Ongoing Project | Page No. 199, Sl. No. 49 of MYT Order | Procurement and construction of 33 KV line bays in form of Indoor VCB panels at 08 nos. of AIS sub-station under transmission circle, Biharsharif ICB 29 | ICB | 2 | 2016-10-29 | 2016-10-29 | 2016-10-28 | 25.2 | 25.2 | ADB | 35.65 | 35.62 | 0 |  |  |  | 35.62 | 0 |  |  |  | 35.62 | 0 |  |  |  | 35.62 | 0 |  |  |  | 35.62 | 0 |  |  |  | 35.62 | 0
31 | 183/2013 | P2 | 12th Plan Ongoing Project | Page No. 199, Sl. No. 50 of MYT Order | Construction of 220 KV Bihta(new) - Sipara(Patna) D/C transmission line ,220 KV Bihta(new)-Bihta(existing) D/c Transmission line (charged at 132 KV ) and 33 Kv down linking lines from Bihta(new) 220/132/33 KV GSS on tunkey basis. NIT- 183/2013 | DCB | 2 | 2014-01-30 | 2014-01-30 | 2015-01-29 | 72.03 | 72.03 | State Plan | 72.03 | 75.94 | 0.85 |  |  |  | 75.94 | 0.85 |  |  |  | 75.94 | 0.85 |  |  |  | 75.94 | 0.85 |  |  |  | 75.94 | 0.85 |  |  |  | 75.94 | 0.85 |  | 0 | 0 |  | 0 | 0
32 |  | P2 | 12th Plan Ongoing Project | Page No. 199, Sl. No. 52 of MYT Order | Second circuit stringing of existing 04 nos of 132KV Double circuit Single strung transmission line:- 1) 132KV Biharsharif- Ekangarsarai- Hulasganj(Except LILO point to Ekangarsasari)(48.14CKM) 2)132KV BIharsharif- Nawada(48.89CKM) 3)132KV BIharsharif- Sheikhpura(38.78CKM) 4)132KV Jamui- sheikhpura(51.9CKM | DCB | 4 | 2016-03-02 | 2016-03-02 | 2016-12-01 | 20.34 | 20.34 | State Plan | 20.34 | 21.59 | 0 |  |  |  | 21.59 | 0 |  |  |  | 21.59 | 0 |  |  |  | 21.59 | 0 |  |  |  | 21.59 | 0 |  |  |  | 21.59 | 0 |  | 0 | 0 |  | 0 | 0
33 | 24/Package D-1/ BSPTCL/ADB/16 | P2 | 12th Plan Ongoing Project | Page No. 201, Sl. No. 58 of MYT Order | Procurement and Construction of 33KV line bays in form of Indoor VCB panels at 06 nos. of AIS Sub-station under Transmission Circle Bhagalpur against 24/Package D-1/ BSPTCL/ADB/16 | ICB | 3 | 2016-10-29 | 2016-10-29 | 2017-10-28 | 18.91 | 18.91 | ADB | 23.38 | 22.33 | 0 |  |  |  | 22.33 | 0 |  |  |  | 22.33 | 0 |  |  |  | 22.33 | 0 |  |  |  | 22.33 | 0 |  |  |  | 22.33 | 0
34 | M-1/ BSPTCL/ADB/16 | P2 | 12th Plan Ongoing Project | Page No. 201, Sl. No. 60 of MYT Order | Procurement and Construction for Re- conductoring of 06 nos.132KV Transmission lines against 33/Package M-1/ BSPTCL/ADB/16 | ICB | 3 | 2016-10-31 | 2016-10-31 | 2018-01-31 | 40.86 | 40.86 | ADB | 41.32 | 40.41 | 2.82 |  |  |  | 40.41 | 2.82 |  |  |  | 40.41 | 2.82 |  |  |  | 40.41 | 2.82 |  |  |  | 40.41 | 2.82 |  |  |  | 40.41 | 2.82
35 |  | P2 | 12th Plan Ongoing Project | Page No. 201, Sl. No. 61 of MYT Order | i) LILO of one ckt. At north of muthani railway station from 132KV D/C Pusouli (New) – Mohania Trans. Line to proposed 3x50 MV Ramgarh GSS (BSPTCL of route length 20Km. ii) LILO of 132KV Line Biharsharif – Nawada D/C Trans. Line – Warsaliganj (New) GSS of Route length 40Kms.iii) LILO of one Ckt. Of 132KV Chhapra – Siwan Transmission Line – Siwan (New) GSS near Darauli of route length 45Kms. Turnkey basis under Under State Plan. | DCB | 3 | 2015-12-30 | 2015-12-30 | 2016-12-30 | 56.17 | 56.17 | State Plan | 36.91 | 37.16 | 0 |  |  |  | 37.16 | 0 |  |  |  | 37.16 | 0 |  |  |  | 37.16 | 0 |  |  |  | 37.16 | 0 |  |  |  | 37.16 | 0 |  | 0 | 0 |  | 0 | 0
36 | 7/pkg-I/ADB/BSEB/2010 | P2 | 12th Plan Ongoing Project | Page No. 236, Sl. No. 392 of MYT Order | Construction of 132KV Lines and 33KV Lines | ICB | 2 | 2012-06-22 | 2012-06-22 | 2013-12-21 | 58.23 | 58.23 | ADB | 81.09 | 82.7413 | -5.8113 |  |  |  | 82.7413 | -5.8113 |  |  |  | 82.7413 | -5.8113 |  |  |  | 82.7413 | -5.8113 |  |  |  | 82.7413 | -5.8113 |  |  |  | 82.7413 | -5.8113
37 | ICB 8 | P2 | 12th Plan Ongoing Project | Page No. 201, Sl. No. 64 of MYT Order | Construction of 220KV Lines | ICB | 2 | 2012-06-22 | 2012-06-22 | 2013-12-21 | 41.52 | 41.52 | ADB | 41.52 | 0 | 31.55 |  |  |  | 0 | 31.55 |  |  |  | 0 | 31.55 |  |  |  | 0 | 31.55 |  |  |  | 0 | 31.55 |  |  |  | 0 | 31.55
38 |  | P2 | 12th Plan Ongoing Project | Page No. 202, Sl. No. 65 of MYT Order | Procurement and Construction of 33KV line bays in form of Indoor VCB panels at 14 nos. of AIS Sub-station under Transmission Circle DOS | ICB | 1 | 2016-10-31 | 2016-10-31 | 2017-10-30 | 33.02 | 33.02 | ADB | 46.84 | 42.68 | 0 |  |  |  | 42.68 | 0 |  |  |  | 42.68 | 0 |  |  |  | 42.68 | 0 |  |  |  | 42.68 | 0 |  |  |  | 42.68 | 0
39 |  | P2 | 12th Plan Ongoing Project | Page No. 202, Sl. No. 66 of MYT Order | Construction of 33 kV Line Bays in form of Indoor GIS Panel at 11 nos. of AIS Substation under Patna District of BSPTCL on Turnkey Basis. | ICB | 2 | 2016-10-31 | 2016-10-31 | 2018-01-30 | 66.79 | 66.79 | ADB | 83 | 82.72 | 0 |  |  |  | 82.72 | 0 |  |  |  | 82.72 | 0 |  |  |  | 82.72 | 0 |  |  |  | 82.72 | 0 |  |  |  | 82.72 | 0
40 |  | P2 | 12th Plan Ongoing Project | Page No. 202, Sl. No. 67 of MYT Order | Re-conductoring of 05 nos. 220KV & 132KV Transmission lines -- 254.99 Ckm | ICB | 2 | 2016-10-31 | 2016-10-31 | 2018-01-30 | 35.45 | 35.45 | ADB | 35.55 | 35.03 | 0 |  |  |  | 35.03 | 0 |  |  |  | 35.03 | 0 |  |  |  | 35.03 | 0 |  |  |  | 35.03 | 0 |  |  |  | 35.03 | 0
41 | 12/PR/BSPTCL/2016 Pkg-B | P2 | 12th Plan Ongoing Project | Page No. 202, Sl. No. 70 of MYT Order | Construction of LILO line on both circuits of 132 KV BTPS- Purnea D/C Transmission line at Khagariya new 220/132/33 KV GSS (CKM-10 KM) against NIT 12/PR/BSPTCL/2016 Pkg-B under state plan. | DCB | 3 | 2016-08-30 | 2016-08-30 | 2017-08-30 | 11.62 | 11.62 | State Plan | 10.25 | 12.06 | 0 |  |  |  | 12.06 | 0 |  |  |  | 12.06 | 0 |  |  |  | 12.06 | 0 |  |  |  | 12.06 | 0 |  |  |  | 12.06 | 0 |  | 0 | 0 |  | 0 | 0
42 | 59/2014 | P2 | 12th Plan Ongoing Project | Page No. 203, Sl. No. 74 of MYT Order | Construction of 132KV D/C Sonenagar (New)-Aurangabad Transmission Line.NIT-59/2014, | DCB | 2 | 2015-03-21 | 2015-03-21 | 2016-03-20 | 15.9 | 15.89 | BRGF | 15.9 | 0 | 17.05 |  |  |  | 0 | 17.05 |  |  |  | 0 | 17.05 |  |  |  | 0 | 17.05 |  |  |  | 0 | 17.05 |  |  |  | 0 | 17.05 |  |  | 0 |  |  | 0
43 |  | P2 | 12th Plan Ongoing Project | Page No. 203, Sl. No. 75 of MYT Order | Construction of 132KV D/C Ara-Jagdishpur Transmission Line. | DCB | 2 | 2015-03-21 | 2015-03-21 | 2016-03-20 | 21.16 | 21.16 | BRGF | 21.07 | 22.07 | 0 |  |  |  | 22.07 | 0 |  |  |  | 22.07 | 0 |  |  |  | 22.07 | 0 |  |  |  | 22.07 | 0 |  |  |  | 22.07 | 0 |  |  | 0 |  |  | 0
44 |  | P2 | 12th Plan Ongoing Project | Page No. 203, Sl. No. 76 of MYT Order | Work of construction of 06 nos. of 132 KV D/C towers from Ara (PG) to tower loc. No. 1 with ACSR Panther Conductor for connectivity of 2nd circuit of 132 KV D/C Ara (PG)- Jagdishpur Transmission line on turnkey basis. | DCB | 3 | 2018-03-27 | 2018-03-27 | 2018-09-26 | 1.46 | 1.46 | BRGF | 1.46 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  | 0 |  |  | 0
45 |  | P2 | 12th Plan Ongoing Project | Page No. 203, Sl. No. 77 of MYT Order | Replacement of 23 nos. 50 MVA and 01 no 20 MVA transformer by 24 nos. 132/33 KV, 80 MVA transformer along with associated bay work in existing GSS of Patna | DCB | 2 | 2017-03-31 | 2017-03-31 | 2018-11-30 | 107.62 | 107.62 | State Plan | 106.5 | 110.41 | 0 |  |  |  | 110.41 | 0 |  |  |  | 110.41 | 0 |  |  |  | 110.41 | 0 |  |  |  | 110.41 | 0 |  |  |  | 110.41 | 0 |  | 0 | 0 |  | 0 | 0
46 | ICB 28 | P2 | 12th Plan Old Projects | Page No. 203, Sl. No. 81 of MYT Order | Procurement & Construction of 33Kv Line Bays in Form of Indoor VCB Panel at 14 Nos AIS Substation Under DOS ICB 28 | ICB |  |  |  |  | 36.54 | 36.54 | ADB | 48.98 | 47.32 | 0 |  |  |  | 47.32 | 0 |  |  |  | 47.32 | 0 |  |  |  | 47.32 | 0 |  |  |  | 47.32 | 0 |  |  |  | 47.32 | 0
47 | 73/2015 | P2 | 12th Plan Old Projects | Page No. 204, Sl. No. 82 of MYT Order | Tr. Line Dumraon- Buxer/Sasaram-Banjari, NIT- 73/2015 | [6 empty] | 123.67 | State Plan | 0 | 2.08 | 0 |  |  |  | 2.08 | 0 |  |  |  | 2.08 | 0 |  |  |  | 2.08 | 0 |  |  |  | 2.08 | 0 |  |  |  | 2.08 | 0 |  | 0 | 0 |  | 0 | 0
48 | 103/2014, GR 1 | P1 | 12th Plan Old Projects | Page No. 204, Sl. No. 84 of MYT Order | Extension of switcyard of 220/132 KV GSS Madhepura for Capicity Augmentation work , NIT-103/2014, GR 1 | DCB | [6 empty] | State Plan | 0 | 0.91 | 0 |  |  |  | 0.91 | 0 |  |  |  | 0.91 | 0 |  |  |  | 0.91 | 0 |  |  |  | 0.91 | 0 |  |  |  | 0.91 | 0 |  | 0 | 0 |  | 0 | 0
49 |  | P1 | 12th Plan Old Projects | Page No. 204, Sl. No. 86 of MYT Order | For Construction of 132 KV D/C Electrical crossing (Dalsingsarai-Kusheshwarsthan) Trans. Line. | DCB | [6 empty] | BRGF | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  | 0 |  |  | 0
50 | 387/2013 A &B | P2 | 12th Plan Old Projects | Page No. 269, Sl. No. 87 of MYT Order | Being amount pertaining to capacity augmentation of 132/33 KV GSS Karmanasa and Sonenagar., NIT-387/2013 A &B | DCB | [6 empty] | BRGF | 0 | 35.57 | 0 |  |  |  | 35.57 | 0 |  |  |  | 35.57 | 0 |  |  |  | 35.57 | 0 |  |  |  | 35.57 | 0 |  |  |  | 35.57 | 0 |  |  | 0 |  |  | 0
51 | 427/2013, Pkg C | P1 | 12th Plan Old Projects | Page No. 165, Sl. No. 6 of MYT Order | R&M of 132/33 Kv GSS Sone- Nagar,Karmnasha,Ara and Dumraon, NIT- 427/2013, Pkg C | DCB | 2 | 04.03.2014 | 04.03.2014 | 03.03.2015 | 23.7 |  | BRGF | 26.75 | 27.37 | 0.30615 |  |  |  | 27.37 | 0.30615 |  |  |  | 27.37 | 0.30615 |  |  |  | 27.37 | 0.30615 |  |  |  | 27.37 | 0.30615 |  |  |  | 27.37 | 0.30615 |  |  | 0 |  |  | 0
52 | 06/2014 | P1 | 12th Plan Old Projects | Page No. 165, Sl. No. 8 of MYT Order | Erection of 03 nos. 132/33 KV Transformer Bays at GSS Rajgir, Ekangarsarai & Sheikhpura , NIT- 06/2014 | DCB | [6 empty] | BRGF | 0 | 5.99 | 0 |  |  |  | 5.99 | 0 |  |  |  | 5.99 | 0 |  |  |  | 5.99 | 0 |  |  |  | 5.99 | 0 |  |  |  | 5.99 | 0 |  |  | 0 |  |  | 0
53 | 09/2014 | P1 | 12th Plan Old Projects | Page No. 205, Sl. No. 91 of MYT Order | Construction of 03 no 132/33 Kv Transformer Bays at GSS Sasaram, Bikramganj & Banjari, NIT- 09/2014 | DCB | [6 empty] | BRGF | 0 | 7.58 | 0 |  |  |  | 7.58 | 0 |  |  |  | 7.58 | 0 |  |  |  | 7.58 | 0 |  |  |  | 7.58 | 0 |  |  |  | 7.58 | 0 |  |  | 0 |  |  | 0
54 | 13/2014 | P1 | 12th Plan Old Projects | Page No. 205, Sl. No. 92 of MYT Order | Earth filling and construction of boundry wall of proposed land for 220/132/33 KV GSS Kishanganj under BRGF Ph-III Part-II, NIT- 13/2014 | DCB | [6 empty] | BRGF | 0 | 6.5 | 0 |  |  |  | 6.5 | 0 |  |  |  | 6.5 | 0 |  |  |  | 6.5 | 0 |  |  |  | 6.5 | 0 |  |  |  | 6.5 | 0 |  |  | 0 |  |  | 0
55 | 134/2013 | P1 | 12th Plan Old Projects | Page No. 205, Sl. No. 93 of MYT Order | SCT Limited, NIT-134/2013 | DCB | [6 empty] | BRGF | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  | 0 |  |  | 0
56 | 60/2014 | P1 | 12th Plan Old Projects | Page No. 205, Sl. No. 95 of MYT Order | Construction of 132 KV DC Transmission line from Motihari (400/132 Kv) GSS to Motihari (132/33KV) GSS , nit-60/2014 | DCB | [6 empty] | BRGF | 0 | 1.56 | 0 |  |  |  | 1.56 | 0 |  |  |  | 1.56 | 0 |  |  |  | 1.56 | 0 |  |  |  | 1.56 | 0 |  |  |  | 1.56 | 0 |  |  | 0 |  |  | 0
57 | 78/2014 | P1 | 12th Plan Old Projects | Page No. 205, Sl. No. 96 of MYT Order | construction of 132/33 KV GSS of 02 nos. 132 Kv line bays each at 132/33 KV GSS ramnagar, Dalsingsarai & Dhanaha, nit-78/2014 | DCB | 2 | 09.02.2015 | 09.02.2015 | 08.02.2016 | 11.67 | 11.72 | BRGF | 11.77 | 11.52 | 0 |  |  |  | 11.52 | 0 |  |  |  | 11.52 | 0 |  |  |  | 11.52 | 0 |  |  |  | 11.52 | 0 |  |  |  | 11.52 | 0 |  |  | 0 |  |  | 0
58 | 404/2013 | P1 | 12th Plan Old Projects | Page No. 205, Sl. No. 98 of MYT Order | Earth Filling and Construction of Boundry Wall around the acquired Area of 132/33 KV GSS Sheohar, NIT-404/2013 | DCB | [6 empty] | BRGF | 0 | 2.32 | 0 |  |  |  | 2.32 | 0 |  |  |  | 2.32 | 0 |  |  |  | 2.32 | 0 |  |  |  | 2.32 | 0 |  |  |  | 2.32 | 0 |  |  | 0 |  |  | 0
59 | 408/2013 | P1 | 12th Plan Old Projects | Page No. 205, Sl. No. 99 of MYT Order | Construction of 02 Nos 132 KV line bays extension at Sonenagar existing 132/33 kv GSS, NIT-408/2013 | DCB | [6 empty] | BRGF | 0 | 56.6 | 0 |  |  |  | 56.6 | 0 |  |  |  | 56.6 | 0 |  |  |  | 56.6 | 0 |  |  |  | 56.6 | 0 |  |  |  | 56.6 | 0 |  |  | 0 |  |  | 0
60 | 05/2015, GR-03 | P1 | 12th Plan Old Projects | Page No. 206, Sl. No. 101 of MYT Order | height raising of boundary wall at 132/33KV GSS campur Hajipur( 05/PR/BSPTCL/2015 Gr. No.;- 03) | DCB | [6 empty] | State Plan | 0 | 0.52 | 0 | 0.11348 |  |  | 0.52 | 0.11348 |  |  |  | 0.52 | 0.11348 |  |  |  | 0.52 | 0.11348 |  |  |  | 0.52 | 0.11348 |  |  |  | 0.52 | 0.11348 |  | 0 | 0 |  | 0 | 0
61 | 05/2015 | P1 | 12th Plan Old Projects | Page No. 206, Sl. No. 104 of MYT Order | Increasing height of Boundary Wall at GSS Forbesgan,NIT-05/2015 | DCB | [6 empty] | State Plan | 0 | 0.96 | 0 |  |  |  | 0.96 | 0 |  |  |  | 0.96 | 0 |  |  |  | 0.96 | 0 |  |  |  | 0.96 | 0 |  |  |  | 0.96 | 0 |  | 0 | 0 |  | 0 | 0
62 | 37/2015, Pkg B | P1 | 12th Plan Old Projects | Page No. 206, Sl. No. 105 of MYT Order | Construction Bay at GSS Begusarai,, Kishanganj, Sonebasha and Pusauli NIT-37/2015, Pkg B | DCB | [6 empty] | State Plan | 0 | 8.48 | 0 |  |  |  | 8.48 | 0 |  |  |  | 8.48 | 0 |  |  |  | 8.48 | 0 |  |  |  | 8.48 | 0 |  |  |  | 8.48 | 0 |  | 0 | 0 |  | 0 | 0
63 | 37/2015, Pkg A | P1 | 12th Plan Old Projects | Page No. 206, Sl. No. 106 of MYT Order | Construction Bay at GSS Begusarai,and Bikramganj NIT-37/2015, Pkg A | DCB | [6 empty] | State Plan | 0 | 6.04 | 0 |  |  |  | 6.04 | 0 |  |  |  | 6.04 | 0 |  |  |  | 6.04 | 0 |  |  |  | 6.04 | 0 |  |  |  | 6.04 | 0 |  | 0 | 0 |  | 0 | 0
64 | 15/2014 B | P1 | 12th Plan Old Projects | Page No. 206, Sl. No. 109 of MYT Order | Construction of LILO of both circuits of 220 KV Begusarai Kanti transmission line by constructing new 2X220 KV D/C transmission line to be connected with new 220/132/33 KV GSS Samastipur, NIT-15/2014 B | DCB | [6 empty] | BRGF | 0 | 1.82 | 0 |  |  |  | 1.82 | 0 |  |  |  | 1.82 | 0 |  |  |  | 1.82 | 0 |  |  |  | 1.82 | 0 |  |  |  | 1.82 | 0 |  |  | 0 |  |  | 0
65 | 160/2013 Pkg A &B | P1 | 12th Plan Old Projects | Page No. 206, Sl. No. 110 of MYT Order | 1)construction of newe 132KV D/C Line from banka PG-Sulatanganj of route length 45 KMs along with construction of 02 nos of 132KV Bays at GSS Sulatabganj , 2) Construction of new 132 KV DC Trans Line (line length -26 KM) from GSS Lakhisarai (PG) to GSS Lakhisarai (BSPTCL0) including construction of 2 nos. 132 KV bays and PLCC and complete in all respect , NIT-160/2013 Pkg A &B | DCB | [6 empty] | BRGF | 0 | 0.83 | 0 |  |  |  | 0.83 | 0 |  |  |  | 0.83 | 0 |  |  |  | 0.83 | 0 |  |  |  | 0.83 | 0 |  |  |  | 0.83 | 0 |  |  | 0 |  |  | 0
66 | 161/2013 Pkg A & D | P1 | 12th Plan Old Projects | Page No. 207, Sl. No. 111 of MYT Order | 1.Reconducorting of 132 KV SC BTPS Naugachia transmission line and 132 KV Baripahari Fathua Gaighat Mithapur Jakanpur with panther conductor, 2. Re-conductoring of 132 KV D/C Trans. line. Biharsharif-Hathidah T/L (RL-65 kms.) and 132 KV S/C Hathidah-Lakhisarai T/Line (RL-28 kms.) , NIT-161/2013 Pkg A & D | DCB | [6 empty] | BRGF | 0 | 1.02 | 0 |  |  |  | 1.02 | 0 |  |  |  | 1.02 | 0 |  |  |  | 1.02 | 0 |  |  |  | 1.02 | 0 |  |  |  | 1.02 | 0 |  |  | 0 |  |  | 0
67 | 161/2013 Pkg B&C | P1 | 12th Plan Old Projects | Page No. 207, Sl. No. 112 of MYT Order | Re condutoring of 132 KV SC Purnea Khagaria transmission line against with ACSR panther conductor , NIT-161/2013 Pkg B&C | DCB | [6 empty] | BRGF | 0 | 16.34 | 0 |  |  |  | 16.34 | 0 |  |  |  | 16.34 | 0 |  |  |  | 16.34 | 0 |  |  |  | 16.34 | 0 |  |  |  | 16.34 | 0 |  |  | 0 |  |  | 0
68 | 162/2013, Pkg A&C | P1 | 12th Plan Old Projects | Page No. 207, Sl. No. 113 of MYT Order | Work of reconducting of 132 KV D/C MTPS - Muzaffarpur Trans Line and 132 KLV S/C MTPS Motihari Trans Line,Chapra line & Betiah Line , NIT-162/2013, Pkg A&C | DCB | [5 empty] | 472.53 | BRGF | 0 | 3.56 | 0 |  |  |  | 3.56 | 0 |  |  |  | 3.56 | 0 |  |  |  | 3.56 | 0 |  |  |  | 3.56 | 0 |  |  |  | 3.56 | 0 |  |  | 0 |  |  | 0
69 | 162/2013, Pkg B | P1 | 12th Plan Old Projects | Page No. 207, Sl. No. 114 of MYT Order | 1. reconstruction of 132/33 KV S/C Darbhanga Pandaul transmission line and 132 KV S/C Darbhanga Samastipur transmission line 2.Reconducting of 132 KV S/C Darbhanga Pandaul Trans line and 132 KV S/C Darbhanga Samastipur line , NIT-162/2013, Pkg B | DCB | [5 empty] | 472.53 | BRGF | 0 | 4.27 | 0 |  |  |  | 4.27 | 0 |  |  |  | 4.27 | 0 |  |  |  | 4.27 | 0 |  |  |  | 4.27 | 0 |  |  |  | 4.27 | 0 |  |  | 0 |  |  | 0
70 | 47/2014 | P1 | 12th Plan Old Projects | Page No. 207, Sl. No. 115 of MYT Order | construction of (i) 2nd circuit stringing of 132 KV D/c Madhepura-Saharsa trans line from LILO point to 132/33 KV GSS saharsa. (ii) LILO of one circuit of 132 KV D/C Dhaka-Sitamarhi tran line at GSS Seohar. NIT-47/2014 | DCB | [5 empty] | 1370.02 | BRGF | 0 | 3.74 | 0 |  |  |  | 3.74 | 0 |  |  |  | 3.74 | 0 |  |  |  | 3.74 | 0 |  |  |  | 3.74 | 0 |  |  |  | 3.74 | 0 |  |  | 0 |  |  | 0
71 | 168/2013, Pkg A | P1 | 12th Plan Old Projects | Page No. 208, Sl. No. 116 of MYT Order | Reconductoing of 220 KV Bihar Sharif to Fatuha Line, NIT-168/2013, Pkg A | DCB | [5 empty] | 472.53 | BRGF | 0 | 10.09 | 0 |  |  |  | 10.09 | 0 |  |  |  | 10.09 | 0 |  |  |  | 10.09 | 0 |  |  |  | 10.09 | 0 |  |  |  | 10.09 | 0 |  |  | 0 |  |  | 0
72 | 18/2015 | P1 | 12th Plan Old Projects | Page No. 208, Sl. No. 117 of MYT Order | Construction of 132 KV DC trans line with ACSR panther conductor from Ramnagar to Gangwara, NIT-18/2015 | DCB | [5 empty] | 1370.02 | BRGF | 9.84 | 10.4 | 0 | 0.55235 |  |  | 10.4 | 0.55235 |  |  |  | 10.4 | 0.55235 |  |  |  | 10.4 | 0.55235 |  |  |  | 10.4 | 0.55235 |  |  |  | 10.4 | 0.55235 |  |  | 0 |  |  | 0
73 | 185/2013 | P1 | 12th Plan Old Projects | Page No. 208, Sl. No. 118 of MYT Order | work of augmentation of 132/33 KV GSS Bodhgaya,Sipara,Fatuha, Madhepura, darbhanga,Gopalganj & Begusarai. NIT- 185/2013 | DCB | [5 empty] | 472.53 | BRGF | 0 | 56.97 | 0 |  |  |  | 56.97 | 0 |  |  |  | 56.97 | 0 |  |  |  | 56.97 | 0 |  |  |  | 56.97 | 0 |  |  |  | 56.97 | 0 |  |  | 0 |  |  | 0
74 | 427/2013, Pkg A | P1 | 12th Plan Old Projects | Page No. 208, Sl. No. 120 of MYT Order | R & M work at 132/33 KV GSS Chandauti Nawada & Rafiganj, NIT-427/2013, Pkg A | DCB | 1 | 04.03.2014 | 04.03.2014 | 03.03.2015 | 17.75 | 1370.02 | BRGF | 17.74 | 17.68 | 0.29 |  |  |  | 17.68 | 0.29 |  |  |  | 17.68 | 0.29 |  |  |  | 17.68 | 0.29 |  |  |  | 17.68 | 0.29 |  |  |  | 17.68 | 0.29 |  |  | 0 |  |  | 0
75 | 429/2013 A | P1 | 12th Plan Old Projects | Page No. 208, Sl. No. 121 of MYT Order | Construction of new 132 KV DC Trans Line from GSS Lakhisarai (PG) to GSS Jamui (BSPTCL) of route length 48 KM along with construction of 02 nos. 132 bays at GSS Jamui , NIT- 429/2013 A | DCB | [5 empty] | 472.53 | BRGF | 0 | 0.93 | 0 |  |  |  | 0.93 | 0 |  |  |  | 0.93 | 0 |  |  |  | 0.93 | 0 |  |  |  | 0.93 | 0 |  |  |  | 0.93 | 0 |  |  | 0 |  |  | 0
76 | 429/2013 B | P1 | 12th Plan Old Projects | Page No. 208, Sl. No. 122 of MYT Order | Reconductoing of 132 KV Kahalgaon (NTPC) to Kahalgaon, NIT-429/2013 B | DCB | [5 empty] | 472.53 | BRGF | 0 | 1.65 | 0 |  |  |  | 1.65 | 0 |  |  |  | 1.65 | 0 |  |  |  | 1.65 | 0 |  |  |  | 1.65 | 0 |  |  |  | 1.65 | 0 |  |  | 0 |  |  | 0
77 | 186/2013 | P1 | 12th Plan Old Projects | Page No. 208, Sl. No. 124 of MYT Order | Capacity augmentation of 220/132 KV GSS Bodhgaya & Sipara by installing additional one no 160 MVA and at Fatuha, Madhepura Begusarai (02 nos.), Gopalganj, Darbhanga ,by installing additional one no. 100 MVA Transformer at each GSS and constructing corresp, work of augmentation of 132/33 KV GSS Khagaul, Bihta, Sitamarhi, Ara Nawada, Sabour, Navgachhiya, Jainagar Phulparas, supaul, Dhaka, & Belaganj. NIT-186/2013 | DCB | 2 | 09.12.2013 | 09.12.2013 | 08.03.2015 | 43.53 | 58.46 | BRGF | 36.62 | 34.61 | 0 |  |  |  | 34.61 | 0 |  |  |  | 34.61 | 0 |  |  |  | 34.61 | 0 |  |  |  | 34.61 | 0 |  |  |  | 34.61 | 0 |  |  | 0 |  |  | 0
78 | 21/2015 | P1 | 12th Plan Old Projects | Page No. 209, Sl. No. 125 of MYT Order | Construction of 2*50MVA. 132/33kv GSS at Sheohar , NIT-21/2015 | DCB | [5 empty] | 1370.02 | BRGF | 0 | 23.78 | 0 |  |  |  | 23.78 | 0 |  |  |  | 23.78 | 0 |  |  |  | 23.78 | 0 |  |  |  | 23.78 | 0 |  |  |  | 23.78 | 0 |  |  | 0 |  |  | 0
79 | 24/2015 | P1 | 12th Plan Old Projects | Page No. 209, Sl. No. 126 of MYT Order | Double Moose Conductor along with thier hardware fitting at GSS Motihari, NIT- 24/2015 | DCB | [6 empty] | BRGF | 61.87 | 0.09 | 0 |  |  |  | 0.09 | 0 |  |  |  | 0.09 | 0 |  |  |  | 0.09 | 0 |  |  |  | 0.09 | 0 |  |  |  | 0.09 | 0 |  |  | 0 |  |  | 0
80 | 06/PR/BSPTCL/2014 Gr. No.:-01 | P1 | 12th Plan Old Projects | Page No. 178, Sl. No. 147 of MYT Order | Reconstruction of Boundary Wall & Earth Filling )(GSS Sabour, 06/PR/BSPTCL/2014 Gr. No.:-01 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0.83 | 0 |  |  |  | 0.83 | 0 |  |  |  | 0.83 | 0 |  |  |  | 0.83 | 0 |  |  |  | 0.83 | 0 |  |  |  | 0.83 | 0 |  | 0 | 0 |  | 0 | 0
81 | 350/200/2013 | - | 12th Plan Old Projects | Page No. 211, Sl. No. 149 of MYT Order | Eart Filling & Construction of Boundary wall Around the land of 220/132/33 KV GSS, Sonenagar, NIT-350/200/2013 | DCB | [6 empty] | State Plan | 0 | 2.39 | 2.39 |  |  |  | 2.39 | 2.39 |  |  |  | 2.39 | 2.39 |  |  |  | 2.39 | 2.39 |  |  |  | 2.39 | 2.39 |  |  |  | 2.39 | 2.39 |  | 0 | 0 |  | 0 | 0
82 | 36/2015 | P1 | 12th Plan Old Projects | Page No. 209, Sl. No. 129 of MYT Order | Construction of LILO line on both circuits of 132KV 2nd Circuit Benipatti-Pupri Trans. Line,Jandaha-Mahnar T/L.,Bettiah-Ramnagar Trans. Line, Dalsinghsarai- K. Sthan T. L. Gopalganj-Bettiah Trans. Line,Madhubani- Jaynagar T/L, NIT 36/2015 under state plan. | DCB | [6 empty] | State Plan | 83.03 | 1.16 | 0 |  |  |  | 1.16 | 0 |  | 0.086315 |  | 1.2463 | -0.086315 |  |  |  | 1.2463 | -0.086315 |  |  |  | 1.2463 | -0.086315 |  |  |  | 1.2463 | -0.086315 |  | 0 | 0 |  | 0 | 0
83 | 32/2016 Gr 1 & c2 | P1 | 12th Plan Old Projects | Page No. 209, Sl. No. 130 of MYT Order | Civil construction of 132/33 Kv GSS SKMCH, Nit-32/2016 Gr 1 & c2 | DCB | [6 empty] | State Plan | 0 | 0.6 | 0 |  |  |  | 0.6 | 0 |  |  |  | 0.6 | 0 |  |  |  | 0.6 | 0 |  |  |  | 0.6 | 0 |  |  |  | 0.6 | 0 |  | 0 | 0 |  | 0 | 0
84 | 20/2016 | - | 12th Plan Old Projects | Page No. 209, Sl. No. 131 of MYT Order | Construction of 2 nos. 132KV Line Bays at 132/33kv GSS Musrakh, NIT-20/2016 | DCB | [6 empty] | Deposit Work | 0 | 3.61 | 3.61 |  |  |  | 3.61 | 3.61 |  |  |  | 3.61 | 3.61 |  |  |  | 3.61 | 3.61 |  |  |  | 3.61 | 3.61 |  |  |  | 3.61 | 3.61 | 0
85 | 28/2011 | P1 | 12th Plan Old Projects | Page No. 209, Sl. No. 132 of MYT Order | Construction of 4X50MVA 132/33 KV GSS Karbighhiya of 132/33 KV D/C cable lines including switching station., NIT-28/2011 | DCB | [6 empty] | State Plan | 0 | 0 | 2.49 |  |  |  | 0 | 2.49 |  |  |  | 0 | 2.49 |  |  |  | 0 | 2.49 |  |  |  | 0 | 2.49 |  |  |  | 0 | 2.49 |  | 0 | 0 |  | 0 | 0
86 | 21/2016 | P1 | 12th Plan Old Projects | Page No. 209, Sl. No. 133 of MYT Order | Construction of Doubl Storey Guest House building at 132/33Kv GSS Triveniganj,NIT- 21/2016 | DCB | [6 empty] | State Plan | 0 | 1.61 | 0 |  |  |  | 1.61 | 0 |  |  |  | 1.61 | 0 |  |  |  | 1.61 | 0 |  |  |  | 1.61 | 0 |  |  |  | 1.61 | 0 |  | 0 | 0 |  | 0 | 0
87 | 13/2016, GR-01 | P1 | 12th Plan Old Projects | Page No. 209, Sl. No. 134 of MYT Order | Extension of Boundary Wall including Soil Filling and PCC Road at 132/33Kv GSS Raxaul, NIT-13/2016, GR-01 | DCB | [6 empty] | State Plan | 1.01 | 0.94 | 0 |  |  |  | 0.94 | 0 |  |  |  | 0.94 | 0 |  |  |  | 0.94 | 0 |  |  |  | 0.94 | 0 |  |  |  | 0.94 | 0 |  | 0 | 0 |  | 0 | 0
88 | 104/2014, Gr-5 | P1 | 12th Plan Old Projects | Page No. 209, Sl. No. 135 of MYT Order | PCC road & Gravel Spreading GSS Khagaria, NIT-104/2014, Gr-5 | DCB | [6 empty] | State Plan | 0 | 1.02 | 0 |  |  |  | 1.02 | 0 |  |  |  | 1.02 | 0 |  |  |  | 1.02 | 0 |  |  |  | 1.02 | 0 |  |  |  | 1.02 | 0 |  | 0 | 0 |  | 0 | 0
89 | 104/2014, Gr-1 | P1 | 12th Plan Old Projects | Page No. 209, Sl. No. 136 of MYT Order | For the work of PCC and Gravel spreading is working area of switchyard at 132/33 KV GSS Kishanganj, NIT-104/2014, Gr-1 | DCB | [6 empty] | State Plan | 0 | 1.48 | 0 |  |  |  | 1.48 | 0 |  |  |  | 1.48 | 0 |  |  |  | 1.48 | 0 |  |  |  | 1.48 | 0 |  |  |  | 1.48 | 0 |  | 0 | 0 |  | 0 | 0
90 | 104/2014, Gr-2 | P1 | 12th Plan Old Projects | Page No. 210, Sl. No. 137 of MYT Order | PCC and Gravel spreading is working area of switchyard at 132/33 KV GSS Udakishanganj, NIT-104/2014, Gr-2 | DCB | [6 empty] | State Plan | 0 | 0.42 | 0 | 0.11478 |  |  | 0.42 | 0.11478 |  |  |  | 0.42 | 0.11478 |  |  |  | 0.42 | 0.11478 |  |  |  | 0.42 | 0.11478 |  |  |  | 0.42 | 0.11478 |  | 0 | 0 |  | 0 | 0
91 | 104/2014, Gr 8 | P1 | 12th Plan Old Projects | Page No. 210, Sl. No. 138 of MYT Order | For the work of Earth filling & Construction of boundary wall around the periphery of acquired land for 132/33 KV Gss Campus Kataiya, NIT- 104/2014, Gr 8 | DCB | [6 empty] | State Plan | 0 | 2.97 | 0 |  |  |  | 2.97 | 0 |  |  |  | 2.97 | 0 |  |  |  | 2.97 | 0 |  |  |  | 2.97 | 0 |  |  |  | 2.97 | 0 |  | 0 | 0 |  | 0 | 0
92 | 11/2015, Gr 2 | P1 | 12th Plan Old Projects | Page No. 210, Sl. No. 139 of MYT Order | Construction of North, South & West Side boundry wall at GSS Katra under State Plan, NIT 11/2015, Gr 2 | DCB | [6 empty] | State Plan | 0 | 0 | 1.01 |  |  |  | 0 | 1.01 |  |  |  | 0 | 1.01 |  |  |  | 0 | 1.01 |  |  |  | 0 | 1.01 |  |  |  | 0 | 1.01 |  | 0 | 0 |  | 0 | 0
93 | 41/2015, Pkg A | P1 | 12th Plan Old Projects | Page No. 210, Sl. No. 140 of MYT Order | Construction of 15ft Wide PCC Road at 132/33KV GSS Hathidah, NIT-41/2015, Pkg A | DCB | [5 empty] | 106.69 | State Plan | 72.43 | 0.53 | 0 |  |  |  | 0.53 | 0 |  |  |  | 0.53 | 0 |  |  |  | 0.53 | 0 |  |  |  | 0.53 | 0 |  |  |  | 0.53 | 0 |  | 0 | 0 |  | 0 | 0
94 |  | P1 | 12th Plan Old Projects | Page No. 210, Sl. No. 142 of MYT Order | Reconductoring of 132 KV SC BTPS Naugachiapur transmission line and 132 KV Baripahari Fathua Gaighat Mithapur Jakanpur with panther conductor | DCB | [6 empty] | BRGF | 0 | 0 | 1 |  |  |  | 0 | 1 |  |  |  | 0 | 1 |  |  |  | 0 | 1 |  |  |  | 0 | 1 |  |  |  | 0 | 1 |  |  | 0 |  |  | 0
95 | 71/2014 | P1 | 12th Plan Old Projects | Page No. 210, Sl. No. 143 of MYT Order | R&M work at Sitamarhi, Ramnagar,Pandaul, Chapra ans Siwan (71/PR/BSPTCL/2014) | DCB | 2 | 21.03.2015 | 21.03.2015 | 20.03.2016 | 33.49 |  | BRGF | 35.37 | 0 | 36.49 | 0.44851 |  |  | 0 | 36.9385 |  |  |  | 0 | 36.9385 |  |  |  | 0 | 36.9385 |  |  |  | 0 | 36.9385 |  |  |  | 0 | 36.9385 |  |  | 0 |  |  | 0
96 | 16/2016 | P1 | 12th Plan Old Projects | Page No. 210, Sl. No. 145 of MYT Order | Construction of 2No.132KV line bays each at 132/33 KV GSS Banka (old) and Jammu (old) total 4 No.s of Bay, NIT- 16/2016 | DCB | [6 empty] | State Plan | 0 | 0.12 | 0 |  |  |  | 0.12 | 0 |  |  |  | 0.12 | 0 |  |  |  | 0.12 | 0 |  |  |  | 0.12 | 0 |  |  |  | 0.12 | 0 |  | 0 | 0 |  | 0 | 0
97 | 18/2016 | P1 | 12th Plan Old Projects | Page No. 210, Sl. No. 146 of MYT Order | Construction of 132Kv D/C Transmission Line from Banka- Banka(New),NIT-18/2016 | DCB | [6 empty] | State Plan | 0 | 0.71 | 0 |  |  |  | 0.71 | 0 |  |  |  | 0.71 | 0 |  |  |  | 0.71 | 0 |  |  |  | 0.71 | 0 |  |  |  | 0.71 | 0 |  | 0 | 0 |  | 0 | 0
98 | 24/PR/BSPTCL/2014 | P1 | 12th Plan Old Projects | Page No. 210, Sl. No. 147 of MYT Order | 132/33 KV GSS Siwan - Main Bus & Other Works(24/PR/BSPTCL/2014) | DCB | [6 empty] | BRGF | 0 | 0.18 | 0 | 0.076574 |  |  | 0.18 | 0.076574 |  |  |  | 0.18 | 0.076574 |  |  |  | 0.18 | 0.076574 |  |  |  | 0.18 | 0.076574 |  |  |  | 0.18 | 0.076574 |  |  | 0 |  |  | 0
99 | 26/2015 | P1 | 12th Plan Old Projects | Page No. 210, Sl. No. 148 of MYT Order | Work of Assembly of 50 MVA Transformer including all work of erection ,testing and Commissioning'at GSS Purnea, Arraia, Dhamdaha, Dalsinghsarai, Pandaul, Madhubani, NIT-26/2015 | DCB | 6 | 2015-08-13 | 2015-08-13 | 2016-06-12 | 43.08 | 60 | State Plan | 43.08 | 5.92 | 0 |  |  |  | 5.92 | 0 |  |  |  | 5.92 | 0 |  |  |  | 5.92 | 0 |  |  |  | 5.92 | 0 |  |  |  | 5.92 | 0 |  | 0 | 0 |  | 0 | 0
100 | 26/2015, GR 3 | P1 | 12th Plan Old Projects | Page No. 211, Sl. No. 150 of MYT Order | Reconstruction of Boundary Wall at 132/33KV GSS Samastipur NIT-26/2015, GR 3 | DCB | [6 empty] | State Plan | 0 | 0.21 | 0 |  |  |  | 0.21 | 0 |  |  |  | 0.21 | 0 |  |  |  | 0.21 | 0 |  |  |  | 0.21 | 0 |  |  |  | 0.21 | 0 |  | 0 | 0 |  | 0 | 0
101 | 26/2015 Gr 4 | P1 | 12th Plan Old Projects | Page No. 211, Sl. No. 151 of MYT Order | Construction of Drainage system at 132/33 KV GSS Campur Arrah NIT-26/2015 Gr 4 | DCB | [6 empty] | State Plan | 0 | 0.13 | 0 |  |  |  | 0.13 | 0 |  |  |  | 0.13 | 0 |  |  |  | 0.13 | 0 |  |  |  | 0.13 | 0 |  |  |  | 0.13 | 0 |  | 0 | 0 |  | 0 | 0
102 | 26/2016, GR 4 | P1 | 12th Plan Old Projects | Page No. 211, Sl. No. 152 of MYT Order | Construction of Double storied control room building including electrical illumination & fitting at 132/33kv GSS Kataiya NIT-26/2016, GR 4 | DCB | [6 empty] | State Plan | 0 | 1.45 | 0 |  |  |  | 1.45 | 0 |  |  |  | 1.45 | 0 |  |  |  | 1.45 | 0 |  |  |  | 1.45 | 0 |  |  |  | 1.45 | 0 |  | 0 | 0 |  | 0 | 0
103 | 90/2015 | P1 | 12th Plan Old Projects | Page No. 211, Sl. No. 158 of MYT Order | Construction of 2x50 MVA, 132/33 KV GSS at Bhabhua , NIT-90/2015 | DCB | [6 empty] | State Plan | 0 | 1.27 | 0 |  |  |  | 1.27 | 0 |  |  |  | 1.27 | 0 |  |  |  | 1.27 | 0 |  |  |  | 1.27 | 0 |  |  |  | 1.27 | 0 |  | 0 | 0 |  | 0 | 0
104 | 02/PR/BSPTCL/2016 | P1 | 12th Plan Old Projects | Page No. 211, Sl. No. 160 of MYT Order | Construction of associated 132 KV line Bays (No. of Bays-05) for second Circuit Stringing of existing 132 KV double Circuit Single Strung NIT No. 02/PR/BSPTCL/2016/State Plan | DCB | [6 empty] | State Plan | 0 | 8.4 | 0 |  |  |  | 8.4 | 0 |  |  |  | 8.4 | 0 |  |  |  | 8.4 | 0 |  |  |  | 8.4 | 0 |  |  |  | 8.4 | 0 |  | 0 | 0 |  | 0 | 0
105 | 315/2013 | P1 | 12th Plan Old Projects | Page No. 212, Sl. No. 161 of MYT Order | Work of capacity augmentation of 132/33GSS Forbesganj,Katihar, Kishanganj , and Saharsa NIT No. 315/2013 | DCB | 3 | 03.12.2013 | 03.12.2013 | 02.03.2015 | 31.43 | 38.93 | BRGF | 32.67 | 31.88 | 0 |  |  |  | 31.88 | 0 |  |  |  | 31.88 | 0 |  |  |  | 31.88 | 0 |  |  |  | 31.88 | 0 |  |  |  | 31.88 | 0 |  |  | 0 |  |  | 0
106 | 301/2015 | P1 | 12th Plan Old Projects | Page No. 212, Sl. No. 162 of MYT Order | capacity augmention of 220/132/33KV GSS Bodh Gaya, NIT-301/2015 | DCB | [6 empty] | BRGF | 0 | 9.56 | 0 |  |  |  | 9.56 | 0 |  |  |  | 9.56 | 0 |  |  |  | 9.56 | 0 |  |  |  | 9.56 | 0 |  |  |  | 9.56 | 0 |  |  | 0 |  |  | 0
107 | 427/2013 D | P1 | 12th Plan Old Projects | Page No. 212, Sl. No. 163 of MYT Order | R&M work of 132/33 KV GSS at Sultanganj, Sabour & Kahalgaon. NIT-427/2013 D | DCB | 2 | 04.03.2014 | 04.03.2014 | 03.03.2015 | 16.33 |  | BRGF | 15.97 | 16.41 | 0 |  |  |  | 16.41 | 0 |  |  |  | 16.41 | 0 |  |  |  | 16.41 | 0 |  |  |  | 16.41 | 0 |  |  |  | 16.41 | 0 |  |  | 0 |  |  | 0
108 | 427/2013 Pkg-E | P1 | 12th Plan Old Projects | Page No. 212, Sl. No. 165 of MYT Order | R&M Work of 132/33 Kv GSS Saharsha and Katihar NIT No. 427/2013 Pkg-E | DCB | 1 | 04.03.2014 | 04.03.2014 | 03.03.2015 | 10 |  | BRGF | 11.47 | 0.25 | 0 |  |  |  | 0.25 | 0 |  |  |  | 0.25 | 0 |  |  |  | 0.25 | 0 |  |  |  | 0.25 | 0 |  |  |  | 0.25 | 0 |  |  | 0 |  |  | 0
109 | 31/2015 | P1 | 12th Plan Old Projects | Page No. 212, Sl. No. 166 of MYT Order | Construction of Tr Ln Purnea - Saharsha NIT No. 31/2015 | DCB | [6 empty] | State Plan | 112.73 | 111.84 | 0 |  |  |  | 111.84 | 0 |  |  |  | 111.84 | 0 |  |  |  | 111.84 | 0 |  |  |  | 111.84 | 0 |  |  |  | 111.84 | 0 |  | 0 | 0 |  | 0 | 0
110 | 168/2014, Pkg B | P1 | 12th Plan Old Projects | Page No. 212, Sl. No. 167 of MYT Order | Re-condunctoring of220 KV D/C Biharsharif- Bodhgaya Transmission Line, NIT-168/2014, Pkg B | DCB | [6 empty] | BRGF | 0 | 0.55 | 0 |  |  |  | 0.55 | 0 |  |  |  | 0.55 | 0 |  |  |  | 0.55 | 0 |  |  |  | 0.55 | 0 |  |  |  | 0.55 | 0 |  |  | 0 |  |  | 0
111 | 89/2013 | P1 | 12th Plan Old Projects | Page No. 212, Sl. No. 168 of MYT Order | Earth Filling and Construction Of Boundary wall of Proposed land for 220/132/33KV GSS Supaul (Laukahi), NIT-89/2013 | DCB | [6 empty] | BRGF | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  | 0 |  |  | 0
112 | 467/2013 | P1 | 12th Plan Old Projects | Page No. 212, Sl. No. 169 of MYT Order | Earth Filling and Construction Of Boundary wall of Proposed land for 220/132/33KV GSS Samastipur, NIT-467/2013 | DCB | [6 empty] | BRGF | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  | 0 |  |  | 0
113 | 28/2016 | P1 | 12th Plan Old Projects | Page No. 212, Sl. No. 174 of MYT Order | Construction of drain along road and expended metalfencing in area of proposed 132 KV line Kv GSS jandaha NIT No. 28/2016 | DCB | [6 empty] | State Plan | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
114 | 482/PR/BSPTCL/2013 | P1 | 12th Plan Old Projects | Page No. 213, Sl. No. 175 of MYT Order | Construction Of 132 KV bay Extension at remote at GSS samastipur NIT No.- 482/PR/BSPTCL/2013 | DCB | [6 empty] | BRGF | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  | 0 |  |  | 0
115 | 97/2015 | P1 | 12th Plan Old Projects | Page No. 213, Sl. No. 177 of MYT Order | Construction of Bays at GSS Gaihat, 97/2015 | DCB | [6 empty] | BRGF | 0 | 0 | 0.14 |  |  |  | 0 | 0.14 |  |  |  | 0 | 0.14 |  |  |  | 0 | 0.14 |  |  |  | 0 | 0.14 |  |  |  | 0 | 0.14 |  |  | 0 |  |  | 0
116 |  | P1 | 12th Plan Old Projects | Page No. 213, Sl. No. 178 of MYT Order | Being consultancy charge paid to PGCIL for towards construction of 02 nos. 132 KV bays at 400/220 KV GSS Banka (PG) for evacuation of power from 400/220 KV Banka (PG) | DCB | [6 empty] | IRF | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  | 0 |  |  | 0
117 |  | P1 | 12th Plan Old Projects | Page No. 213, Sl. No. 179 of MYT Order | Capital Expenditure - Deposit Works | DCB | [6 empty] | Deposit Work | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0
118 | 01/2015 | P1 | 12th Plan Old Projects | Page No. 213, Sl. No. 180 of MYT Order | Constriction of 132 KV SC trans line on DC tower from GSS Dalsinghsarai to TSS Bachwara and construction of 01 no. 132 KV line bay at Dalsinghsarai GSS to feed power to TSS Bachwara , NIT-01/2015 | DCB | [6 empty] | Deposit Work | 0 | 7.99 | 0 |  |  |  | 7.99 | 0 |  |  |  | 7.99 | 0 |  |  |  | 7.99 | 0 |  |  |  | 7.99 | 0 |  |  |  | 7.99 | 0 | 0
119 | 181/2011 | P1 | 12th Plan Old Projects | Page No. 213, Sl. No. 181 of MYT Order | Augmentation of 132 KV GSS Kahalgaon by 1 X 50 MVA 132/33 KV power transformer and construction of one no. 132 KV bay and 03 nos. 33 KV bays , NIT-181/2011 | DCB | [6 empty] | Deposit Work | 0 | 0 | 0.31 |  |  |  | 0 | 0.31 |  |  |  | 0 | 0.31 |  |  |  | 0 | 0.31 |  |  |  | 0 | 0.31 |  |  |  | 0 | 0.31 | 0
120 | 23/2013 | P1 | 12th Plan Old Projects | Page No. 213, Sl. No. 182 of MYT Order | Augmentation of 132 KV GSS Kahalgaon by 1 X 50 MVA 132/33 KV power transformer and construction of one no. 132 KV bay and 03 nos. 33 KV bays , NIT-23/2013 | DCB | [6 empty] | Deposit Work | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0
121 | 27/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 214, Sl. No. 184 of MYT Order | Construction of 132KV traction transmission line (2-phase strung) on D/C tower with ACSR panther conductor between GSS Runnisaidpur & TSS Bajpatti GSS Narkatiyaganj-TSS Raxaul GSS Dhaka - TSS Bairgania , NIT-27/2018 | DCB | [6 empty] | Deposit Work | 7.19 | 10.62 | 34.8138 | 0.056998 |  |  | 10.62 | 34.8708 | 0.04 |  |  | 10.62 | 34.9108 |  |  |  | 10.62 | 34.9108 |  |  |  | 10.62 | 34.9108 |  |  |  | 10.62 | 34.9108 | 0.04 | [8 empty] | 0.04
122 | 29/2016 | P1 | 12th Plan Old Projects | Page No. 214, Sl. No. 185 of MYT Order | Construction of 132 KV D/C transmission Line over river crossing span with ACSR Panther conductor on turnkey basis , NIT-29/2016 | DCB | [6 empty] | Deposit Work | 0 | 15.84 | 7.17 |  |  |  | 15.84 | 7.17 |  |  |  | 15.84 | 7.17 |  |  |  | 15.84 | 7.17 |  |  |  | 15.84 | 7.17 |  |  |  | 15.84 | 7.17 | 0
123 | 49/2016 | P1 | 12th Plan Old Projects | Page No. 214, Sl. No. 187 of MYT Order | for supply/delivery of equipments required for shifting/height raising of 132KV D/C transmission line(Sonenagar-Garhwa-Rihand) ,NIT-49/2016 | DCB | [6 empty] | Deposit Work | 0 | 1.0313 | -0.0013268 |  |  |  | 1.0313 | -0.0013268 | 0.1 |  |  | 1.0313 | 0.098673 |  |  |  | 1.0313 | 0.098673 |  |  |  | 1.0313 | 0.098673 |  |  |  | 1.0313 | 0.098673 | 0.1 | [8 empty] | 0.1
124 | 77/2014 | P1 | 12th Plan Old Projects | Page No. 214, Sl. No. 189 of MYT Order | Construction of 132 KV L4 & L5 line Bays at BTPS after dismentling old existing bays on turnkey basis, NIT-77/2014 | DCB | [6 empty] | Deposit Work | 3.1 | 0 | 3.38 |  |  |  | 0 | 3.38 |  |  |  | 0 | 3.38 |  |  |  | 0 | 3.38 |  |  |  | 0 | 3.38 |  |  |  | 0 | 3.38 | 0
125 | 98/2015 | P1 | 12th Plan Old Projects | Page No. 214, Sl. No. 190 of MYT Order | Dismantling of 04 nos. Towers of 132 KV SC trans line from LOC No. 254 to 257 and its rerouting and construction of 01 Nos 132 KV line bay at GSS Madhepura, NIT-98/2015 | DCB | 3 | 13.06.2016 | 13.06.2016 | 12.03.2017 | 5.49 | 5.16 | Deposit Work | 4.57 | 4.48 | 0 |  |  |  | 4.48 | 0 |  |  |  | 4.48 | 0 |  |  |  | 4.48 | 0 |  |  |  | 4.48 | 0 |  |  |  | 4.48 | 0 | 0
126 |  | P1 | 12th Plan Old Projects | Page No. 214, Sl. No. 191 of MYT Order | Other Misc. Deposit | DCB | [6 empty] | Deposit Work | 0 | 0.81 | 16.02 |  |  |  | 0.81 | 16.02 |  |  |  | 0.81 | 16.02 |  |  |  | 0.81 | 16.02 |  |  |  | 0.81 | 16.02 |  |  |  | 0.81 | 16.02 | 0
127 |  | P1 | 12th Plan Old Projects | Page No. 214, Sl. No. 192 of MYT Order | Deposit-Office Equipment | DCB | [6 empty] | Deposit Work | 0 | 0 | 0.92 |  |  |  | 0 | 0.92 |  |  |  | 0 | 0.92 |  |  |  | 0 | 0.92 |  |  |  | 0 | 0.92 |  |  |  | 0 | 0.92 | 0
128 | 04/2017 | P1 | 12th Plan Old Projects | Page No. 215, Sl. No. 194 of MYT Order | Construction Of 132KV two phase railway trans. Line from 132/33 KV GSS Nalanda To TSS Nalanda (Approx 06KM) and construction of 01 no. dedicated 132kv line bay at 132/33KV Nalanda, NIT-4/2017 | DCB | [6 empty] | Deposit Work | 0 | 1.7 | 0 |  |  |  | 1.7 | 0 |  |  |  | 1.7 | 0 |  |  |  | 1.7 | 0 |  |  |  | 1.7 | 0 |  |  |  | 1.7 | 0 | 0
129 |  | P1 | 12th Plan Old Projects | Page No. 215, Sl. No. 195 of MYT Order | Building WIP | DCB | [6 empty] | State Plan | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
130 |  | P1 | 12th Plan Old Projects | Page No. 215, Sl. No. 196 of MYT Order | Office Eqipment' | DCB | [6 empty] | State Plan | 0 | 0 | 0.03 |  |  |  | 0 | 0.03 |  |  |  | 0 | 0.03 |  |  |  | 0 | 0.03 |  |  |  | 0 | 0.03 |  |  |  | 0 | 0.03 |  | 0 | 0 |  | 0 | 0
131 |  | P1 | 12th Plan Old Projects | Page No. 215, Sl. No. 197 of MYT Order | Land | DCB | [6 empty] | State Plan | 0 | 0 | 4.2 |  |  |  | 0 | 4.2 |  | 21.8192 |  | 21.8192 | -17.6192 |  |  |  | 21.8192 | -17.6192 |  |  |  | 21.8192 | -17.6192 |  |  |  | 21.8192 | -17.6192 |  | 0 | 0 |  | 0 | 0
132 |  | P1 | 12th Plan Old Projects | Page No. 215, Sl. No. 198 of MYT Order | Common Pool | DCB | [6 empty] | State Plan | 0 | 132.58 | 506.5453 |  |  |  | 132.58 | 506.5453 |  |  |  | 132.58 | 506.5453 |  |  |  | 132.58 | 506.5453 |  |  |  | 132.58 | 506.5453 |  |  |  | 132.58 | 506.5453 |  | 0 | 0 |  | 0 | 0
133 | 22/PR/BSPTCL/2017 | P1 | 12th Plan Old Projects | Page No. 215, Sl. No. 199 of MYT Order | Furniture (22/PR/BSPTCL/2017) | DCB | [6 empty] | IRF | 0 | 0 | 0.19 |  |  |  | 0 | 0.19 |  |  |  | 0 | 0.19 |  |  |  | 0 | 0.19 |  |  |  | 0 | 0.19 |  |  |  | 0 | 0.19 |  |  | 0 |  |  | 0
134 |  | P1 | 12th Plan Old Projects | Page No. 215, Sl. No. 200 of MYT Order | NIT-11/2016, construction of two no 33 KV line bays Grid Sub-Station at Supaul on turnkey basis |  | 3 | 04.05.2016 | 04.05.2016 | 03.10.2016 | 0.92 |  | IRF | 0.95 | 0.87 | 0 |  |  |  | 0.87 | 0 |  |  |  | 0.87 | 0 |  |  |  | 0.87 | 0 |  |  |  | 0.87 | 0 |  |  |  | 0.87 | 0 |  |  | 0 |  |  | 0
135 | 58/PR/BSPCL/2015 | P1 | 12th Plan Old Projects | Page No. 215, Sl. No. 201 of MYT Order | 33KV line bay at GSS Raxaul for 33/11 KV PSS Maina Tand (58/PR/BSPCL/2015) | [7 empty] | IRF | 0.54 | 0.53 | 0 |  |  |  | 0.53 | 0 |  |  |  | 0.53 | 0 |  |  |  | 0.53 | 0 |  |  |  | 0.53 | 0 |  |  |  | 0.53 | 0 |  |  | 0 |  |  | 0
136 | 33/PR/BSPTCL/2017 | P1 | 12th Plan Old Projects | Page No. 215, Sl. No. 202 of MYT Order | Construction of four nos of 132KV single circuit transmission line (2-phase strung) from GSS Motipur to TSS Mahawal, GSS Motihari to TSS Jivdhara, GSS Bettiah to TSS Majhaulia and GSS Ramnagar to TSS Harinagar (33/PR/BSPTCL/2017) | [7 empty] | Deposit Work | 15.12 | 14.85 | 0 |  |  |  | 14.85 | 0 |  |  |  | 14.85 | 0 |  |  |  | 14.85 | 0 |  |  |  | 14.85 | 0 |  |  |  | 14.85 | 0 | 0
137 | 34/PR/BSPTCL/2017 | P1 | 12th Plan Old Projects | Page No. 215, Sl. No. 203 of MYT Order | power supply from GSS Motipur to Mahaval, GSS Motihari to TSS Jivdhara, GSS Bettiah to TSS Majhaulia, GSS Ramnagar to TSS Harinagar (34/PR/BSPTCL/2017) | [7 empty] | Deposit Work | 5.19 | 14.76 | 0 |  |  |  | 14.76 | 0 | 0.04 |  |  | 14.76 | 0.04 |  |  |  | 14.76 | 0.04 |  |  |  | 14.76 | 0.04 |  |  |  | 14.76 | 0.04 | 0.04 | [8 empty] | 0.04
138 | 35/PR/BSPTCL/2017 | - | 12th Plan Old Projects | Page No. 215, Sl. No. 204 of MYT Order | For design, manufacture, testing at manufacture’s works and delivery of equipments required for restoration of different transmission lines(Total-06 nos) of BSPTCL by constructing pile foundations (Total-14 no’s)/Height rising (01 no) on turnkey basis under O & M Head on firm price | [7 empty] | IRF | 17.2 | 17.1782 | -8.9569 |  |  |  | 17.1782 | -8.9569 |  |  |  | 17.1782 | -8.9569 |  |  |  | 17.1782 | -8.9569 |  |  |  | 17.1782 | -8.9569 |  |  |  | 17.1782 | -8.9569 |  |  | 0 |  |  | 0
139 | 36/2017, Gr-04 | P1 | 12th Plan Old Projects | Page No. 215, Sl. No. 205 of MYT Order | Special repair and maintenance of B &C type quarter, Guard Room, Parking Shed and control room building at 132/33 KV GSS Dhaka, NIT- 36/2017, Gr-04 | [7 empty] | IRF | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  | 0 |  |  | 0
140 | 10/PR/BSPCL/2015 | P1 | 12th Plan Old Projects | Page No. 216, Sl. No. 206 of MYT Order | for transportation, insurance, installation erection incuding associated civil works testing and commissioning and performance Testing for construction of 132 KV line bays, one at sabour & Banka (10/PR/BSPCL/2015) | [7 empty] | IRF | 0 | 0.15 | 0 |  |  |  | 0.15 | 0 |  |  |  | 0.15 | 0 |  |  |  | 0.15 | 0 |  |  |  | 0.15 | 0 |  |  |  | 0.15 | 0 |  |  | 0 |  |  | 0
141 | 16/PR/BSPCL/2017 | P1 | 12th Plan Old Projects | Page No. 216, Sl. No. 207 of MYT Order | Supply and installation of 138 nos. 2T 5star split Air- conditioner with sablizer and A.C. Wiring at 46 nos. GSS i.e. 03 nos. 2T 5star split Air- Conditioners each at 46 nos GSS (16/PR/BSPCL/2017) | [7 empty] | IRF | 0.96 | 0 | 0.8 |  |  |  | 0 | 0.8 |  |  |  | 0 | 0.8 |  |  |  | 0 | 0.8 |  |  |  | 0 | 0.8 |  |  |  | 0 | 0.8 |  |  | 0 |  |  | 0
142 | 26/PR/BSPCL/2017 | P1 | 12th Plan Old Projects | Page No. 216, Sl. No. 208 of MYT Order | design, manufacture, testing ,supply and delivery of 33 KV Current Transformers of different rating (26/PR/BSPCL/2017) | [7 empty] | IRF | 0 | 0 | 0.21 |  |  |  | 0 | 0.21 |  |  |  | 0 | 0.21 |  |  |  | 0 | 0.21 |  |  |  | 0 | 0.21 |  |  |  | 0 | 0.21 |  |  | 0 |  |  | 0
143 | 33/PR/BSPCL/2016 | P1 | 12th Plan Old Projects | Page No. 216, Sl. No. 209 of MYT Order | for erection and commissioning of 27 No’s. ACDB and 28 No’s DCDB (for 40 Nos. feeder((33/PR/BSPCL/2016) | [7 empty] | IRF | 0 | 0 | 0.13 |  |  |  | 0 | 0.13 |  |  |  | 0 | 0.13 |  |  |  | 0 | 0.13 |  |  |  | 0 | 0.13 |  |  |  | 0 | 0.13 |  |  | 0 |  |  | 0
144 | 40/PR/BSPTCL/2017 Package-B | P1 | 12th Plan Old Projects | Page No. 216, Sl. No. 210 of MYT Order | for procurement of different type and Sizes of Power & Control Cables and cable termination kits package B:-33KV and 132KV cables & termination kit (40/PR/BSPTCL/2017 Package-B ) | [7 empty] | IRF | 0 | 0 | 1.52 |  |  |  | 0 | 1.52 |  |  |  | 0 | 1.52 |  |  |  | 0 | 1.52 |  |  |  | 0 | 1.52 |  |  |  | 0 | 1.52 |  |  | 0 |  |  | 0
145 | 53/2016 | P1 | 12th Plan Old Projects | Page No. 216, Sl. No. 211 of MYT Order | for supply and retrofifitting/installation of differential protection relay to be used in Grid Sub-Station of BSPTCL, NIT-53/2016 | [7 empty] | IRF | 0.71 | 0 | 0.22 |  |  |  | 0 | 0.22 |  |  |  | 0 | 0.22 |  |  |  | 0 | 0.22 |  |  |  | 0 | 0.22 |  |  |  | 0 | 0.22 |  |  | 0 |  |  | 0
146 | 96/2016 | P1 | 12th Plan Old Projects | Page No. 216, Sl. No. 212 of MYT Order | Restoration work of collapsed tower of 132 KV DC Kahalgoan-Sultanganj Trans. Line., NIT- 96/2016 | [7 empty] | IRF | 0 | 0 | 4.72 |  |  |  | 0 | 4.72 |  |  |  | 0 | 4.72 |  |  |  | 0 | 4.72 |  |  |  | 0 | 4.72 |  |  |  | 0 | 4.72 |  |  | 0 |  |  | 0
147 | 98/PR/BSPTCL/2015 | P1 | 12th Plan Old Projects | Page No. 216, Sl. No. 213 of MYT Order | supply of equipment and material for Construction of one no 33 KV Grid Sub-Station at Raxual for 33/11 KV PSS Mainatand (98/PR/BSPTCL/2015) | [7 empty] | IRF | 0 | 0 | 0.18 |  |  |  | 0 | 0.18 |  |  |  | 0 | 0.18 |  |  |  | 0 | 0.18 |  |  |  | 0 | 0.18 |  |  |  | 0 | 0.18 |  |  | 0 |  |  | 0
148 |  | P1 |  | Page No. 173, Sl. No. 90 of MYT Order | Misc. Others IRF | [7 empty] | IRF | 0 | 24.64 | 13.56 | -13.2334 |  |  | 24.64 | 0.3266 |  |  |  | 24.64 | 0.3266 |  |  |  | 24.64 | 0.3266 |  |  |  | 24.64 | 0.3266 |  |  |  | 24.64 | 0.3266 |  |  | 0 |  |  | 0
149 |  | P1 | 12th Plan Old Projects | Page No. 173, Sl. No. 92 of MYT Order | Computer & Accessories | [7 empty] | ADB | 0 | 0 | 0.16 |  |  |  | 0 | 0.16 |  |  |  | 0 | 0.16 |  |  |  | 0 | 0.16 |  |  |  | 0 | 0.16 |  |  |  | 0 | 0.16
150 |  | P1 | 12th Plan Old Projects | Page No. 173, Sl. No. 93 of MYT Order | Procurement and Construction of 220/132KV Sub-station at Pusauli and addittional 02 nos. of 220KV bays at existing Dehri Grid Sub-station | [7 empty] | ADB | 0 | 1.16 | 0 |  |  |  | 1.16 | 0 |  |  |  | 1.16 | 0 |  |  |  | 1.16 | 0 |  |  |  | 1.16 | 0 |  |  |  | 1.16 | 0
151 | 36/2017, Gr-01 | P1 | 12th Plan Old Projects | Page No. 173, Sl. No. 93 of MYT Order | Special repair and maintenance of division office and construction of 1 unit septic tanks at 132/33 KV Campus, Motihari NIT-36/2017, Gr-01 | [7 empty] | IRF | 0 | 0.12 | 0 |  |  |  | 0.12 | 0 |  |  |  | 0.12 | 0 |  |  |  | 0.12 | 0 |  |  |  | 0.12 | 0 |  |  |  | 0.12 | 0 |  |  | 0 |  |  | 0
152 | 10/PR/BSPTCL/2020 | P1 | 12th Plan Old Projects | Page No. 174, Sl. No. 94 of MYT Order | For Re-Construction of Damaged Eastern Side Boundary Wall at 132/33Kv GSS, Digha. , 10/PR/BSPTCL/2020 | [7 empty] | IRF | 0 | 0.8 | 0 |  |  |  | 0.8 | 0 |  |  |  | 0.8 | 0 |  |  |  | 0.8 | 0 |  |  |  | 0.8 | 0 |  |  |  | 0.8 | 0 |  |  | 0 |  |  | 0
153 | 102/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 174, Sl. No. 95 of MYT Order | Local sand filling , PCC and Gravel work in switchyard at 132/33 KV GSS Mithapur, 102/PR/BSPTCL/2018 Sl. No-02 | [7 empty] | IRF | 0 | 0.78 | 0 |  |  |  | 0.78 | 0 |  |  |  | 0.78 | 0 |  |  |  | 0.78 | 0 |  |  |  | 0.78 | 0 |  |  |  | 0.78 | 0 |  |  | 0 |  |  | 0
154 | 11/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 174, Sl. No. 96 of MYT Order | Earth Filling and Construction of Boundary wall with espanded metal fencing for construction of 02 nos. 132 kV line bay at 132/33 kv GSS Supaul, 11/PR/BSPTCL/2018 | [7 empty] | IRF | 0 | 0.22 | 0 |  |  |  | 0.22 | 0 |  |  |  | 0.22 | 0 |  |  |  | 0.22 | 0 |  |  |  | 0.22 | 0 |  |  |  | 0.22 | 0 |  |  | 0 |  |  | 0
155 | 99/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 174, Sl. No. 97 of MYT Order | Supply & Installation of Furniture in different GSS, 99/PR/BSPTCL/2018 | [7 empty] | IRF | 0 | 0.92 | 0 |  |  |  | 0.92 | 0 |  |  |  | 0.92 | 0 |  |  |  | 0.92 | 0 |  |  |  | 0.92 | 0 |  |  |  | 0.92 | 0 |  |  | 0 |  |  | 0
156 | 115/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 174, Sl. No. 98 of MYT Order | Implementation of Balance Work Of Scheduling , Accounting Metering and Settlement of Transaction(Samast) in Bihar, - 115/PR/BSPTCL/2018 | [7 empty] | IRF | 0 | 8.22 | 0 |  |  |  | 8.22 | 0 |  |  |  | 8.22 | 0 |  |  |  | 8.22 | 0 |  |  |  | 8.22 | 0 |  |  |  | 8.22 | 0 |  |  | 0 |  |  | 0
157 | 117/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 174, Sl. No. 99 of MYT Order | Special repair and maintenance of IB and construction of septic tanks at 132/33 KV GSS Motihari, 117/PR/BSPTCL/2018 Sl. No.:-02, 03 | [7 empty] | IRF | 0 | 0.18 | 0.4 |  |  |  | 0.18 | 0.4 |  |  |  | 0.18 | 0.4 |  |  |  | 0.18 | 0.4 |  |  |  | 0.18 | 0.4 |  |  |  | 0.18 | 0.4 |  |  | 0 |  |  | 0
158 | 123/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 174, Sl. No. 100 of MYT Order | Construction of cable trench in switchyard at 220/132/33 KV Super Grid Biharsharif, 123/PR/BSPTCL/2018 | [7 empty] | IRF | 0 | 1.17 | 0 |  |  |  | 1.17 | 0 |  |  |  | 1.17 | 0 |  |  |  | 1.17 | 0 |  |  |  | 1.17 | 0 |  |  |  | 1.17 | 0 |  |  | 0 |  |  | 0
159 | 13/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 174, Sl. No. 101 of MYT Order | Special repair and maintance of GM cum CE residence (A type) including electrical work at 132/33 KV GSS muzaffarpur, 13/PR/BSPTCL/2018 | [7 empty] | IRF | 0 | 0.08 | 0 |  |  |  | 0.08 | 0 |  |  |  | 0.08 | 0 |  |  |  | 0.08 | 0 |  |  |  | 0.08 | 0 |  |  |  | 0.08 | 0 |  |  | 0 |  |  | 0
160 | 13/PR/BSPTCL/2019 | P1 | 13th Plan Other Project | Page No. 174, Sl. No. 102 of MYT Order | Construction of 220 KV line bay at 220/132/33KV GSS Darbhanga & PCC for Construction of 02 Nos, 132 KV line bays at GSS Supaul (Existing), NIT-13/PR/BSPTCL/2019 | [7 empty] | IRF | 0 | 1.767 | 0.36 |  |  |  | 1.767 | 0.36 |  |  |  | 1.767 | 0.36 |  |  |  | 1.767 | 0.36 |  |  |  | 1.767 | 0.36 |  |  |  | 1.767 | 0.36 |  |  | 0 |  |  | 0
161 | 132/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 175, Sl. No. 103 of MYT Order | construction of store shed at campus of transmission circle office sabour, Bhagalpur , 132/PR/BSPTCL/2018 | [7 empty] | IRF | 0 | 0.32 | 0 |  |  |  | 0.32 | 0 |  |  |  | 0.32 | 0 |  |  |  | 0.32 | 0 |  |  |  | 0.32 | 0 |  |  |  | 0.32 | 0 |  |  | 0 |  |  | 0
162 | 14/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 175, Sl. No. 104 of MYT Order | Renovation and rising height of boundary wall of 220/132 KV GSS Campus Gaurichak, 14/PR/BSPTCL/2018 | [7 empty] | IRF | 0 | 1.08 | 0.09 |  |  |  | 1.08 | 0.09 |  |  |  | 1.08 | 0.09 |  |  |  | 1.08 | 0.09 |  |  |  | 1.08 | 0.09 |  |  |  | 1.08 | 0.09 |  |  | 0 |  |  | 0
163 | 41/PR/BSPTCL/2019 | P1 | 13th Plan Other Project | Page No. 175, Sl. No. 105 of MYT Order | Renovation work of IB including Electrical wiring & Supply of Furniture at 132/33 KV GSS Muzaffarpur, 41/PR/BSPTCL/2019 | [7 empty] | IRF | 0 | 0.44 | 0 |  |  |  | 0.44 | 0 |  |  |  | 0.44 | 0 |  |  |  | 0.44 | 0 |  |  |  | 0.44 | 0 |  |  |  | 0.44 | 0 |  |  | 0 |  |  | 0
164 | 97/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 175, Sl. No. 106 of MYT Order | For enovation of Store -1 and 2 for transmission Division T&C Division & L&M Division office at 132/33Kv GSS Chhapra., 97/PR/BSPTCL/2018, Sl.No.:-02 | [7 empty] | IRF | 0 | 0.41 | 0 |  |  |  | 0.41 | 0 |  |  |  | 0.41 | 0 |  |  |  | 0.41 | 0 |  |  |  | 0.41 | 0 |  |  |  | 0.41 | 0 |  |  | 0 |  |  | 0
165 | 20/2019 | P2 | 13th Plan Other Project | Page No. 175, Sl. No. 107 of MYT Order | 2 Phase TR Line from Sabour-to Sabour TSS , NIT-20/2019 | [7 empty] | Deposit Work | 0 | 0 | 15.28 |  |  |  | 0 | 15.28 |  |  |  | 0 | 15.28 |  |  |  | 0 | 15.28 |  |  |  | 0 | 15.28 |  |  |  | 0 | 15.28 | 0
166 | 59/PR/BSPTCL/2014 Pkj-D | P2 | 12th Plan Old Projects | Page No. 210, Sl. No. 144 of MYT Order | Railway crossing 132 kv D/C Forbesganj-Kishanganj, NIT-59/2014, D | DCB | [6 empty] | BRGF | 0 | 3.8841 | -0.7023 |  |  |  | 3.8841 | -0.7023 |  |  |  | 3.8841 | -0.7023 |  |  |  | 3.8841 | -0.7023 |  |  |  | 3.8841 | -0.7023 |  |  |  | 3.8841 | -0.7023 |  |  | 0 |  |  | 0
167 | 46/PR/BSPTCL/2015 | P2 | 12th Plan Old Projects | Page No. 296, Sl. No. 186 of MYT Order | Relocation/Rerouting of 132 KV D/C transmission line(Sonenagar-Garhwa-Rihand) along with height raising work at two places from location no-30 to 48(Approx line length-10CKM) on turnkey basis. | DCB | [6 empty] | BRGF | 0 | 6.2967 | -0.34584 |  |  |  | 6.2967 | -0.34584 |  |  |  | 6.2967 | -0.34584 |  |  |  | 6.2967 | -0.34584 |  |  |  | 6.2967 | -0.34584 |  |  |  | 6.2967 | -0.34584 |  |  | 0 |  |  | 0
168 | 12/PR/BSPTCL/2018 | P2 | 13th Plan Other Project | Page No. 306, Sl. No. 229 of MYT Order | construction of 132 KV DCSS (2-Phase) transmission line from GSS Wazirganj (BSPTCL) to TSS Tilaiya (Line-length-21KM) and 01 no 132 KV Line bay at GSS Wazirganj (BSPTCL) on turnkey basis | DCB | 2 | 5.10.2018 | 05.10.2018 | 04.07.2019 | 8.58 |  | Deposit Work | 10.42 | 10.0563 | 0.0001335 | 0.28517 |  |  | 10.0563 | 0.28531 |  | 0 |  | 10.0563 | 0.28531 |  |  |  | 10.0563 | 0.28531 |  |  |  | 10.0563 | 0.28531 |  |  |  | 10.0563 | 0.28531 | 0
169 | 29/PR/BSPTCL/2019 | P2 | 13th Plan Other Project | Page No. 306, Sl. No. 230 of MYT Order | construction of one no of 132 KV line bay with bus extension at GSS Bikramganj and construction of 132 KV 2-phase DCSS transmission line from GSS Bikramganj to upcoming TSS Bikramganj (Line length-18 RKM) with ACSR panther conductor on turnkey basis. | [7 empty] | Deposit Work | 0 | 8.6554 | 6.89e-05 | 0.045935 |  |  | 8.6554 | 0.046004 |  | 0 |  | 8.6554 | 0.046004 |  |  |  | 8.6554 | 0.046004 |  |  |  | 8.6554 | 0.046004 |  |  |  | 8.6554 | 0.046004 | 0
170 | 24/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 175, Sl. No. 115 of MYT Order | Const of Line bay at GSS Pandaul & Rosera , NIT- 24/2018 | Completed | [6 empty] | Deposit Work | 0 | 0 | 5.8504 |  | 5.8568 |  | 5.8568 | -0.0064034 |  |  |  | 5.8568 | -0.0064034 |  |  |  | 5.8568 | -0.0064034 |  |  |  | 5.8568 | -0.0064034 |  |  |  | 5.8568 | -0.0064034 | 0
171 | 116/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 176, Sl. No. 119 of MYT Order | Furniture & Electrical Wiring in E-type quarter at division & LMSD office at Jahanabad (116/PR/BSPTCL/2018) | [7 empty] | IRF | 0 | 0.14 | 0 |  |  |  | 0.14 | 0 |  |  |  | 0.14 | 0 |  |  |  | 0.14 | 0 |  |  |  | 0.14 | 0 |  |  |  | 0.14 | 0 |  |  | 0 |  |  | 0
172 | 05/2020 | P1 | 12th Plan Old Projects | Page No. 176, Sl. No. 120 of MYT Order | Requirement of furniture for newly constucted control room & inspection room at 132/33 Kv GSS Kataiya NIT 05/2020 | [7 empty] | IRF | 0 | 0.082913 | -0.002913 |  |  |  | 0.082913 | -0.002913 |  |  |  | 0.082913 | -0.002913 |  |  |  | 0.082913 | -0.002913 |  |  |  | 0.082913 | -0.002913 |  |  |  | 0.082913 | -0.002913 |  |  | 0 |  |  | 0
173 | 12/PR/BSPTCL/2014 | P1 | 12th Plan Old Projects | Page No. 176, Sl. No. 122 of MYT Order | NIT-12/PR/BSPTCL/2014 | DCB | [6 empty] | BRGF | 0 | 0.03 | 0 |  |  |  | 0.03 | 0 |  |  |  | 0.03 | 0 |  |  |  | 0.03 | 0 |  |  |  | 0.03 | 0 |  |  |  | 0.03 | 0 |  |  | 0 |  |  | 0
174 | 15/PR/BSPTCL/2014 pkg- A | P1 | 12th Plan Old Projects | Page No. 176, Sl. No. 123 of MYT Order | Darbhanga to Darbhanga & Darbhanga to Samastipur Tr. Line(15/PR/BSPTCL/2014 pkg- A) | DCB | [6 empty] | BRGF | 0 | 4.51 | 0 |  |  |  | 4.51 | 0 |  |  |  | 4.51 | 0 |  |  |  | 4.51 | 0 |  |  |  | 4.51 | 0 |  |  |  | 4.51 | 0 |  |  | 0 |  |  | 0
175 | 18/PR/BSPTCL/2014 | P1 | 12th Plan Old Projects | Page No. 176, Sl. No. 124 of MYT Order | Procurement of 01 No. 100MVA 220/132 KV Power Transformer for Hajipur, 18/PR/BSPTCL/2014 | DCB | [6 empty] | BRGF | 0 | 4.72 | 0 |  |  |  | 4.72 | 0 |  |  |  | 4.72 | 0 |  |  |  | 4.72 | 0 |  |  |  | 4.72 | 0 |  |  |  | 4.72 | 0 |  |  | 0 |  |  | 0
176 | 20/PR/BSPTCL/2014 PKG B | P1 | 12th Plan Old Projects | Page No. 176, Sl. No. 125 of MYT Order | capitalisation of construction of 132 KV D/C Transmission Line with ACSR Panther Conductor between Dalsinghsarai to Kusheswarsthan (59.481 KM)., 20/PR/BSPTCL/2014 PKG B | DCB | [6 empty] | BRGF | 0 | 0.69 | 0 |  |  |  | 0.69 | 0 |  |  |  | 0.69 | 0 |  |  |  | 0.69 | 0 |  |  |  | 0.69 | 0 |  |  |  | 0.69 | 0 |  |  | 0 |  |  | 0
177 | 234/PR/BSPTCL/2013 | P1 | 12th Plan Old Projects | Page No. 176, Sl. No. 126 of MYT Order | 2nd Circuit Stringing of 132 KV Muzaffarpur to Vaishali and 132 KV Bettiah to Raxaul and 132 KV Motihari to Dhaka to Sitamarhi, 234/PR/BSPTCL/2013, PKG A,B,C | DCB | [6 empty] | BRGF | 0 | 0.92 | 0 |  |  |  | 0.92 | 0 |  |  |  | 0.92 | 0 |  |  |  | 0.92 | 0 |  |  |  | 0.92 | 0 |  |  |  | 0.92 | 0 |  |  | 0 |  |  | 0
178 | 322/PR/BSPTCL/2013, Pkg-A | P1 | 12th Plan Old Projects | Page No. 176, Sl. No. 127 of MYT Order | Work of augmentation of 132/33 KV GSS Sultanganj, Kahalgaon & Banka., 322/PR/BSPTCL/2013, Pkg-A, | DCB | [6 empty] | BRGF | 0 | 0.02 | 0 |  |  |  | 0.02 | 0 |  |  |  | 0.02 | 0 |  |  |  | 0.02 | 0 |  |  |  | 0.02 | 0 |  |  |  | 0.02 | 0 |  |  | 0 |  |  | 0
179 | 322/PR/BSPTCL/2013, Pkg-B | P1 | 12th Plan Old Projects | Page No. 176, Sl. No. 128 of MYT Order | Aug of GSS 132/33Kv HJP,Pandaul,G-Ganj, Swn, Moti, 322/PR/BSPTCL/2013, Pkg-B, | DCB | [6 empty] | BRGF | 38.63 | 2.46 | 0 |  |  |  | 2.46 | 0 |  |  |  | 2.46 | 0 |  |  |  | 2.46 | 0 |  |  |  | 2.46 | 0 |  |  |  | 2.46 | 0 |  |  | 0 |  |  | 0
180 | 119/PR/BSPTCL/2018 | Civil | 13th Plan Other Project | Page No. 218, Sl. No. 239 of MYT Order | Shifting of dilapidated residential quarter of SDO, Jagdishpur for clearance of ROW obstruction falling in alignment of Ara – Jagdishpur Transmission line. | [7 empty] | IRF | 0 | 0 | 1.4522 |  |  |  | 0 | 1.4522 |  |  |  | 0 | 1.4522 |  |  |  | 0 | 1.4522 |  |  |  | 0 | 1.4522 |  |  |  | 0 | 1.4522 |  |  | 0 |  |  | 0
181 | 41/PR/BSPTCL/2015 | - | 12th Plan Ongoing Project | Page No. 164, Sl. No. 48 of MYT Order | Construction of (2x160 + 2x50) MVA, 220/132/33KV Grid Sub- Station in KHAGARIA (New) under State Plan in between 220KV D/C Purnea (PG) – Begusarai Transmission Line., NIT- 41/2015 | DCB | 3 | 27.08.2015 | 23.05.2018 | 27.02.2017 | 70 |  | State Plan | 72.78 | 87.0125 | 0.68 |  |  |  | 87.0125 | 0.68 |  |  |  | 87.0125 | 0.68 |  |  |  | 87.0125 | 0.68 |  |  |  | 87.0125 | 0.68 |  |  |  | 87.0125 | 0.68 |  | 0 | 0 |  | 0 | 0
182 |  | P1 | 12th Plan Old Projects | Page No. 177, Sl. No. 130 of MYT Order | Interest on Loan ADB | [7 empty] | ADB | 0 | 61.92 | 16.61 |  |  |  | 61.92 | 16.61 |  |  |  | 61.92 | 16.61 |  |  |  | 61.92 | 16.61 |  |  |  | 61.92 | 16.61 |  |  |  | 61.92 | 16.61
183 |  | P1 | 12th Plan Old Projects | Page No. 177, Sl. No. 131 of MYT Order | Crop Compensation against Unidentified NIT | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0 | 0.06 |  |  |  | 0 | 0.06 |  |  |  | 0 | 0.06 |  |  |  | 0 | 0.06 |  |  |  | 0 | 0.06 |  |  |  | 0 | 0.06 |  | 0 | 0 |  | 0 | 0
184 |  | P1 | 12th Plan Old Projects | Page No. 177, Sl. No. 132 of MYT Order | Railway Charges against Unidentified NIT | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0 | 0.78 |  |  |  | 0 | 0.78 |  |  |  | 0 | 0.78 |  |  |  | 0 | 0.78 |  |  |  | 0 | 0.78 |  |  |  | 0 | 0.78 |  | 0 | 0 |  | 0 | 0
185 | 01/PR/BSPTCL/2018 Gr. No.-01 | P1 | 13th Plan Other Project | Page No. 177, Sl. No. 133 of MYT Order | 220/132/33 KV GSS Gaurichak patna under state plan, 01/PR/BSPTCL/2018 Gr. No.-01 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0.1 | 0 |  |  |  | 0.1 | 0 |  |  |  | 0.1 | 0 |  |  |  | 0.1 | 0 |  |  |  | 0.1 | 0 |  |  |  | 0.1 | 0 |  | 0 | 0 |  | 0 | 0
186 |  | P1 | 12th Plan Old Projects | Page No. 177, Sl. No. 134 of MYT Order | Const of 1 NO Bay at Banka GS an Supervision Charge for 10MW SolarPV Project at Banka | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0.56 | 0 |  |  |  | 0.56 | 0 |  |  |  | 0.56 | 0 |  |  |  | 0.56 | 0 |  |  |  | 0.56 | 0 |  |  |  | 0.56 | 0 |  | 0 | 0 |  | 0 | 0
187 | 50/PR/BSPTCL/2016 GRrNo 04 | P1 | 12th Plan Old Projects | Page No. 177, Sl. No. 135 of MYT Order | Misc Civil Work at GSS Banmankhi, 50/PR/BSPTCL/2016 GRrNo 04 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0.34 | 0 |  |  |  | 0.34 | 0 |  |  |  | 0.34 | 0 |  |  |  | 0.34 | 0 |  |  |  | 0.34 | 0 |  |  |  | 0.34 | 0 |  | 0 | 0 |  | 0 | 0
188 | 42/PR/BSPTCL/2014, Gr-03 | P1 | 12th Plan Old Projects | Page No. 177, Sl. No. 136 of MYT Order | Construction of 220/132 Kv GSS , Darbhanga, 42/PR/BSPTCL/2014, Gr-03 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0.82 | 0 |  |  |  | 0.82 | 0 |  |  |  | 0.82 | 0 |  |  |  | 0.82 | 0 |  |  |  | 0.82 | 0 |  |  |  | 0.82 | 0 |  | 0 | 0 |  | 0 | 0
189 | 42/PR/BSPTCL/2016- GR 04 | P1 | 12th Plan Old Projects | Page No. 177, Sl. No. 137 of MYT Order | Construction of 220/132/33 Kv GSS Gaurichak, 42/PR/BSPTCL/2016- GR 04 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0.18 | 0 |  |  |  | 0.18 | 0 |  |  |  | 0.18 | 0 |  |  |  | 0.18 | 0 |  |  |  | 0.18 | 0 |  |  |  | 0.18 | 0 |  | 0 | 0 |  | 0 | 0
190 | 23/PR/BSPTCL/2015 | P1 | 12th Plan Old Projects | Page No. 177, Sl. No. 138 of MYT Order | Supply of Automatic Relay Test Kit at Central Store Fatuha, 23/PR/BSPTCL/2015 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0 | 0.42 |  |  |  | 0 | 0.42 |  |  |  | 0 | 0.42 |  |  |  | 0 | 0.42 |  |  |  | 0 | 0.42 |  |  |  | 0 | 0.42 |  | 0 | 0 |  | 0 | 0
191 | 75/PR/BSPTCL/2015 | P1 | 12th Plan Old Projects | Page No. 177, Sl. No. 139 of MYT Order | Line Work at Madhubnai-Jainagar, Madhubni- Pandaul, 75/PR/BSPTCL/2015 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 10.12 | 0.29 |  |  |  | 10.12 | 0.29 |  |  |  | 10.12 | 0.29 |  |  |  | 10.12 | 0.29 |  |  |  | 10.12 | 0.29 |  |  |  | 10.12 | 0.29 |  | 0 | 0 |  | 0 | 0
192 | 90/PR/BSPTCL/2015 Gr No.-11 | P1 | 12th Plan Old Projects | Page No. 177, Sl. No. 140 of MYT Order | Const. Of Boundry Wall at GSS Chandauti & Maintenance of quarter at GSS Bodhgaya, 90/PR/BSPTCL/2015 Gr No.-11 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0.57 | 0.47 | 0 |  |  |  | 0.47 | 0 |  |  |  | 0.47 | 0 |  |  |  | 0.47 | 0 |  |  |  | 0.47 | 0 |  |  |  | 0.47 | 0 |  | 0 | 0 |  | 0 | 0
193 | 90/PR/BSPTCL/2015 Gr No.-10 | P1 | 12th Plan Old Projects | Page No. 177, Sl. No. 141 of MYT Order | Maintenance of Quarter at Dumraon GSS, 90/PR/BSPTCL/2015 Gr No.-10 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0.36 | 0.29 | 0 |  |  |  | 0.29 | 0 |  |  |  | 0.29 | 0 |  |  |  | 0.29 | 0 |  |  |  | 0.29 | 0 |  |  |  | 0.29 | 0 |  | 0 | 0 |  | 0 | 0
194 | 90/PR/BSPTCL/2015 Gr. No.;-18 | P1 | 12th Plan Old Projects | Page No. 177, Sl. No. 142 of MYT Order | Maintenance of Qr at GSS Biharsharif, 90/PR/BSPTCL/2015 Gr. No.;-18 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0.47 | 0.41 | 0 |  |  |  | 0.41 | 0 |  |  |  | 0.41 | 0 |  |  |  | 0.41 | 0 |  |  |  | 0.41 | 0 |  |  |  | 0.41 | 0 |  | 0 | 0 |  | 0 | 0
195 | 90/PR/BSPTCL/2015 Gr-06 | P1 | 12th Plan Old Projects | Page No. 177, Sl. No. 143 of MYT Order | Cons. Of Drainage System at 132/33 KV GSS,Ara, 90/PR/BSPTCL/2015 Gr-06 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0.13 | 0 |  |  |  | 0.13 | 0 |  |  |  | 0.13 | 0 |  |  |  | 0.13 | 0 |  |  |  | 0.13 | 0 |  |  |  | 0.13 | 0 |  | 0 | 0 |  | 0 | 0
196 | 2/PR/BSPTCL/2016 GR-02 | P1 | 12th Plan Old Projects | Page No. 220, Sl. No. 257 of MYT Order | Construction of Boundry Wall along with entry road , 32/PR/BSPTCL/2016 GR-02 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0.6 | 0 |  |  |  | 0.6 | 0 |  |  |  | 0.6 | 0 |  |  |  | 0.6 | 0 |  |  |  | 0.6 | 0 |  |  |  | 0.6 | 0 |  | 0 | 0 |  | 0 | 0
197 | 90/PR/BSPTCL/2015 Gr- 17 | P1 | 12th Plan Old Projects | Page No. 178, Sl. No. 144 of MYT Order | Special repair & maintenance of quater of E-8 & F-12 type of total 20 nos. at 132/33 KV GSS Hathidah, Biharsharif, 90/PR/BSPTCL/2015 Gr- 17 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0.66 | 0 |  |  |  | 0.66 | 0 |  |  |  | 0.66 | 0 |  |  |  | 0.66 | 0 |  |  |  | 0.66 | 0 |  |  |  | 0.66 | 0 |  | 0 | 0 |  | 0 | 0
198 | 90/PR/BSPTCl/2015 Gr-05 | P1 | 12th Plan Old Projects | Page No. 222, Sl. No. 294 of MYT Order | Construction of Boundry Wall and PCC Road at GSS Gopalganj, 90/PR/BSPTCl/2015 Gr-05 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0.8 | 0.71 | 0 |  |  |  | 0.71 | 0 |  |  |  | 0.71 | 0 |  |  |  | 0.71 | 0 |  |  |  | 0.71 | 0 |  |  |  | 0.71 | 0 |  | 0 | 0 |  | 0 | 0
199 | 90/PR/BSPTCL/2015 Gr No.-01 | P1 | 12th Plan Old Projects | Page No. 178, Sl. No. 145 of MYT Order | Repair & Maintenance of Quarter & Office Building at GSS Muzaffarpur, 90/PR/BSPTCL/2015 Gr No.-01 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0.76 | 0.76 | 0 |  |  |  | 0.76 | 0 |  |  |  | 0.76 | 0 |  |  |  | 0.76 | 0 |  |  |  | 0.76 | 0 |  |  |  | 0.76 | 0 |  | 0 | 0 |  | 0 | 0
200 | 90/PR/BSPTCL/2015, Gr-02 | P1 | 12th Plan Old Projects | Page No. 178, Sl. No. 146 of MYT Order | Special R&M of 13 Quarter at GSS Motihari, 90/PR/BSPTCL/2015, Gr-02 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0.41 | 0 |  |  |  | 0.41 | 0 |  |  |  | 0.41 | 0 |  |  |  | 0.41 | 0 |  |  |  | 0.41 | 0 |  |  |  | 0.41 | 0 |  | 0 | 0 |  | 0 | 0
201 | 75/PR/BSPTC/2014 Gr- 02 | P1 | 12th Plan Old Projects | Page No. 178, Sl. No. 148 of MYT Order | PCC Road)(GSS Kataiya, 75/PR/BSPTC/2014 Gr- 02 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0.98 | 0 |  |  |  | 0.98 | 0 |  |  |  | 0.98 | 0 |  |  |  | 0.98 | 0 |  |  |  | 0.98 | 0 |  |  |  | 0.98 | 0 |  | 0 | 0 |  | 0 | 0
202 | 53/PR/BSPTCL/2015 Gr. No-03 | P1 | 12th Plan Old Projects | Page No. 178, Sl. No. 149 of MYT Order | Providing PCC and gravel spreading in working area of switchyard at 132/33 KV GSS Muzaffarpur, 53/PR/BSPTCL/2015 Gr. No-03 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 1.07 | 0 |  |  |  | 1.07 | 0 |  |  |  | 1.07 | 0 |  |  |  | 1.07 | 0 |  |  |  | 1.07 | 0 |  |  |  | 1.07 | 0 |  | 0 | 0 |  | 0 | 0
203 | 89/PR/BSPTCL/2014 Gr No-04 | P1 | 12th Plan Old Projects | Page No. 178, Sl. No. 150 of MYT Order | Providing PCC and gravel spreading in working area of switchyard at 132/33 KV GSS Bettaih, 89/PR/BSPTCL/2014 Gr No-04 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 1.46 | 0 |  |  |  | 1.46 | 0 |  |  |  | 1.46 | 0 |  |  |  | 1.46 | 0 |  |  |  | 1.46 | 0 |  |  |  | 1.46 | 0 |  | 0 | 0 |  | 0 | 0
204 | 82/PR/BSPTCL/2015 | P1 | 12th Plan Old Projects | Page No. 178, Sl. No. 151 of MYT Order | Reconductoring of Fatuha-Gaighat(D/C) Trans.Line, 82/PR/BSPTCL/2015 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 60.63 | 0 |  |  |  | 60.63 | 0 |  |  |  | 60.63 | 0 |  |  |  | 60.63 | 0 |  |  |  | 60.63 | 0 |  |  |  | 60.63 | 0 |  | 0 | 0 |  | 0 | 0
205 | 55/PR/BSPTCL/2014 GR No. 02 | P1 | 12th Plan Old Projects | Page No. 178, Sl. No. 152 of MYT Order | Construction of PCC Road for 132/33Kv GSS Khagaria, 55/PR/BSPTCL/2014 GR No. 02 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0 | 0.3 |  |  |  | 0 | 0.3 |  |  |  | 0 | 0.3 |  |  |  | 0 | 0.3 |  |  |  | 0 | 0.3 |  |  |  | 0 | 0.3 |  | 0 | 0 |  | 0 | 0
206 | 53/PR/BSPTCL/2014 Gr-02 | P1 | 12th Plan Old Projects | Page No. 178, Sl. No. 153 of MYT Order | PCC Road)(GSS Pandaul, 53/PR/BSPTCL/2014 Gr-02 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0.74 | 0.02 |  |  |  | 0.74 | 0.02 |  |  |  | 0.74 | 0.02 |  |  |  | 0.74 | 0.02 |  |  |  | 0.74 | 0.02 |  |  |  | 0.74 | 0.02 |  | 0 | 0 |  | 0 | 0
207 | 42/PR/BSPTCL/2016- GR 04 | P1 | 12th Plan Old Projects | Page No. 180, Sl. No. 175 of MYT Order | Reconstruction of Boundary wall & Special R&m of IB along with road and boundary wall inside IB , spreading and concerteing block of M 40 grade from main gate to tr circle office road and const of 3 no new store shed at 132/33Kv gSS Purnea, 42/PR/BSPTCL/2016 Gr No-02 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 3.46 | 0 |  |  |  | 3.46 | 0 |  |  |  | 3.46 | 0 |  |  |  | 3.46 | 0 |  |  |  | 3.46 | 0 |  |  |  | 3.46 | 0 |  | 0 | 0 |  | 0 | 0
208 | 90/PR/BSPTCL/2015 Gr no-21 | P1 | 12th Plan Old Projects | Page No. 220, Sl. No. 258 of MYT Order | Construction of Boundry Wall at GSS Belaganj,Gaya, 90/PR/BSPTCL/2015 Gr no-21 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0.62 | 0 |  |  |  | 0.62 | 0 |  |  |  | 0.62 | 0 |  |  |  | 0.62 | 0 |  |  |  | 0.62 | 0 |  |  |  | 0.62 | 0 |  | 0 | 0 |  | 0 | 0
209 | 90/PR/BSPTCl/2015 Gr-09 | P1 | 12th Plan Old Projects | Page No. 178, Sl. No. 154 of MYT Order | Special repair & maintenance of quater of E-8 & F-8 type of 16 nos. at 132/33 KV GSS Arrah, 90/PR/BSPTCl/2015 Gr-09 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0.23 | 0.2 | 0 |  |  |  | 0.2 | 0 |  |  |  | 0.2 | 0 |  |  |  | 0.2 | 0 |  |  |  | 0.2 | 0 |  |  |  | 0.2 | 0 |  | 0 | 0 |  | 0 | 0
210 | 08/PR/BSPTCL/2016 | P1 | 12th Plan Old Projects | Page No. 178, Sl. No. 155 of MYT Order | PCC Road & Gravel spreading at GSS Gaurichak, 08/PR/BSPTCL/2016 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0.11 | 0.11 | 0 |  |  |  | 0.11 | 0 |  |  |  | 0.11 | 0 |  |  |  | 0.11 | 0 |  |  |  | 0.11 | 0 |  |  |  | 0.11 | 0 |  | 0 | 0 |  | 0 | 0
211 | 42/PR/BSPTCL/2014 Gr No.-01 | P1 | 12th Plan Old Projects | Page No. 180, Sl. No. 174 of MYT Order | Construction of New Store Shed , PCC and Garvel spreading at GSS Sheetalpur, Boundary Wall GSS Motihari 42/PR/BSPTCL/2014 Gr No.-01 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 2.17 | 0 |  |  |  | 2.17 | 0 |  |  |  | 2.17 | 0 |  |  |  | 2.17 | 0 |  |  |  | 2.17 | 0 |  |  |  | 2.17 | 0 |  | 0 | 0 |  | 0 | 0
212 |  | P1 | 12th Plan Old Projects | Page No. 223, Sl. No. 300 of MYT Order | PCC Road at GSS Supaul | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0.93 | 0 |  |  |  | 0.93 | 0 |  |  |  | 0.93 | 0 |  |  |  | 0.93 | 0 |  |  |  | 0.93 | 0 |  |  |  | 0.93 | 0 |  | 0 | 0 |  | 0 | 0
213 | 90/PR/BSPTCL/2015 Gr No.-14 | P1 | 12th Plan Old Projects | Page No. 178, Sl. No. 156 of MYT Order | Special repair & Maintance of Quaters of C-1 , D- 3 and F-30 type of total 34 nos. at 132/33 KV GSS Birpur, 90/PR/BSPTCL/2015 Gr No.-14 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0.82 | 0.57 | 0 |  |  |  | 0.57 | 0 |  |  |  | 0.57 | 0 |  |  |  | 0.57 | 0 |  |  |  | 0.57 | 0 |  |  |  | 0.57 | 0 |  | 0 | 0 |  | 0 | 0
214 | 90/PR/BSPTCL/2015 Gr No.- 15 | P1 | 12th Plan Old Projects | Page No. 179, Sl. No. 157 of MYT Order | Special repair & Maintance of Quaters of KF-4, KH-11 and KL-11 type of total 26 nos. at 132/33 KV GSS Kataiya, 90/PR/BSPTCL/2015 Gr No.- 15 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0.12 | 0 |  |  |  | 0.12 | 0 |  |  |  | 0.12 | 0 |  |  |  | 0.12 | 0 |  |  |  | 0.12 | 0 |  |  |  | 0.12 | 0 |  | 0 | 0 |  | 0 | 0
215 | 89/PR/BSPTCL/2014 Gr No 05 | P1 | 12th Plan Old Projects | Page No. 220, Sl. No. 266 of MYT Order | Civil Work at GSS Katihar, 89/PR/BSPTCL/2014 Gr No 05 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0.31 | 0 |  |  |  | 0.31 | 0 |  |  |  | 0.31 | 0 |  |  |  | 0.31 | 0 |  |  |  | 0.31 | 0 |  |  |  | 0.31 | 0 |  | 0 | 0 |  | 0 | 0
216 | 75/PR/BSPTCL/2014 Gr-01 | P1 | 12th Plan Old Projects | Page No. 320, Sl. No. 301 of MYT Order | Boundary Wall)(GSS Ramnagar, 75/PR/BSPTCL/2014 Gr-01 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0.6 | 0 |  |  |  | 0.6 | 0 |  |  |  | 0.6 | 0 |  |  |  | 0.6 | 0 |  |  |  | 0.6 | 0 |  |  |  | 0.6 | 0 |  | 0 | 0 |  | 0 | 0
217 | 94/PR/BSPTCL/2015 | P1 | 12th Plan Old Projects | Page No. 179, Sl. No. 158 of MYT Order | Extn of Control Room, GSS Muzaffarpur, 94/PR/BSPTCL/2015 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0.07 | 0.07 | 0 |  |  |  | 0.07 | 0 |  |  |  | 0.07 | 0 |  |  |  | 0.07 | 0 |  |  |  | 0.07 | 0 |  |  |  | 0.07 | 0 |  | 0 | 0 |  | 0 | 0
218 | 90/PR/BSPTCL/2015 Gr-24 | P1 | 12th Plan Old Projects | Page No. 179, Sl. No. 159 of MYT Order | Special repair & maintenance of quater of E-4 & F-8 type of 12 nos. at 132/33 KV GSS Jamalpur, 90/PR/BSPTCL/2015 Gr-24 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0.33 | 0.24 | 0 |  |  |  | 0.24 | 0 |  |  |  | 0.24 | 0 |  |  |  | 0.24 | 0 |  |  |  | 0.24 | 0 |  |  |  | 0.24 | 0 |  | 0 | 0 |  | 0 | 0
219 | 118/2013 | P1 | 12th Plan Old Projects | Page No. 179, Sl. No. 160 of MYT Order | Supply of 590Kl of EHV Grade Transformer oil, NIT-118/2013 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 4.95 | 5.35 | 0 |  |  |  | 5.35 | 0 |  |  |  | 5.35 | 0 |  |  |  | 5.35 | 0 |  |  |  | 5.35 | 0 |  |  |  | 5.35 | 0 |  | 0 | 0 |  | 0 | 0
220 | PO-13, Dt-19.03.14 & LOI-2275 | P1 | 12th Plan Old Projects | Page No. 179, Sl. No. 161 of MYT Order | Unidentified NIT & Work, Po-PO-13, Dt-19.03.14 & LOI-2275, Dt-24.09.13 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 2.37 | 0 |  |  |  | 2.37 | 0 |  |  |  | 2.37 | 0 |  |  |  | 2.37 | 0 |  |  |  | 2.37 | 0 |  |  |  | 2.37 | 0 |  | 0 | 0 |  | 0 | 0
221 | 95/PR/BSPTCl/2015 Gr No-01 | P1 | 12th Plan Old Projects | Page No. 179, Sl. No. 162 of MYT Order | Special repair & maintenance of quater of F-8 & G-8 Type of total 16 nos. at 132/33 KV Bettiah,95/PR/BSPTCl/2015 Gr No-01 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0.22 | 0.18 | 0 |  |  |  | 0.18 | 0 |  |  |  | 0.18 | 0 |  |  |  | 0.18 | 0 |  |  |  | 0.18 | 0 |  |  |  | 0.18 | 0 |  | 0 | 0 |  | 0 | 0
222 | 13/PR/BSPTCL/2015 Gr. No.-02 | P1 | 12th Plan Old Projects | Page No. 179, Sl. No. 163 of MYT Order | Special repair & Maintance of Quaters of F-4 type of total 4 nos. at 132/33 KV GSS Ramnagar, 13/PR/BSPTCL/2015 Gr. No.-02 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0.14 | 0.13 | 0 |  |  |  | 0.13 | 0 |  |  |  | 0.13 | 0 |  |  |  | 0.13 | 0 |  |  |  | 0.13 | 0 |  |  |  | 0.13 | 0 |  | 0 | 0 |  | 0 | 0
223 | 13/PR/BSPTCl/2015 Gr. No.-03 | P1 | 12th Plan Old Projects | Page No. 179, Sl. No. 164 of MYT Order | Special repair & Maintance of Quaters of C-1 and E-8 type of 09 nos. at 132/33 KV Khagariya and replacement of door, window a7 Chajja over window of store shed at Trans. Division Begusarai, 13/PR/BSPTCl/2015 Gr. No.-03 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0.26 | 0 |  |  |  | 0.26 | 0 |  |  |  | 0.26 | 0 |  |  |  | 0.26 | 0 |  |  |  | 0.26 | 0 |  |  |  | 0.26 | 0 |  | 0 | 0 |  | 0 | 0
224 | 13/PR/BSPTCl/2015 Gr. No.-04 | P1 | 12th Plan Old Projects | Page No. 179, Sl. No. 165 of MYT Order | Special R&M of Quarter at GSS Sabour, 13/PR/BSPTCl/2015 Gr. No.-04 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0.41 | 0 |  |  |  | 0.41 | 0 |  |  |  | 0.41 | 0 |  |  |  | 0.41 | 0 |  |  |  | 0.41 | 0 |  |  |  | 0.41 | 0 |  | 0 | 0 |  | 0 | 0
225 | 44/PR/BSPTCL/2014 Gr-03 | P1 | 12th Plan Old Projects | Page No. 179, Sl. No. 166 of MYT Order | Boundary Wall at GSS Muzaffarpur, 44/PR/BSPTCL/2014 Gr-03 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0.28 | 0 |  |  |  | 0.28 | 0 |  |  |  | 0.28 | 0 |  |  |  | 0.28 | 0 |  |  |  | 0.28 | 0 |  |  |  | 0.28 | 0 |  | 0 | 0 |  | 0 | 0
226 | 90/PR/BSPTCL/2015 Gr No-08 | P1 | 12th Plan Old Projects | Page No. 179, Sl. No. 167 of MYT Order | Construction of damage Boundary wall for raising of height at 132/33 KV GSS Runisaidpur, 90/PR/BSPTCL/2015 Gr No-08 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0.22 | 0.21 | 0 |  |  |  | 0.21 | 0 |  |  |  | 0.21 | 0 |  |  |  | 0.21 | 0 |  |  |  | 0.21 | 0 |  |  |  | 0.21 | 0 |  | 0 | 0 |  | 0 | 0
227 | 55/PR/BSPTCL/2014 Gr. No.- 03 | P1 | 12th Plan Old Projects | Page No. 180, Sl. No. 168 of MYT Order | Construction of PCC raod at 132/33 KV GSS Jamalpur,55/PR/BSPTCL/2014 Gr. No.- 03 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0.3 | 0 |  |  |  | 0.3 | 0 |  |  |  | 0.3 | 0 |  |  |  | 0.3 | 0 |  |  |  | 0.3 | 0 |  |  |  | 0.3 | 0 |  | 0 | 0 |  | 0 | 0
228 | 90/PR/BSPTCL/2015 Gr. No.:- 25 | P1 | 12th Plan Old Projects | Page No. 180, Sl. No. 169 of MYT Order | Maintenence of 7 Nos Qr. At GSS Sultanganj, 90/PR/BSPTCL/2015 Gr. No.:- 25 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0.18 | 0.17 | 0 |  |  |  | 0.17 | 0 |  |  |  | 0.17 | 0 |  |  |  | 0.17 | 0 |  |  |  | 0.17 | 0 |  |  |  | 0.17 | 0 |  | 0 | 0 |  | 0 | 0
229 | 28/PR/BSPTCL/2016 Gr-01 | P1 | 12th Plan Old Projects | Page No. 180, Sl. No. 170 of MYT Order | Civil Work at GSS Bettiah, 28/PR/BSPTCL/2016 Gr-01 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0.27 | 0 |  |  |  | 0.27 | 0 |  |  |  | 0.27 | 0 |  |  |  | 0.27 | 0 |  |  |  | 0.27 | 0 |  |  |  | 0.27 | 0 |  | 0 | 0 |  | 0 | 0
230 |  | P1 | 12th Plan Old Projects | Page No. 180, Sl. No. 171 of MYT Order | Const. Of Boundry Wall at GSS Chandauti & Maintenance of quarter at GSS Bodhgaya | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0 | 0.11 |  |  |  | 0 | 0.11 |  |  |  | 0 | 0.11 |  |  |  | 0 | 0.11 |  |  |  | 0 | 0.11 |  |  |  | 0 | 0.11 |  | 0 | 0 |  | 0 | 0
231 | 90/PR/BSPTCL/2015 Gr No.- 22 | P1 | 12th Plan Old Projects | Page No. 180, Sl. No. 172 of MYT Order | Construction of Boundary wall at Transmission Colony at Rafiganj, 90/PR/BSPTCL/2015 Gr No.- 22 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0.17 | 0.15 | 0 |  |  |  | 0.15 | 0 |  |  |  | 0.15 | 0 |  |  |  | 0.15 | 0 |  |  |  | 0.15 | 0 |  |  |  | 0.15 | 0 |  | 0 | 0 |  | 0 | 0
232 |  | P1 | 12th Plan Old Projects | Page No. 180, Sl. No. 173 of MYT Order | Biharsharif Begusarai Trans. Line | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0 | 0.29 |  |  |  | 0 | 0.29 |  |  |  | 0 | 0.29 |  |  |  | 0 | 0.29 |  |  |  | 0 | 0.29 |  |  |  | 0 | 0.29 |  | 0 | 0 |  | 0 | 0
233 | 50/PR/BSPTCL/2016 Gr No-03 | P1 | 12th Plan Old Projects | Page No. 180, Sl. No. 177 of MYT Order | Construction of Approach road including 04 Nos culvert at 132/33Kv GSS Hathua, 50/PR/BSPTCL/2016 Gr No-03 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0.97 | 0 |  |  |  | 0.97 | 0 |  |  |  | 0.97 | 0 |  |  |  | 0.97 | 0 |  |  |  | 0.97 | 0 |  |  |  | 0.97 | 0 |  | 0 | 0 |  | 0 | 0
234 | 50/PR/BSPTCL/2016 GR. No.-01 | P1 | 12th Plan Old Projects | Page No. 221, Sl. No. 272 of MYT Order | Work of construction of Approach road including culvert at GSS Benipatti, 50/PR/BSPTCL/2016 GR. No.-01 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0.48 | 0 |  |  |  | 0.48 | 0 |  |  |  | 0.48 | 0 |  |  |  | 0.48 | 0 |  |  |  | 0.48 | 0 |  |  |  | 0.48 | 0 |  | 0 | 0 |  | 0 | 0
235 | 53/PR/BSPTCL/2015 Gr. No-04 | P1 | 12th Plan Old Projects | Page No. 221, Sl. No. 273 of MYT Order | Providing PCC & Gravel spreading in working area of switchyard at 220/132/33 KV GSS Darbhanga, 53/PR/BSPTCL/2015 Gr. No-04 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0.64 | 0 |  |  |  | 0.64 | 0 |  |  |  | 0.64 | 0 |  |  |  | 0.64 | 0 |  |  |  | 0.64 | 0 |  |  |  | 0.64 | 0 |  | 0 | 0 |  | 0 | 0
236 | 89/PR/BSPTCL/2014 Gr-10 | P1 | 12th Plan Old Projects | Page No. 178, Sl. No. 150 of MYT Order | Construction of Boundary Wall,Trans Colony Gaya, 89/PR/BSPTCL/2014 Gr-10 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 1.67 | 0 |  |  |  | 1.67 | 0 |  |  |  | 1.67 | 0 |  |  |  | 1.67 | 0 |  |  |  | 1.67 | 0 |  |  |  | 1.67 | 0 |  | 0 | 0 |  | 0 | 0
237 | 53/PR/BSPTCL/2015 Gr-02 | P1 | 12th Plan Old Projects | Page No. 178, Sl. No. 153 of MYT Order | Boundary wall at GSS Darbhanga, 53/PR/BSPTCL/2015 Gr-02 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0.86 | 0 |  |  |  | 0.86 | 0 |  |  |  | 0.86 | 0 |  |  |  | 0.86 | 0 |  |  |  | 0.86 | 0 |  |  |  | 0.86 | 0 |  | 0 | 0 |  | 0 | 0
238 | 89/PR/BSPTCL/2014, GR-02 | P1 | 12th Plan Old Projects | Page No. 181, Sl. No. 181 of MYT Order | PCC Road at GSS Motihari, 89/PR/BSPTCL/2014, GR-02 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 1.22 | 0 |  |  |  | 1.22 | 0 |  |  |  | 1.22 | 0 |  |  |  | 1.22 | 0 |  |  |  | 1.22 | 0 |  |  |  | 1.22 | 0 |  | 0 | 0 |  | 0 | 0
239 | 90/PR/BSPTCL/2015 Gr-02 | P1 | 12th Plan Old Projects | Page No. 181, Sl. No. 182 of MYT Order | Construction of Boundary wall,GSS Katra, 90/PR/BSPTCL/2015 Gr-02 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 1.01 | 0 |  |  |  | 1.01 | 0 |  |  |  | 1.01 | 0 |  |  |  | 1.01 | 0 |  |  |  | 1.01 | 0 |  |  |  | 1.01 | 0 |  | 0 | 0 |  | 0 | 0
240 | 433/PR/BSPTCL/2013 | P1 | 12th Plan Old Projects | Page No. 181, Sl. No. 183 of MYT Order | Construction of Training Institute at Sipara, 433/PR/BSPTCL/2013 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 2.29 | 0 |  |  |  | 2.29 | 0 |  |  |  | 2.29 | 0 |  |  |  | 2.29 | 0 |  |  |  | 2.29 | 0 |  |  |  | 2.29 | 0 |  | 0 | 0 |  | 0 | 0
241 | 53/PR/BSPTCl/2015 Gr. No.-01 | P1 | 12th Plan Old Projects | Page No. 181, Sl. No. 185 of MYT Order | Reconstruction of Boundary walls for 132/33 KV GSS Sultanganj, 53/PR/BSPTCl/2015 Gr. No.-01 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0.98 | 0.91 | 0 |  |  |  | 0.91 | 0 |  |  |  | 0.91 | 0 |  |  |  | 0.91 | 0 |  |  |  | 0.91 | 0 |  |  |  | 0.91 | 0 |  | 0 | 0 |  | 0 | 0
242 | 89/PR/BSPTCL/2014 Gr-06 | P1 | 12th Plan Old Projects | Page No. 181, Sl. No. 186 of MYT Order | PCC Road GSS Forbesganj, 89/PR/BSPTCL/2014 Gr-06 | DCB |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 1.13 | 0 |  |  |  | 1.13 | 0 |  |  |  | 1.13 | 0 |  |  |  | 1.13 | 0 |  |  |  | 1.13 | 0 |  |  |  | 1.13 | 0 |  | 0 | 0 |  | 0 | 0
243 | 90/PR/BSPTCL/2015 Gr No.-16 | P1 | 12th Plan Old Projects | Page No. 181, Sl. No. 187 of MYT Order | special repair & maintance of Quaters of E-4, F- 16 type of 16 nos. at 132/33 KV GSS Baripahari, Biharsharif, 90/PR/BSPTCL/2015 Gr No.-16 |  |  | As per Reconciliation |  |  |  |  | State Plan | 0.58 | 0.47 | 0 |  |  |  | 0.47 | 0 |  |  |  | 0.47 | 0 |  |  |  | 0.47 | 0 |  |  |  | 0.47 | 0 |  |  |  | 0.47 | 0 |  | 0 | 0 |  | 0 | 0
244 | 90/PR/BSPTCL/2015 Gr-23 | P1 | 12th Plan Old Projects | Page No. 181, Sl. No. 188 of MYT Order | Special repair & Maintance of Quaters of D-04 and E-12 type of 16 nos. at 132/33 KV GSS Fathua. Special repair & maintenance of quaters of G-8 type 132/33 KV GSS Gaighat and Special repair & Maintance of Quaters of D-1 at 132/33 KV GSS masaudi, 90/PR/BSPTCL/2015 Gr-23 |  |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0.28 | 0 |  |  |  | 0.28 | 0 |  |  |  | 0.28 | 0 |  |  |  | 0.28 | 0 |  |  |  | 0.28 | 0 |  |  |  | 0.28 | 0 |  | 0 | 0 |  | 0 | 0
245 | 95/PR/BSPTCl/2015 Gr No-05 | P1 | 12th Plan Old Projects | Page No. 181, Sl. No. 189 of MYT Order | Special repair & maintenance of quater of C-1, D- 8, F-8 & G-16 type of total 33 nos. at 132/33 KV GSS Purnea and C type at 132/33 KV GSS at Katihar, 95/PR/BSPTCl/2015 Gr No-05 |  |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0.65 | 0 |  |  |  | 0.65 | 0 |  |  |  | 0.65 | 0 |  |  |  | 0.65 | 0 |  |  |  | 0.65 | 0 |  |  |  | 0.65 | 0 |  | 0 | 0 |  | 0 | 0
246 | 50/PR/BSPTCL/2016 GR. No.-05 | P1 | 12th Plan Old Projects | Page No. 221, Sl. No. 274 of MYT Order | Work of construction of Approach road including 4 culvert at GSS Jhanjharpur, 50/PR/BSPTCL/2016 GR. No.-05 |  |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 1.6 | 0 |  |  |  | 1.6 | 0 |  |  |  | 1.6 | 0 |  |  |  | 1.6 | 0 |  |  |  | 1.6 | 0 |  |  |  | 1.6 | 0 |  | 0 | 0 |  | 0 | 0
247 | 50/PR/BSPTCL/2016 Gr No 02 | P1 | 12th Plan Old Projects | Page No. 221, Sl. No. 275 of MYT Order | Construction of approach road including 04 Nos culvert at 132/33Kv GSS Rosera, 50/PR/BSPTCL/2016 Gr No 02 |  |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 1.89 | 0 |  |  |  | 1.89 | 0 |  |  |  | 1.89 | 0 |  |  |  | 1.89 | 0 |  |  |  | 1.89 | 0 |  |  |  | 1.89 | 0 |  | 0 | 0 |  | 0 | 0
248 | 67/PR/BSPTCl/2013 | P1 | 12th Plan Old Projects | Page No. 221, Sl. No. 276 of MYT Order | 13 No 50MVA Transformer, 67/PR/BSPTCl/2013 |  |  | As per Reconciliation |  |  |  |  | State Plan | 29.4 | 31.67 | 0 |  |  |  | 31.67 | 0 |  |  |  | 31.67 | 0 |  |  |  | 31.67 | 0 |  |  |  | 31.67 | 0 |  |  |  | 31.67 | 0 |  | 0 | 0 |  | 0 | 0
249 | 116/PR/BSEB/2012 | P1 | 12th Plan Old Projects | Page No. 221, Sl. No. 277 of MYT Order | Design Manufacture, Testing,Supply & Delivery of 02 nos. 150MVA, 220/132/33 KV Auto Transformer,116/PR/BSEB/2012 |  |  | As per Reconciliation |  |  |  |  | State Plan | 10.07 | 10.7 | 0 |  |  |  | 10.7 | 0 |  |  |  | 10.7 | 0 |  |  |  | 10.7 | 0 |  |  |  | 10.7 | 0 |  |  |  | 10.7 | 0 |  | 0 | 0 |  | 0 | 0
250 | 53/PR/BSPTCL/2014 Gr-03 | P1 | 12th Plan Old Projects | Page No. 223, Sl. No. 311 of MYT Order | Boundary wall at GSS Hajipur, 53/PR/BSPTCL/2014 Gr-03 |  |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0.32 | 0 |  |  |  | 0.32 | 0 |  |  |  | 0.32 | 0 |  |  |  | 0.32 | 0 |  |  |  | 0.32 | 0 |  |  |  | 0.32 | 0 |  | 0 | 0 |  | 0 | 0
251 | Wo-417 dt 28.02.12 | P1 | 12th Plan Old Projects | Page No. 221, Sl. No. 278 of MYT Order | Unidentified NIT & Work, Po-05, Wo-417 dt 28.02.12 |  |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0 | 0.12 |  |  |  | 0 | 0.12 |  |  |  | 0 | 0.12 |  |  |  | 0 | 0.12 |  |  |  | 0 | 0.12 |  |  |  | 0 | 0.12 |  | 0 | 0 |  | 0 | 0
252 |  | P1 | 12th Plan Old Projects | Page No. 221, Sl. No. 279 of MYT Order | Unidentified NIT, For Const. of 132 KV Tr. Line Lauriya Sugar Mill to GSS Ram Nagar |  |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0 | 1.97 |  |  |  | 0 | 1.97 |  |  |  | 0 | 1.97 |  |  |  | 0 | 1.97 |  |  |  | 0 | 1.97 |  |  |  | 0 | 1.97 |  | 0 | 0 |  | 0 | 0
253 |  | P1 | 12th Plan Old Projects | Page No. 221, Sl. No. 280 of MYT Order | Const of GSS Sherghati |  |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 1.13 | 0 |  |  |  | 1.13 | 0 |  |  |  | 1.13 | 0 |  |  |  | 1.13 | 0 |  |  |  | 1.13 | 0 |  |  |  | 1.13 | 0 |  | 0 | 0 |  | 0 | 0
254 |  | P1 | 12th Plan Old Projects | Page No. 221, Sl. No. 281 of MYT Order | Construction of Sherghati Bodhgaya Trans. Lin |  |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0 | 0.2 |  |  |  | 0 | 0.2 |  |  |  | 0 | 0.2 |  |  |  | 0 | 0.2 |  |  |  | 0 | 0.2 |  |  |  | 0 | 0.2 |  | 0 | 0 |  | 0 | 0
255 |  | P1 | 12th Plan Old Projects | Page No. 221, Sl. No. 282 of MYT Order | Const of Fatuha -Gighat TR Line |  |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0 | 0.11 |  |  |  | 0 | 0.11 |  |  |  | 0 | 0.11 |  |  |  | 0 | 0.11 |  |  |  | 0 | 0.11 |  |  |  | 0 | 0.11 |  | 0 | 0 |  | 0 | 0
256 |  | P1 | 12th Plan Old Projects | Page No. 224, Sl. No. 312 of MYT Order | Lease Rent |  |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0 | 5 |  |  |  | 0 | 5 |  |  |  | 0 | 5 |  |  |  | 0 | 5 |  |  |  | 0 | 5 |  |  |  | 0 | 5 |  | 0 | 0 |  | 0 | 0
257 | 60/PR/BSPHCL/2013 | P1 | 12th Plan Old Projects | Page No. 224, Sl. No. 313 of MYT Order | Const of Compound Wall of bihta, 60/PR/BSPHCL/2013 |  |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0.5 | 0 |  |  |  | 0.5 | 0 |  |  |  | 0.5 | 0 |  |  |  | 0.5 | 0 |  |  |  | 0.5 | 0 |  |  |  | 0.5 | 0 |  | 0 | 0 |  | 0 | 0
258 |  | P1 | 12th Plan Old Projects | Page No. 316, Sl. No. 283 of MYT Order | Imamganj & Associated Line |  |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 24.41 | 0 |  |  |  | 24.41 | 0 |  |  |  | 24.41 | 0 |  |  |  | 24.41 | 0 |  |  |  | 24.41 | 0 |  |  |  | 24.41 | 0 |  | 0 | 0 |  | 0 | 0
259 | 190/PR/BSEB/2009 | P1 | 12th Plan Old Projects | Page No. 182, Sl. No. 200 of MYT Order | Tehta & Sherghati GSS Line, 190/PR/BSEB/2009 |  |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 42.27 | 0 |  |  |  | 42.27 | 0 |  |  |  | 42.27 | 0 |  |  |  | 42.27 | 0 |  |  |  | 42.27 | 0 |  |  |  | 42.27 | 0 |  | 0 | 0 |  | 0 | 0
260 | 232/PR/BSEB/2010 | P1 | 12th Plan Old Projects | Page No. 182, Sl. No. 201 of MYT Order | Construction of 132/33 KV GSS Jandaha with associated transmission Line, 232/PR/BSEB/2010 |  |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 27.65 | 0 |  |  |  | 27.65 | 0 |  |  |  | 27.65 | 0 |  |  |  | 27.65 | 0 |  |  |  | 27.65 | 0 |  |  |  | 27.65 | 0 |  | 0 | 0 |  | 0 | 0
261 | 28/PR/BSEB/2011 | P1 | 12th Plan Old Projects | Page No. 182, Sl. No. 202 of MYT Order | Karbighia GSS & Associated Line, 28/PR/BSEB/2011 |  |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 61.16 | 0 |  |  |  | 61.16 | 0 |  |  |  | 61.16 | 0 |  |  |  | 61.16 | 0 |  |  |  | 61.16 | 0 |  |  |  | 61.16 | 0 |  | 0 | 0 |  | 0 | 0
262 | 167/PR/BSEB/2010 | P1 | 12th Plan Old Projects | Page No. 182, Sl. No. 203 of MYT Order | Ekma & Associated Line, 167/PR/BSEB/2010 |  |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 2.08 | 0 |  |  |  | 2.08 | 0 |  |  |  | 2.08 | 0 |  |  |  | 2.08 | 0 |  |  |  | 2.08 | 0 |  |  |  | 2.08 | 0 |  | 0 | 0 |  | 0 | 0
263 |  | P1 | 12th Plan Old Projects | Page No. 182, Sl. No. 204 of MYT Order | 132 KV Line over Bagmati river crossing |  |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 6.53 | 0 |  |  |  | 6.53 | 0 |  |  |  | 6.53 | 0 |  |  |  | 6.53 | 0 |  |  |  | 6.53 | 0 |  |  |  | 6.53 | 0 |  | 0 | 0 |  | 0 | 0
264 | 179/PR/BSEB/2010 | P1 | 12th Plan Old Projects | Page No. 182, Sl. No. 205 of MYT Order | 132 KV Line over Budhi Gandak river crossing, 179/PR/BSEB2010 |  |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 1.89 | 0 |  |  |  | 1.89 | 0 |  |  |  | 1.89 | 0 |  |  |  | 1.89 | 0 |  |  |  | 1.89 | 0 |  |  |  | 1.89 | 0 |  | 0 | 0 |  | 0 | 0
265 | 03/PR/BSPTCL/2016 | P1 | 12th Plan Old Projects | Page No. 222, Sl. No. 290 of MYT Order | Construction of Associated 132KV Line bays for Second Circuit Stringing of Existing double circuit Single strung atDumraon, Buxar, Goh etc, 03/PR/BSPTCL/2016 |  |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 7.97 | 0 |  |  |  | 7.97 | 0 |  |  |  | 7.97 | 0 |  |  |  | 7.97 | 0 |  |  |  | 7.97 | 0 |  |  |  | 7.97 | 0 |  | 0 | 0 |  | 0 | 0
266 | 55/PR/BSPTCL/2014 Gr-05 | P1 | 12th Plan Old Projects | Page No. 222, Sl. No. 291 of MYT Order | Boundry ball at GSS Jamalpur, 55/PR/BSPTCL/2014 Gr-05 |  |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 1 | 0 |  |  |  | 1 | 0 |  |  |  | 1 | 0 |  |  |  | 1 | 0 |  |  |  | 1 | 0 |  |  |  | 1 | 0 |  | 0 | 0 |  | 0 | 0
267 | 89/PR/BSPTCL/2014 Gr No 08 | P1 | 12th Plan Old Projects | Page No. 224, Sl. No. 314 of MYT Order | Boundary Wall,GSS Saharsa, 89/PR/BSPTCL/2014 Gr No 08 |  |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0.83 | 0 |  |  |  | 0.83 | 0 |  |  |  | 0.83 | 0 |  |  |  | 0.83 | 0 |  |  |  | 0.83 | 0 |  |  |  | 0.83 | 0 |  | 0 | 0 |  | 0 | 0
268 | 5/PR/BSPTCL/2014 Gr No 05 | P1 | 12th Plan Old Projects | Page No. 224, Sl. No. 315 of MYT Order | Boundary Wall,GSS Saharsa, 5/PR/BSPTCL/2014 Gr No 05 |  |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0.54 | 0 |  |  |  | 0.54 | 0 |  |  |  | 0.54 | 0 |  |  |  | 0.54 | 0 |  |  |  | 0.54 | 0 |  |  |  | 0.54 | 0 |  | 0 | 0 |  | 0 | 0
269 | 75/PR/BSPTCL/2014 Gr no.-03 | P1 | 12th Plan Old Projects | Page No. 224, Sl. No. 316 of MYT Order | providing PCC road for 132/33 KV Saharsa, 75/PR/BSPTCL/2014 Gr no.-03 |  |  | As per Reconciliation |  |  |  |  | State Plan | 0.58 | 0.57 | 0 |  |  |  | 0.57 | 0 |  |  |  | 0.57 | 0 |  |  |  | 0.57 | 0 |  |  |  | 0.57 | 0 |  |  |  | 0.57 | 0 |  | 0 | 0 |  | 0 | 0
270 |  | P1 | 12th Plan Old Projects | Page No. 183, Sl. No. 209 of MYT Order | Erection, testing & commissioning of 08 nos transmission towers on pile foundation and open foundation of 132 KV S/C Muzaffarpur- Sitamarhi trans line. |  |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0.25 | 0.95 |  |  |  | 0.25 | 0.95 |  |  |  | 0.25 | 0.95 |  |  |  | 0.25 | 0.95 |  |  |  | 0.25 | 0.95 |  |  |  | 0.25 | 0.95 |  | 0 | 0 |  | 0 | 0
271 | 89/PR/BSPTCL/2014 GR -01 | P1 | 12th Plan Old Projects | Page No. 183, Sl. No. 210 of MYT Order | Construction of Boundary Wall at 132/33 KV Khagaria, 89/PR/BSPTCL/2014 GR -01 |  |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0.12 | 0 |  |  |  | 0.12 | 0 |  |  |  | 0.12 | 0 |  |  |  | 0.12 | 0 |  |  |  | 0.12 | 0 |  |  |  | 0.12 | 0 |  | 0 | 0 |  | 0 | 0
272 |  | P1 | 12th Plan Old Projects | Page No. 183, Sl. No. 211 of MYT Order | Widening of exsting road for transpost of heavy Transformer for 132/33 GSS Nirmali |  |  | As per Reconciliation |  |  |  |  | State Plan | 0 | 0.24 | 0 |  |  |  | 0.24 | 0 |  |  |  | 0.24 | 0 |  |  |  | 0.24 | 0 |  |  |  | 0.24 | 0 |  |  |  | 0.24 | 0 |  | 0 | 0 |  | 0 | 0
273 | 39/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 224, Sl. No. 321 of MYT Order | Construction of 220/132/33 KV (2X160+3x50MVA) GSS at Garaul (Dist. Vaishali) on turnkey basis NIT No 39/PR/BSPTCL/2018. | DCB | 18 | 2019-01-21 | 2019-01-21 | 20.07.2020 | 86.59 | 98.27 | State Plan | 84.62 | 84.7384 | -2.687 | 1.0378 | 0.53291 | 0.0036297 | 85.2749 | -2.1858 |  |  |  | 85.2749 | -2.1858 |  |  |  | 85.2749 | -2.1858 |  |  |  | 85.2749 | -2.1858 |  |  |  | 85.2749 | -2.1858 |  | 0 | 0 |  | 0 | 0
274 | 40/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 224, Sl. No. 322 of MYT Order | Construction of 220/132/33 KV, (2x200 + 3x50) MVA GSS at Raxaul District- NIT 40/PR/BSPTCL/2018 | DCB | 18 | 2019-01-21 | 2019-01-21 | 20.07.2020 | 84.23 | 93.49 | State Plan | 83.69 | 0 | 72.2268 | 10.001 | 73.3506 | 8.2736 | 81.6243 | 0.60355 |  |  |  | 81.6243 | 0.60355 |  |  |  | 81.6243 | 0.60355 |  |  |  | 81.6243 | 0.60355 |  |  |  | 81.6243 | 0.60355 |  | 0 | 0 |  | 0 | 0
275 | 58/PR/BSPTCL/2018 | P2 | 13th Plan Other Project | Page No. 225, Sl. No. 327 of MYT Order | Construction of Transmission lines of 220/132 kv D/C Sheikhopursarai(BGCL)- GSS Asthawan,GSS Biharsarif- GSS Asthawan,Asthawan- Rajgir GSS,Asthawan- Nalanda, & Asthawan- Barh GSS. NIT 58/PR/BSPTCL/2018 | DCB | 5 | 2019-01-21 | 2019-01-21 | 20.04.2020 | 105.28 | 128.33 | State Plan | 101.98 | 0 | 101.7094 | 0.75762 | 102.7368 | 23.464 | 126.2007 | 0 | 0.19 | 0.19941 |  | 126.4001 | -0.0094142 |  |  |  | 126.4001 | -0.0094142 |  |  |  | 126.4001 | -0.0094142 |  |  |  | 126.4001 | -0.0094142 |  | 0 | 0 |  | 0 | 0 |  | 0.152 | 0.038
276 | 78/PR/BSPTCL/2018 | P2 | 13th Plan Other Project | Page No. 225, Sl. No. 329 of MYT Order | Construction of 132 kv D/C Bakhtiyarpur(New) to Harnaut(BSPTCL) & Baripahari to Harnaut transmission line with ACSR Panther Conductor. NIT 78/PR/BSPTCL/2018 | DCB |  | 2019-01-15 | 2019-01-15 |  | 29.14 | 39.62 | State Plan | 25.61 | 0 | 24.87 | 0.21591 |  |  | 0 | 25.0859 | 1.57 | 0 |  | 0 | 26.6559 |  |  |  | 0 | 26.6559 |  |  |  | 0 | 26.6559 |  |  |  | 0 | 26.6559 |  | 0 | 0 |  | 0 | 0 |  | 1.256 | 0.314
277 | 56/PR/BSPTCL/2018 | P2 | 13th Plan Other Project | Page No. 225, Sl. No. 330 of MYT Order | 1. Construction of 220kV D/c Pusauli (PG)- Sahpuri LILO Karmnasha (new) Transmission line with single moose (Line length-12 Ckm) on turnkey basis. 2. Construction of 220kV D/c Pusauli (BSPTCL)- Karmnasha (New) Transmission Line with twin moose (Line length 80 Ckm) on turnkey basis NIT No.- 56/PR/BSPTCL/2018 | DCB | 7 | 2019-01-21 | 2019-01-21 | 20.04.2020 | 87.86 | 87.86 | State Plan | 57.2 | 63.8353 | -8.875 |  |  |  | 63.8353 | -8.875 |  |  |  | 63.8353 | -8.875 |  |  |  | 63.8353 | -8.875 |  |  |  | 63.8353 | -8.875 |  |  |  | 63.8353 | -8.875 |  | 0 | 0 |  | 0 | 0
278 | 57/PR/BSPTCL/2018 | P2 | 13th Plan Other Project | Page No. 226, Sl. No. 331 of MYT Order | Construction of 220 KV D/C Saharsa( New)- Khagaria(New) Transmission line with ACSR Zebra Conductor (Approx Route Length-80KM) under State Plan against NIT No. 57/PR/BSPTCL/2018 | DCB | 7 | 2019-01-21 | 2019-01-21 | 20.04.2020 | 114 | 114 | State Plan | 93.37 | 108.9335 | -18.2376 | 1.1544 |  |  | 108.9335 | -17.0832 |  |  |  | 108.9335 | -17.0832 |  |  |  | 108.9335 | -17.0832 |  |  |  | 108.9335 | -17.0832 |  |  |  | 108.9335 | -17.0832 |  | 0 | 0 |  | 0 | 0
279 | 109/PR/BSPTCL/2018 | P2 | 13th Plan Other Project | Page No. 226, Sl. No. 332 of MYT Order | Re-Conductoring of 132KV Chandauti-Sonenagr S/C Trans. Line(L-30) and 132 KV Chandauti- Rafiganj-Sonenagar Trans. Line(L-31) with HTLS Conductor NIT 109/PR/BSPTCL/2018 | DCB |  | 2019-02-06 | 2019-02-06 |  | 81.76 | 79.94 | State Plan | 76.35 | 77.52 | 0.03 |  |  |  | 77.52 | 0.03 |  |  |  | 77.52 | 0.03 |  |  |  | 77.52 | 0.03 |  |  |  | 77.52 | 0.03 |  |  |  | 77.52 | 0.03 |  | 0 | 0 |  | 0 | 0
280 | 110/PR/BSPTCL/2018 | P2 | 13th Plan Other Project | Page No. 226, Sl. No. 333 of MYT Order | Construction of 132 KV D/C Transmission Line for LILO of Chandauti-Sonenagar (L-30) 132 KV S/C Transmission Line and Chandauti-Rafiganj- Sonenagar (L-31) 132 KV S/C Transmission Line at GSS Chandauti (New) with HTLS Conductor (equivalent to Panther Conductor) on Turnkey Basis (Route Length- 46 KM) NIT 110/PR/BSPTCL/2018 | DCB | 4 | 2019-02-06 | 2019-02-06 | 05.02.2020 | 63.93 | 67.8 | State Plan | 71.8 | 79.4372 | -7.5528 |  |  |  | 79.4372 | -7.5528 |  |  |  | 79.4372 | -7.5528 |  |  |  | 79.4372 | -7.5528 |  |  |  | 79.4372 | -7.5528 |  |  |  | 79.4372 | -7.5528 |  | 0 | 0 |  | 0 | 0
281 | 108/PR/BSPTCL/2018 | P2 | 13th Plan Other Project | Page No. 226, Sl. No. 334 of MYT Order | i)Construction of 132 KV LLO line on 132KV S/C Dehri-Banjari Transmission line to new GSS Kerpa (ii) Re-conductoring of existing 132 KV S/C transmission line from Dehri to Banjari (iii) Re-conductoring of existing 132 KV D/C transmission line from Dehri to Sonenagar with HTLS(equivalent to panther) Conductor(Approx CKM=29KM NIT 108/PR/BSPTCL/2018 | DCB |  | 2019-02-07 | 2019-02-07 | 06.02.2020 | 40.39 | 39.36 | State Plan | 37.25 | 39.41 | 0 |  |  |  | 39.41 | 0 |  |  |  | 39.41 | 0 |  |  |  | 39.41 | 0 |  |  |  | 39.41 | 0 |  |  |  | 39.41 | 0 |  | 0 | 0 |  | 0 | 0
282 | 69/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 226, Sl. No. 335 of MYT Order | Construction of LILO of One Ckt of 132Kv D/C Kishanganj(Old)-Forbesganj Transmission Line at Palasi GSS with ACSR Panther Conductor (line Length- 20 RKM) against NIT- 69/PR/BSPTCL/2018 | DCB | 6 | 14.01.2019 | 14.01.2019 | 13.01.2020 | 15.6 | 17.93 | State Plan | 6.72 | 0 | 3.5327 | 0.67014 |  |  | 0 | 4.2029 |  | 0 |  | 0 | 4.2029 |  |  |  | 0 | 4.2029 |  |  |  | 0 | 4.2029 |  |  |  | 0 | 4.2029 |  | 0 | 0 |  | 0 | 0
283 | 55/PR/BSPTCl/2018 | P2 | 13th Plan Other Project | Page No. 226, Sl. No. 336 of MYT Order | Construction of 132Kv D/C Karmnasa (new)- Ramgarh Tr Line on single mooze. 2. Construction of 132KV D/c Karmnasa (new)- Karmnasa Tr line on single mooze.NIT No.- 55/PR/BSPTCl/2018 | DCB | 2 | 2019-01-21 | 2019-01-21 | 20.04.2020 | 40.18 | 40.18 | State Plan | 35.85 | 36.2805 | -2.1181 |  |  |  | 36.2805 | -2.1181 |  |  |  | 36.2805 | -2.1181 |  |  |  | 36.2805 | -2.1181 |  |  |  | 36.2805 | -2.1181 |  |  |  | 36.2805 | -2.1181 |  | 0 | 0 |  | 0 | 0
284 | 66/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 227, Sl. No. 338 of MYT Order | (i)Construction of 220 KV D/C Samastipur (new) GSS - Tajpur GSS.(ii) Construction of 220 KV D/C Tajpur GSS - Garaul GSS.(iii) Construction of 132 KV D/C Shahpur Patori GSS - Tajpur GSS. NIT 66/PR/BSPTCL/2018 | DCB |  | 2019-01-21 | 2019-01-21 | 20.04.2020 | 87.63 | 103.6 | State Plan | 75.76 | 0 | 68.6767 | 3.1615 |  |  | 0 | 71.8382 | 3.3 | 93.865 |  | 93.865 | -18.7268 |  |  |  | 93.865 | -18.7268 |  |  |  | 93.865 | -18.7268 |  |  |  | 93.865 | -18.7268 |  | 0 | 0 |  | 0 | 0 |  | 2.64 | 0.66
285 | 50/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 227, Sl. No. 339 of MYT Order | Construction of following Transmission lines on Turnkey basis: i) 220 KV D/C Muzaffarpur(PG)- Garaul Transmission Line with ACSR Zebra Conductor (Line Length-20 RKM) ii) 132 KV D/C Garaul-MahnarTransmission Line with ACSR Panther Conductor (Line Length- 45 RKM) iii) LILO of both circuit of 132 KV D/C Muzaffarpur-vaishali Transmission Line at Garaul GSS with ACSR Panther Conductor (Line Length- 2x15 RKM) iv) 132 KV D/C Transmission line from GSS Chhapra(New)- Ekma with ACSR Panther Conductor (Line Length - 45 RKM) NIT No- 50/PR/BSPTCL/2018 | DCB |  | 2019-01-21 | 2019-01-21 | 20.05.2020 | 103.14 | 103.14 | State Plan | 79.28 | 66.0791 | 11.7975 | 0.57451 | 20.9989 | 5.2008 | 92.2788 | -13.8276 |  |  |  | 92.2788 | -13.8276 |  |  |  | 92.2788 | -13.8276 |  |  |  | 92.2788 | -13.8276 |  |  |  | 92.2788 | -13.8276 |  | 0 | 0 |  | 0 | 0
286 | 37/PR/BSPTCL/2017 | P1 | 12th Plan Old Projects | Page No. 227, Sl. No. 340 of MYT Order | Supply, Installation , testing& commsisioning of DLMS complaint .2s class ABT type energy meter with implementation of 100% metering.Data Acquisition and Online ABT monitoring for the transmission & sub transmission substation upto 33Kv Level , NIT- 37/PR/BSPTCL/2017 | DCB | 1 | 28.03.2018 | 28.03.2018 | 27.06.2019 | 68.11 | 81.35 | State Plan | 68.11 | 0.37 | 55.8694 |  |  |  | 0.37 | 55.8694 |  |  |  | 0.37 | 55.8694 |  |  |  | 0.37 | 55.8694 |  |  |  | 0.37 | 55.8694 |  |  |  | 0.37 | 55.8694 |  | 0 | 0 |  | 0 | 0
287 | 51/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 228, Sl. No. 341 of MYT Order | Construction of the following lines:(i) 220/132/33 KV D/C Chapra, Amnaur - MZP Transmission line. (ii) 132KV D/C Chapra, Amnaur - Vaishali Transmission line. NIT 51/PR/BSPTCL/2018 | DCB | 7 | 2019-01-21 | 2019-01-21 | 20.04.2020 | 85.43 | 84.93 | State Plan | 101.56 | 52.6071 | 48.9293 | 0.80553 | 61.7449 | 12.8747 | 127.2267 | -24.8847 |  |  |  | 127.2267 | -24.8847 |  |  |  | 127.2267 | -24.8847 |  |  |  | 127.2267 | -24.8847 |  |  |  | 127.2267 | -24.8847 |  | 0 | 0 |  | 0 | 0
288 | 53/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 228, Sl. No. 342 of MYT Order | Construction of the following lines: (i) 132 KV D/C Saharsa (Old) - Banmakhi Transmission line. (ii) 132KV D/C Saharsa (Old) - Udaikishanganj Transmission line.(iii) 132KV D/C Madhepura - Sonebarsa Transmission line NIT 53/PR/BSPTCL/2018 | DCB | 6 | 2019-01-21 | 2019-01-21 | 20.01.2020 | 49.57 | 54.07 | State Plan | 47.48 | 0 | 40.31 |  |  |  | 0 | 40.31 |  |  |  | 0 | 40.31 |  |  |  | 0 | 40.31 |  |  |  | 0 | 40.31 |  |  |  | 0 | 40.31 |  | 0 | 0 |  | 0 | 0
289 | 54/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 228, Sl. No. 343 of MYT Order | Construction of 220 KV D/C Saharsa(New)- Begusarai Transmission line with ACSR Zebra Conductor (Approx Route Length-100KM) under State Plan against NIT No. 54/PR/BSPTCL/2018. | DCB | 6 | 21.01.2019 | 21.01.2019 | 20.04.2020 | 132.39 | 165.64 | State Plan | 130.56 | 0 | 130.0086 | 1.2885 |  |  | 0 | 131.2972 |  | 141.357 | 0.61573 | 141.9728 | -10.6756 |  |  |  | 141.9728 | -10.6756 |  |  |  | 141.9728 | -10.6756 |  |  |  | 141.9728 | -10.6756 |  | 0 | 0 |  | 0 | 0
290 | 62/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 228, Sl. No. 345 of MYT Order | Construction of 220 kV D/C Raxaul (new) Gopalganj with twin moose conductor. NIT 62/PR/BSPTCL/2018 | DCB |  | 2019-01-21 | 2019-01-21 | 20.04.2021 | 138.98 | 150.09 | State Plan | 137.8 | 0 | 137.8201 |  | 134.8495 | 24.7176 | 159.5671 | -21.7469 |  |  |  | 159.5671 | -21.7469 |  |  |  | 159.5671 | -21.7469 |  |  |  | 159.5671 | -21.7469 |  |  |  | 159.5671 | -21.7469 |  | 0 | 0 |  | 0 | 0
291 | 63/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 228, Sl. No. 346 of MYT Order | Construction of 132 KV line bays 02 nos. at GSS Phulparas. & Construction of 132 KV line bays 02 nos. at GSS Laukahi. NIT 63/PR/BSPTCL/2018 | DCB |  | 2019-01-15 | 2019-01-15 |  | 6.99 | 9.1 | State Plan | 6.99 | 0 | 1.9993 |  |  |  | 0 | 1.9993 | 0.25 |  |  | 0 | 2.2493 |  |  |  | 0 | 2.2493 |  |  |  | 0 | 2.2493 |  |  |  | 0 | 2.2493 |  | 0 | 0 |  | 0 | 0 |  | 0.2 | 0.05
292 | 65/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 228, Sl. No. 347 of MYT Order | Construction of 02 nos. 132 KV line bays each at GSS Muzaffarpur & Vaishali against NIT 65/PR/BSPTCL/2018 | DCB | 4 | 2019-01-14 | 2019-01-14 | 13.07.2019 | 7.04 | 9.32 | State Plan | 7.04 | 5.2461 | -0.31906 |  |  |  | 5.2461 | -0.31906 | 0.02 |  |  | 5.2461 | -0.29906 |  |  |  | 5.2461 | -0.29906 |  |  |  | 5.2461 | -0.29906 |  |  |  | 5.2461 | -0.29906 |  | 0 | 0 |  | 0 | 0 |  | 0.016 | 0.004
293 | 67/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 228, Sl. No. 348 of MYT Order | Construction of 02 No. 220Kv Line Bay at 220/132/33Kv GSS Kishanganj (New) and Construction of 02 Nos 1320Kv Line Bays at 132/33Kv GSS Araria on Turnkey NIT 67/PR/BSPTCL/2018 | DCB | 4 | 2019-01-14 | 2019-01-14 | 13.10.2019 | 10.9 | 10.77 | State Plan | 9.46 | 9.7068 | -0.64363 |  |  |  | 9.7068 | -0.64363 |  |  |  | 9.7068 | -0.64363 |  |  |  | 9.7068 | -0.64363 |  |  |  | 9.7068 | -0.64363 |  |  |  | 9.7068 | -0.64363 |  | 0 | 0 |  | 0 | 0
294 | 70/PR/BSPTCL/2018 | P1 | 13th Plan Upcoming Project | Page No. 229, Sl. No. 349 of MYT Order | Construction of 220Kv D/C by making LILO arrangement of both circuits of 220Kv D/C Purnea(PG) -Begusarai Transmission Line to 220/132/33Kv GSS Korha GSS on Turnkey Basis against NIT- 70/PR/BSPTCL/2018 | DCB |  | 2019-01-14 | 2019-01-14 |  | 14.14 | 14.14 | State Plan | 15.05 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
295 | 71/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 229, Sl. No. 350 of MYT Order | Construction of LILO of 132 KV DCSS Benipatti - Pupari Transmission line at Sitamarhi (new) and LILO of both ckt. of 132 KV Raxaul - Bettiah D/C Transmission line at Raxaul (new) with ACSR Panther Conductor. NIT No.- 71/PR/BSPTCL/2018 | DCB |  | 2019-01-21 | 2019-01-21 |  | 52.8 | 52.8 | State Plan | 44.57 | 0 | 30.8442 | 0.41892 |  |  | 0 | 31.2632 | 0.49 | 0 |  | 0 | 31.7532 |  |  |  | 0 | 31.7532 |  |  |  | 0 | 31.7532 |  |  |  | 0 | 31.7532 |  | 0 | 0 |  | 0 | 0 |  | 0.392 | 0.098
296 | 72/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 229, Sl. No. 351 of MYT Order | Construction of 2nd circuit stringing of 220KV DCSS Darbhanga-Samastipur Transmission Line with ACSR Zebra Conductor NIT 72/PR/BSPTCL/2018 | DCB | 3 | 2019-01-15 | 2019-01-15 | 14.10.2019 | 8.25 | 8.09 | State Plan | 8.25 | 0 | 8.2444 | 0.056201 |  |  | 0 | 8.3006 |  | 0 |  | 0 | 8.3006 |  |  |  | 0 | 8.3006 |  |  |  | 0 | 8.3006 |  |  |  | 0 | 8.3006 |  | 0 | 0 |  | 0 | 0
297 | 79/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 229, Sl. No. 353 of MYT Order | Supply, erection, testing and commissioning of Reliable communication and Data Acquisition for implementation of Integrated Communication system upto 132 KV in Bihar with AMC for 6 years. NIT 79/PR/BSPTCL/2018 | DCB | 4 | 2019-01-21 | 2019-01-21 | 20.07.2020 | 124.74 | 160.4 | State Plan | 122.39 | 0 | 103.5276 | 2.3554 | 106.0102 | 22.049 | 128.0592 | -22.1762 | 0.19 | 0.18836 |  | 128.2476 | -22.1746 |  |  |  | 128.2476 | -22.1746 |  |  |  | 128.2476 | -22.1746 |  |  |  | 128.2476 | -22.1746 |  | 0 | 0 |  | 0 | 0 |  | 0.152 | 0.038
298 | 68/PR/BSPTCL/2018 | P2 | 13th Plan Other Project | Page No. 231, Sl. No. 362 of MYT Order | for Construction of 02 nos. of 220 KV line bays at Begusarai GSS & 02 Nos. 220 KV line bays at Khagaria (New) GSS with SAS on turnkey basis NIT 68/PR/BSPTCL/2018 | DCB |  | 2019-01-15 | 2019-01-15 |  | 12.8 | 16.25 | State Plan | 12.8 | 10.2781 | -0.91439 | 0.5525 | 0.5525 | 0.0020803 | 10.8327 | -0.91647 | 0.28 | 0.28365 |  | 11.1164 | -0.92012 |  |  |  | 11.1164 | -0.92012 |  |  |  | 11.1164 | -0.92012 |  |  |  | 11.1164 | -0.92012 |  | 0 | 0 |  | 0 | 0 |  | 0.224 | 0.056
299 | 107/PR/BSPTCL/2018 | P2 | 13th Plan Other Project | Page No. 231, Sl. No. 363 of MYT Order | Re-Conductoring of 132KV Biharsarif-Baripahari D/C Trans. Line(L-14) and 132 KV Sipara- Mithapur-Karbigahiya Trans. Line(L-07) with HTLS Conductor . NIT 107/PR/BSPTCL/2018 | DCB |  | 2019-02-06 | 2019-02-06 |  | 14.62 | 14.97 | State Plan | 9.2 | 8.59 | 0 | 0.76543 | 0.76543 | 0.00969 | 9.3651 | -0.00969 |  |  |  | 9.3651 | -0.00969 |  |  |  | 9.3651 | -0.00969 |  |  |  | 9.3651 | -0.00969 |  |  |  | 9.3651 | -0.00969 |  | 0 | 0 |  | 0 | 0
300 | 49/PR/BSPTCL2018 | P2 | 13th Plan Other Project | Page No. 231, Sl. No. 366 of MYT Order | Capacity augmentation of different GSS by Addition /Replacement by 200 MVA Power Transformer alongwith associated bays on Turnkey Basis at GSS Khagaul & Sipara NIT No.- 49/PR/BSPTCL2018 | DCB |  | 2019-01-21 | 2019-01-21 |  | 65.41 | 65.46 | State Plan | 65.37 | 0 | 63.9646 | 0.54679 | 64.5136 | 3.3644 | 67.878 | -3.3666 |  |  |  | 67.878 | -3.3666 |  |  |  | 67.878 | -3.3666 |  |  |  | 67.878 | -3.3666 |  |  |  | 67.878 | -3.3666 |  | 0 | 0 |  | 0 | 0
301 | 22/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 231, Sl. No. 367 of MYT Order | For supply contract for design, Manufacture, Assembly, testing, supply, delivery, unloading at site, placing on plinth, erection, testing & commissioning of 04 nos. 20 MVA, 132/33 KV Transformer on turnkey basis NIT 22/PR/BSPTCL/2018 | DCB |  | 2018-10-01 | 2018-10-01 |  | 6.6 | 6.6 | IRF | 6.6 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  | 0 |  |  | 0
302 | 03/PR/BSPTCL/2018 | P2 | 13th Plan Other Project | Page No. 232, Sl. No. 369 of MYT Order | Construction of (2x50) MVA, 132/33 KV GSS Paliganj (Dist.- Patna) and 02 Nos. 132 KV Line Bay Extension at remote end on turnkey basis NIT No.-03/PR/BSPTCL/2018 | DCB |  | 2018-10-03 | 2018-10-03 |  | 24.74 | 24.74 | State Plan | 24.63 | 23.6119 | -0.48595 | 1.5545 | 1.5545 | 0.019302 | 25.1857 | -0.50525 |  |  |  | 25.1857 | -0.50525 |  |  |  | 25.1857 | -0.50525 |  |  |  | 25.1857 | -0.50525 |  |  |  | 25.1857 | -0.50525 |  | 0 | 0 |  | 0 | 0
303 | 41/PR/BSPTCL/2018 | P2 | 13th Plan Other Project | Page No. 232, Sl. No. 370 of MYT Order | Construction of 220/132/33 KV, (2x160 + 3x50) MVA, GSS Asthawan including Residential Quarters with Construction of 02 Nos. 132 KV Line Bays & 06 Nos. 132 KV Line Bays at remote end on turnkey basis. NIT 41/PR/BSPTCL/2018 | DCB |  | 2019-01-21 | 2019-01-21 |  | 104.38 | 106.63 | State Plan | 106.25 | 109.8599 | -5.1132 | 0.49122 | 0.49122 | 0.0043864 | 110.3555 | -5.1176 |  |  |  | 110.3555 | -5.1176 |  |  |  | 110.3555 | -5.1176 |  |  |  | 110.3555 | -5.1176 |  |  |  | 110.3555 | -5.1176 |  | 0 | 0 |  | 0 | 0
304 | 38/PR/BSPTCL/2018 | P2 | 13th Plan Other Project | Page No. 232, Sl. No. 371 of MYT Order | Construction of 220/132/33 KV (2x200 MVA + 3x50MVA) GSS Karmnasha (new) NIT No.- 38/PR/BSPTCL/2018 | DCB | 14 | 2019-01-21 | 2019-01-21 | 20.07.2020 | 86.68 | 95.86 | State Plan | 93.58 | 91.8024 | -4.7299 | 3.6807 | 3.6325 | 0.051831 | 95.4867 | -4.7336 |  |  |  | 95.4867 | -4.7336 |  |  |  | 95.4867 | -4.7336 |  |  |  | 95.4867 | -4.7336 |  |  |  | 95.4867 | -4.7336 |  | 0 | 0 |  | 0 | 0
305 | 35/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 232, Sl. No. 372 of MYT Order | Construction of (2x160 MVA+3x50MVA) 220/132/33 KV GSS, Thakurganj (with SAS) (District-Kishanganj) and Residential Quarters under State Plan on turnkey basiS, against NIT No. 35/PR/BSPTCL/2018 | DCB |  | 2019-01-21 | 2019-01-21 |  | 92.55 | 92.55 | State Plan | 92.55 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
306 | 52/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 233, Sl. No. 375 of MYT Order | Construction of the following lines: (i) 132 KV D/C Thakurganj - Araria Transmission line with ACSR Panther Conductor (ii) 220 KV D/C Kishanganj (New) - Thakurganj Transmission line with ACSR Zebra Conductor. NIT 52/PR/BSPTCL/2018 | DCB |  | 2019-01-21 | 2019-01-21 |  | 148.62 | 167.45 | State Plan | 148.62 | 0 | 86.2603 | 35.9249 |  |  | 0 | 122.1852 | 10.19 | 0 |  | 0 | 122.1852 |  |  |  | 0 | 122.1852 |  |  |  | 0 | 122.1852 |  |  |  | 0 | 122.1852 |  | 0 | 0 |  | 0 | 0 |  | 8.152 | 2.038
307 | 15/PR/BSPTCL/2019 & 73/2018 | P1 | 13th Plan Other Project | Page No. 190, Sl. No. 255 of MYT Order | Construction o f (2x500+2x160) MVA 400/220/132 KV GIS Grid Sub-Station Bakhtiyarpur with SAS under turnkey basis. NIT No. 15/PR/BSPTCL/2019. retendered from 73/2018 | DCB | 7 | 26.11.2019 | 26.11.2019 | 25.05.2021 | 250.51 | 250.51 | State Plan | 219.66 | 0 | 161.8547 | 30.4217 |  |  | 0 | 192.2764 | 8.96 | 201.4782 |  | 201.4782 | 0.9882 |  |  |  | 0 | 0.9882 |  |  |  | 0 | 0.9882 |  |  |  | 0 | 0.9882 |  | 0 | 0 |  | 0 | 0 |  | 7.168 | 1.792
308 | 64/PR/BSPTCL/2018 | P2 | 13th Plan Other Project | Page No. 190, Sl. No. 256 of MYT Order | For erection including associated civil works, testing and commissioning including performance testing of all the equipments supplied under supply contract and all other services specified in the tender documents required for construction of 220KV D/C transmission line from GSS Amnour(BGCL) to 220/132/33KV GSS Digha(New) on turnkey basis. NIT 64/PR/BSPTCL/2018 | DCB |  | 2019-01-21 | 2019-01-21 | 20.07.2020 | 188.85 | 200.62 | State Plan | 174.98 | 0 | 171.1712 | 0.38285 | 162.3833 | 14.0761 | 176.4594 | -4.9054 |  |  |  | 176.4594 | 4.0546 |  |  |  | 176.4594 | 4.0546 |  |  |  | 176.4594 | 4.0546 |  |  |  | 176.4594 | 4.0546 |  | 0 | 0 |  | 0 | 0
309 | 121/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 191, Sl. No. 259 of MYT Order | Construction of onstrcution of 4 Nos of 132/33Kv Transformer Bay in Saran, Koshi, Bhagalpur on Turnkey NIT 121/PR/BSPTCL/2018 | DCB | 5 | 2019-02-25 | 2019-02-25 | 24.11.2019 | 8.45 | 10.66 | State Plan | 9.46 | 0 | 9.3835 |  |  |  | 0 | 9.3835 |  |  |  | 0 | 9.3835 |  |  |  | 0 | 9.3835 |  |  |  | 0 | 9.3835 |  |  |  | 0 | 9.3835 |  | 0 | 0 |  | 0 | 0
310 | 122/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 191, Sl. No. 260 of MYT Order | Construction of 132 KV line bays 03 nos. of 132/33 KV Transformer Bays in Biharsharif and Dehri-on Sone NIT 122/PR/BSPTCL/2018 | DCB | 6 | 2019-02-25 | 2019-02-25 | 24.11.2019 | 7.22 | 7.99 | State Plan | 5.96 | 0 | 4.9405 |  |  |  | 0 | 4.9405 |  |  |  | 0 | 4.9405 |  |  |  | 0 | 4.9405 |  |  |  | 0 | 4.9405 |  |  |  | 0 | 4.9405 |  | 0 | 0 |  | 0 | 0
311 | 128/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 191, Sl. No. 264 of MYT Order | Supply, erection, testing and commissioning of 05 Nos. of 50 MVA Power Transformer with construction/modification of foundation in Transmission Circle Purnea & Bhagalpur on turnkey basis under State Plan against NIT 128/PR/BSPTCL/2018 | DCB | 3 | 2019-02-25 | 2019-02-25 | 24.02.2020 | 18.95 | 18.38 | State Plan | 18.24 | 18.37 | 0 |  |  |  | 18.37 | 0 |  |  |  | 18.37 | 0 |  |  |  | 18.37 | 0 |  |  |  | 18.37 | 0 |  |  |  | 18.37 | 0 |  | 0 | 0 |  | 0 | 0
312 | 129/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 192, Sl. No. 265 of MYT Order | Supply, erection, testing and commissioning of 05 Nos. of 50 MVA Power Transformer with construction/modification of foundation in Transmission Circle Patna & Dehri-on -sone on turnkey basis under State Plan against NIT No. 129/PR/BSPTCL/2018 | DCB | 4 | 2019-02-25 | 2019-02-25 | 24.02.2020 | 17.09 | 18.38 | State Plan | 17.1 | 16.5862 | -2.7756e-17 |  |  |  | 16.5862 | -2.7756e-17 |  |  |  | 16.5862 | -2.7756e-17 |  |  |  | 16.5862 | -2.7756e-17 |  |  |  | 16.5862 | -2.7756e-17 |  |  |  | 16.5862 | -2.7756e-17 |  | 0 | 0 |  | 0 | 0
313 | 16/PR/BSPTCL/2019 | P1 | 13th Plan Upcoming Project | Page No. 341, Sl. No. 354 of MYT Order | Construction of 4 Nos of 220 KV GIS bays and 4 nos of 132 KV GIS bays at 220/132/33 KV GSS Chhapra(new), Amnaur against NIT No.- 16/PR/BSPTCL/2019 | [5 empty] | 41.59 | 0 | State Plan | 41.58 | 0 | 35.3102 | 0.57319 | 35.8834 | 1.9186 | 37.8021 | -1.9186 | 0.07 | 0.070008 |  | 37.8721 | -1.9886 |  |  |  | 37.8721 | -1.9886 |  |  |  | 37.8721 | -1.9886 |  |  |  | 37.8721 | -1.9886 |  | 0 | 0 |  | 0 | 0 |  | 0.056 | 0.014
314 | 02/PR/BSPTCL/2019 | P1 | 13th Plan Upcoming Project | Page No. 341, Sl. No. 355 of MYT Order | Construction of 2 Nos of 220 KV GIS Bays at 220/132/33 KV GSS Gopalganj against NIT No.- 02/PR/BSPTCL/2019 | [5 empty] | 22.26 | 0 | State Plan | 22.26 | 0 | 20.5742 | 1.7767 |  |  | 0 | 22.3509 | 1.4 | 24.6455 |  | 24.6455 | -2.2246 |  |  |  | 24.6455 | -2.2246 |  |  |  | 24.6455 | -2.2246 |  |  |  | 24.6455 | -2.2246 |  | 0 | 0 |  | 0 | 0 |  | 1.12 | 0.28
315 | 08/PR/BSPTCL/2019 | P2 | 13th Plan Other Project | Page No. 342, Sl. No. 357 of MYT Order | Construction of 04 Nos. 220 KV GIS Line Bays at GSS Sheikhpura(GIS, BGCL) & 02 nos. 220 KV GIS Line Bays at GSS Hathidah (GIS, BGCL) (Total 06 nos. of GIS Line Bays) on turnkey basis against NIT No. 08/PR/BSPTCL/2019 | DCB |  | 10.12.2019 | 10.12.2019 | 09.12.2020 | 41.51 | 46.95 | State Plan | 38.05 | 0 | 2.7435 | 19.6151 |  |  | 0 | 22.3586 | 3.37 |  |  | 0 | 23.7586 | 0 | 38.05 |  | 38.05 | -14.2914 |  |  |  | 38.05 | -14.2914 |  |  |  | 38.05 | -14.2914 |  | 0 | 0 |  | 0 | 0 |  | 2.696 | 0.674
316 | 100/PR/BSPTCL/2018 | P2 | 13th Plan Other Project | Page No. 192, Sl. No. 267 of MYT Order | Construction of 220 KV D/C Transmission Line for LILO of both circuits of 220 KV D/C Gaya (PG)- Sonenagar Trans. Line at both 220/132/33 KV GSS Bodhgaya & 400/220/132 KV GSS Chandauti (New) on Turn Key Basis NIT 100/PR/BSPTCL/2018 | DCB |  | 2019-01-21 | 2019-01-21 | 20.01.2020 | 42.19 | 0 | State Plan | 43.33 | 0 | 42.1476 | 1.6099 |  |  | 0 | 43.7575 |  | 0 |  | 0 | 43.7575 |  |  |  | 0 | 43.7575 |  |  |  | 0 | 43.7575 |  |  |  | 0 | 43.7575 |  | 0 | 0 |  | 0 | 0
318 | 17/PR/BSPTCL/2019 | P2 | 13th Plan Other Project | Page No. 192, Sl. No. 269 of MYT Order | Construction of 2x80MVA, 132/33 KV Gas Insulated Sub-station at Board colony Patna on turnkey basis against NIT No. 17/PR/BSPTCL/2019 under State Plan | DCB |  | 11.11.2019 | 11.11.2019 | 10.04.2021 | 58.27 | 0 | State Plan | 58.27 | 0 | 24.7629 | 8.6154 |  |  | 0 | 33.3783 | 0.59 | 37.7916 | 0.35063 | 38.1422 | -4.1739 | 20.1278 | 20.13 |  | 58.2722 | -4.1761 |  |  |  | 58.2722 | -4.1761 |  |  |  | 58.2722 | -4.1761 |  | 16.1022 | 4.0256 |  | 0 | 0 |  | 0.472 | 0.118
319 | 19/PR/BSPTCL/2019 | P2 | 13th Plan Other Project | Page No. 193, Sl. No. 270 of MYT Order | Construction of 132 KV D/C transmission line with cable from 220/132/33 KV Gas Insulated Sub-station at Digha (new) to 132/33 KV Gas Insulated Sub-station at Board colony (CKM – 7 KM) and construction of 132 KV D/C transmission line with cable from 220/132/33 KV Gas Insulated Sub-station at Digha (new) to Digha (Old) (CKM – 1 KM ) on turnkey basis against NIT No. 19/PR/BSPTCL/2019 |  |  | 03.06.2022 | 03.06.2022 | 02.12.2021 | 68.59 | 0 | State Plan | 68.59 | 0 | 70.114 | 7.5163 | 78.089 | 6.2602 | 84.3492 | -6.7189 | 0.19 | 7.5422 |  | 91.8914 | -14.0711 |  |  |  | 91.8914 | -14.0711 |  |  |  | 91.8914 | -14.0711 |  |  |  | 91.8914 | -14.0711 |  | 0 | 0 |  | 0 | 0 |  | 0.152 | 0.038
320 | 07/PR/BSPTCL/2020 | P2 | 13th Plan Other Project | Page No. 235, Sl. No. 392 of MYT Order | Successful completion of balance work of construction of 220 KV D/C Transmission Line from GSS Dehri to GSS Pusauli, ACSR Zebra Conductor. (RL-63Km) against NIT No. 07/PR/BSPTCL/2020 | DCB |  | 01.06.2020 | 01.06.2020 | 31.05.2021 | 25.21 | 0 | IRF | 25.21 | 0 | 13.0312 | 8.333 |  |  | 0 | 21.3642 | 0.95 | 0 |  | 0 | 22.3142 |  |  |  | 0 | 22.3142 |  |  |  | 0 | 22.3142 |  |  |  | 0 | 22.3142 |  |  | 0 |  |  | 0 |  |  | 0.95
321 | 135/2018 | P1 | 13th Plan Other Project | Page No. 236, Sl. No. 393 of MYT Order | Line shifting of tower of 132 KV S/C Purnea- Dhamdaha Transmission Line due to construction of Goat Rearing and breeding Centre at maranga, Purnea, NIT-135/2018 | [7 empty] | State Plan | 0.85 | 0.85 | 0 |  |  |  | 0.85 | 0 |  |  |  | 0.85 | 0 |  |  |  | 0.85 | 0 |  |  |  | 0.85 | 0 |  |  |  | 0.85 | 0 |  | 0 | 0 |  | 0 | 0
322 | 18/PR/BSPTCL/2019 | P2 | 13th Plan Other Project | Page No. 230, Sl. No. 356 of MYT Order | Construction of 2X 200 MVA + 2X80 MVA ), 220/132/33 KV GIS at Digha (New) against NIT No. 18/PR/BSPTCL/2019 under state plan. | DCB |  |  |  |  | 104.99 | 0 | State Plan | 104.99 | 0 | 35.3821 | 47.0831 |  |  | 0 | 82.4652 | 7.03 | 99.0763 |  | 99.0763 | -9.5811 |  |  |  | 99.0763 | -9.5811 |  |  |  | 99.0763 | -9.5811 |  |  |  | 99.0763 | -9.5811 |  | 0 | 0 |  | 0 | 0 |  | 5.624 | 1.406
323 | 47/PR/BSPTCL/2018 | P2 | 13th Plan Other Project | Page No. 175, Sl. No. 113 of MYT Order | Construction of 132 KV transmission line (2-Phase) from Jamalpur (BSPTCL) to TSS Jamalpur of route length 5.0KM (4.0 KM through overhead and 01 KM through Underground XLPE cable) and one no associated 132 KV Bay at Jamalpur on turnkey basis | DCB | 3 | 15.01.2019 | 15.01.2019 | 14.11.2019 | 10.58 |  | Deposit Work | 0 | 11.0064 | -0.0016319 |  |  |  | 11.0064 | -0.0016319 |  |  |  | 11.0064 | -0.0016319 |  |  |  | 11.0064 | -0.0016319 |  |  |  | 11.0064 | -0.0016319 |  |  |  | 11.0064 | -0.0016319 | 0
324 | 03/PR/BSPTCL/2020 | P2 | 13th Plan Other Project | Page No. 192, Sl. No. 267 of MYT Order | construction of one no of D/C transmission line for river crossing (Chanan river) with 01 no pile foundation and 01 no open foundation required for erection of 33 KV feeder from 132/33 kv GSS Banka to new 33/11 KV Gokula PSS on turnkey basis under Deposit Scheme | DCB | 3 | 05.05.2020 | 05.05.2020 | 05.11.2020 | 2.57 | 0 | Deposit Work | 2.055 | 2.0546 | -0.73567 |  |  |  | 2.0546 | -0.73567 |  |  |  | 2.0546 | -0.73567 |  |  |  | 2.0546 | -0.73567 |  |  |  | 2.0546 | -0.73567 |  |  |  | 2.0546 | -0.73567 | 0
325 | 18/PR/BSPTCL/2018 | O&M | 13th Plan Other Project | Page No. 192, Sl. No. 268 of MYT Order | For shifting/Height raising of 132 KV D/C Biharsharif-Sheikhpura transmission line between Railway station Barbigha-Sheikhpura in Dist-Sheikhpura from LOC no-127 to 130 on turnkey basis. NIT-18/PR/BSPTCL/2018 | DCB |  | 2018-10-23 | 2018-10-23 |  | 1.08 |  | Deposit Work | 0 | 1.0685 | 0.0061943 |  |  |  | 1.0685 | 0.0061943 |  |  |  | 1.0685 | 0.0061943 |  |  |  | 1.0685 | 0.0061943 |  |  |  | 1.0685 | 0.0061943 |  |  |  | 1.0685 | 0.0061943 | 0
326 | 11/PR/BSPTCL/2019 | P2 | 13th Plan Other Project | Page No. 306, Sl. No. 226 of MYT Order | construction of 132 KV S/C transmission line (2-Phase) from Naugachia (BSPTCL)-Naugachia TSS (Approx-RL-3KM) on turnkey basis under Deposit head | DCB | 2 | 01.07.2019 | 01.07.2019 | 31.03.2020 | 2.01 |  | Deposit Work | 2.01 | 1.4789 | 0.0017449 | 0.033001 |  |  | 1.4789 | 0.034746 |  | 0 |  | 1.4789 | 0.034746 |  |  |  | 1.4789 | 0.034746 |  |  |  | 1.4789 | 0.034746 |  |  |  | 1.4789 | 0.034746 | 0
327 | 01/PR/BSPTCL/2019 | P2 | 13th Plan Other Project | Page No. 306, Sl. No. 227 of MYT Order | TR line Nalanda and Railway TSS Nalanda, NIT- 01/2019 | DCB | 5 | 15.06.2019 | 15.06.2019 | 14.03.2020 | 4.856 | 0 | Deposit Work | 4.88 | 4.8808 | -0.0056382 |  |  |  | 4.8808 | -0.0056382 |  |  |  | 4.8808 | -0.0056382 |  |  |  | 4.8808 | -0.0056382 |  |  |  | 4.8808 | -0.0056382 |  |  |  | 4.8808 | -0.0056382 | 0
328 | 60/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 185, Sl. No. 227 of MYT Order | Construction of 220 KV D/C Sitamarhi (new) GSS - Raxaul (new) GSS on Twin Moose. NIT 60/PR/BSPTCL/2018 | DCB |  | 2019-01-21 | 2019-01-21 | 20.04.2020 | 194.21 | 214.05 | State Plan | 120.91 | 135.6038 | -15.7387 |  |  |  | 135.6038 | -15.7387 |  |  |  | 135.6038 | -15.7387 |  |  |  | 135.6038 | -15.7387 |  |  |  | 135.6038 | -15.7387 |  |  |  | 135.6038 | -15.7387 |  | 0 | 0 |  | 0 | 0
329 | 19/PR/BSPTCL/2017 | P2 | 12th Plan Ongoing Project | Page No. 164, Sl. No. 152 of MYT Order | Construction of 06 nos. of 132kV D/C towers from Ara (PG) to tower loc. No. 01 with ACSR Panther Conductor for connectivity of 2nd circuit of 132kV D/C Ara (PG) – Jagdishpur Transmission Line | [7 empty] | BRGF | 0 | 2.4298 | 0 |  |  |  | 2.4298 | 0 |  |  |  | 2.4298 | 0 |  |  |  | 2.4298 | 0 |  |  |  | 2.4298 | 0 |  |  |  | 2.4298 | 0 |  |  | 0 |  |  | 0
330 | 35/PR/BSPTCL/2015 | P1 | 12th Plan Ongoing Project | Page No. 162, Sl. No. 33 of MYT Order | Construction of 132KV Transmission lines connecting the revenue GSS Bakhri, Ballia, Manjhaul, Nirmali, Triveniganj, Banmankhi, Manihari and Piro against NIT No. 35/PR/BSPTCL/2015 | DCB | 2 | 2015-08-12 | 2015-08-12 | 2016-08-12 | 86.97 | 103.74 | State Plan | 97.13 | 94.2373 | -0.0075906 |  |  |  | 94.2373 | -0.0075906 |  |  |  | 94.2373 | -0.0075906 |  |  |  | 94.2373 | -0.0075906 |  |  |  | 94.2373 | -0.0075906 |  |  |  | 94.2373 | -0.0075906 |  | 0 | 0 |  | 0 | 0
331 | 02/PR/BSPTCL/2017 | P2 | 12th Plan Ongoing Project | Page No. 200, Sl. No. 54 of MYT Order | Construction of 132 KV S/C Transmission Line for Solar PV project of M/s Alfa Infraprop Pvt. Ltd. at Bhagaura from 132/33 KV GSS Rafiganj and 2) Construction of 01 Nos. of 132 KV line bay at GSS Rafiganj for connecting solar PV project of M/s Alfa Infraprop Pvt. Ltd. | DCB | 2 | 2017-03-27 | 2017-03-27 | 2017-09-26 | 9.74 | 9.74 | State Plan | 10.66 | 10.5584 | 0 |  |  |  | 10.5584 | 0 |  |  |  | 10.5584 | 0 |  |  |  | 10.5584 | 0 |  |  |  | 10.5584 | 0 |  |  |  | 10.5584 | 0 |  | 0 | 0 |  | 0 | 0
332 | 06/PR/BSPTCL/2020 | P2 | 13th Plan Other Project | Page No. 235, Sl. No. 391 of MYT Order | Successful completion of balance work of construction of 132 KV DCSS Transmission Line from 132/33 KV GSS Bettiah to 132/33 KV GSS Thakraha with Panther Conductor against NIT No. 06/PR/BSPTCL/2020 | DCB |  | 2020-06-01 | 2020-06-01 | 28.02.2021 | 16.73 |  | IRF | 13.29 | 13.1867 | -10.0926 |  |  |  | 13.1867 | -10.0926 |  |  |  | 13.1867 | -10.0926 |  |  |  | 13.1867 | -10.0926 |  |  |  | 13.1867 | -10.0926 |  |  |  | 13.1867 | -10.0926 |  |  | 0 |  |  | 0
333 | 61/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 337, Sl. No. 344 of MYT Order | Construction of 220 KV D/C Sitamarhi (new) GSS - Motipur (new) GSS on Twin Moose. & Construction of 132 KV D/C Sitamarhi (new) GSS - Runnisaidpur GSS on Twin Moose. NIT 61/PR/BSPTCL/2018 | DCB |  | 2019-01-21 | 2019-01-21 | 20.04.2020 | 112.81 | 119.65 | State Plan | 111.79 | 117.7478 | -6.8925 |  |  |  | 117.7478 | -6.8925 |  |  |  | 117.7478 | -6.8925 |  |  |  | 117.7478 | -6.8925 |  |  |  | 117.7478 | -6.8925 |  |  |  | 117.7478 | -6.8925 |  | 0 | 0 |  | 0 | 0
334 | 52/PR/BSPTCL/2016 | P1 | 12th Plan Ongoing Project | Page No. 208, Sl. No. 119 of MYT Order | 1. .For Construction of 23 Nos Pile Foundation in River koshi Including Setting of stubs and earting system for the connectivity of 220 Kv D/C transmission Line from Laukahi to Supaul ,NIT-52/2016 | DCB |  | 29.03.2017 | 29.03.2017 | 28.09.2017 | 36.68 Cr | 1370.02 | BRGF | 44.52 | 45.6183 | 0 |  |  |  | 45.6183 | 0 |  |  |  | 45.6183 | 0 |  |  |  | 45.6183 | 0 |  |  |  | 45.6183 | 0 |  |  |  | 45.6183 | 0 |  |  | 0 |  |  | 0
335 | 82/PR/BSPTCL/2014 | P1 | 12th Plan Ongoing Project | Page No. 196, Sl. No. 22 of MYT Order | (i) construction of 132 KV S/C transmission lines on D/C Tower from 132/33 KV Dhaka GSS to upcoming Pakridayal GSS (ii) Construction of New 132 KV S/C Transmission line on D/C Tower from 220/132 KV Motipur GSS to upcoming Chakiya GSS (iii) LILO of 132 KV S/C of Jainagar-Phulparas Transmission Line at upcoming Jhanjharpur GSS NIT No 82/PR/BSPTCL/2014 | DCB | 2 | 2015-03-12 | 2015-03-12 | 2016-02-17 | 48.16 | 48.16 | State Plan | 48.16 | 49.9149 | -0.27489 |  |  |  | 49.9149 | -0.27489 |  |  |  | 49.9149 | -0.27489 |  |  |  | 49.9149 | -0.27489 |  |  |  | 49.9149 | -0.27489 |  |  |  | 49.9149 | -0.27489 |  | 0 | 0 |  | 0 | 0
336 | 76/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 229, Sl. No. 352 of MYT Order | Tr. Line Benipatti-Pupri & bettiah- Raxaul | DCB | 3 | 2019-01-14 | 2019-01-14 | 13.07.2019 | 10.41 | 12.31 | State Plan | 9.68 | 8.8715 | -0.15063 | 0.55123 | 0.55123 | 0.0083475 | 9.4311 | -0.15898 | 0.09 |  |  | 9.4311 | -0.06898 |  |  |  | 9.4311 | -0.06898 |  |  |  | 9.4311 | -0.06898 |  |  |  | 9.4311 | -0.06898 |  | 0 | 0 |  | 0 | 0 |  | 0.072 | 0.018
337 | 04/PR/BSPTCL/2014 | P2 | 12th Plan Ongoing Project | Page No. 206, Sl. No. 108 of MYT Order | Construction of new 220 KV S/C Trans. Line on D/C Tower and associated 01 No. 330KV Bay at GSS Sipara(Gaurichak) for connecting 220/132/33 KV GSS Sipara(Gaurichak) with 400/220 KV Patna(PG) for evacuation of power from PGCIL | [7 empty] | BRGF | 0 | 4.9897 | 0 |  |  |  | 4.9897 | 0 |  |  |  | 4.9897 | 0 |  |  |  | 4.9897 | 0 |  |  |  | 4.9897 | 0 |  |  |  | 4.9897 | 0 |  |  | 0 |  |  | 0
338 | 24/PR/BSPTCL/2016 | P2 | 12th Plan Ongoing Project | Page No. 268, Sl. No. 79 of MYT Order | Construction of 132 KV D/C Transmission Line between 220/132/33 KV Bihta (New) GSS and 132/33KV Upcoming Paliganj GSS NIT No.- 24/PR/BSPTCl/2016 | DCB | 4 | 2016-11-18 | 2017-11-17 | 2019-02-28 | 19.4 | 19.4 | State Plan | 18.85 | 19.3858 | 0.35401 |  |  |  | 19.3858 | 0.35401 |  |  |  | 19.3858 | 0.35401 |  |  |  | 19.3858 | 0.35401 |  |  |  | 19.3858 | 0.35401 |  |  |  | 19.3858 | 0.35401 |  | 0 | 0 |  | 0 | 0
339 | 16/PR/BSPTCL/2014 | P1 | 12th Plan Ongoing Project | Page No. 159, Sl. No. 17 of MYT Order | construction of 132KV D/C Udakishanj-Sonebarsha Trans. Line(Approx Length- 55 Rkm) and construction of 132 KV D/C Kusheshwarsthan-Sonebarsha Trans. Line (Approx Length-75 Rkm) | DCB | 2 | 2015-01-06 | 2015-01-06 | 2016-04-05 | 85.26 | 114.7 | BRGF | 114.7 | 115.1997 | 0 |  |  |  | 115.1997 | 0 |  |  |  | 115.1997 | 0 |  |  |  | 115.1997 | 0 |  |  |  | 115.1997 | 0 |  |  |  | 115.1997 | 0 |  |  | 0 |  |  | 0
340 | 12/PR/BSPTCL/2016 | P1 | 12th Plan Ongoing Project | Page No. 202, Sl. No. 69 of MYT Order | Construction of LILO line on both circuits of 220 KV Begusarai- Purnea (PG)Transmission line at Khagariya new 220/132/33 KV GSS against NIT 12/PR/BSPTCL/2016 Pkg-A under state plan. | DCB | 3 | 2016-08-30 | 2016-08-30 | 2017-08-30 | 8.86 | 9.63 | State Plan | 9.14 | 9.5706 | 0 |  |  |  | 9.5706 | 0 |  |  |  | 9.5706 | 0 |  |  |  | 9.5706 | 0 |  |  |  | 9.5706 | 0 |  |  |  | 9.5706 | 0 |  | 0 | 0 |  | 0 | 0
341 | 19/PR/BSPTCL/2014 Package-C | P1 | 12th Plan Old Projects | Page No. 205, Sl. No. 94 of MYT Order | construction of 132 kv DCtransmission line with ACSR penthor conductor from Kishanganj(new) to Forbisganj (approx line length 85 RKM) under special plan/BRGF part 2 Kishanganj project Bihar, NIT-19/2014, Pkg C | DCB | 2 | 19.11.2014 | 19.11.2014 | 18.02.2016 | 49.62 |  | BRGF | 52.18 | 1.5198 | -0.10484 |  |  |  | 1.5198 | -0.10484 |  |  |  | 1.5198 | -0.10484 |  |  |  | 1.5198 | -0.10484 |  |  |  | 1.5198 | -0.10484 |  |  |  | 1.5198 | -0.10484 |  |  | 0 |  |  | 0
342 | 58/PR/BSPTCL/2014 | P1 | 12th Plan Ongoing Project | Page No. 210, Sl. No. 141 of MYT Order | construction of(i)2x220 KV D/C Trans. Line from Kishanganj(New) to Kishanganj(PG)(LL-2x4 RKM) &(ii) Const. of 132 KV D/C Trans. Line from Kishanganj(New) to Kishangang(Existing)(Apprx LL-11 RKM)(BRGF Ph-III Part-II) | DCB | 2 | 06.02.2015 | 06.02.2015 | 05.02.2016 | 17.49 | 25.92 | BRGF | 25.92 | 26.4953 | 0 |  |  |  | 26.4953 | 0 |  |  |  | 26.4953 | 0 |  |  |  | 26.4953 | 0 |  |  |  | 26.4953 | 0 |  |  |  | 26.4953 | 0 |  |  | 0 |  |  | 0
343 | 10/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 306, Sl. No. 228 of MYT Order | For design, manufacture, testing at manufacturer’s works and delivery of equipments required for construction of one no of 132 KV single circuit transmission line (2-Phase strung) on D/C tower from Masrakh GSS to Rajpatti TSS & one no of 132 KV Bay at GSS Masrakh on turnkey basis | [7 empty] | Deposit Work | 0 | 6.4162 | -0.0018687 |  |  |  | 6.4162 | -0.0018687 |  |  |  | 6.4162 | -0.0018687 |  |  |  | 6.4162 | -0.0018687 |  |  |  | 6.4162 | -0.0018687 |  |  |  | 6.4162 | -0.0018687 | 0
344 | 25/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 171, Sl. No. 65 of MYT Order | construction of 132KV traction transmission line (2-phase strung) on D/C tower between GSS Pandaul & TSS Pandaul with ACSR panther conductor(Line length -08 RKM) and construction of 132 KV S/C transmission line (2- Ph strung) on D/C tower between GSS Rosera & TSS Hasanpur, NIT-25/2018 | DCB | [6 empty] | Deposit Work | 0 | 13.9619 | 0 |  |  |  | 13.9619 | 0 |  |  |  | 13.9619 | 0 |  |  |  | 13.9619 | 0 |  |  |  | 13.9619 | 0 |  |  |  | 13.9619 | 0 | 0
345 | 86/PR/BSPCL/2015 | P2 | 12th Plan Ongoing Project | Page No. 222, Sl. No. 72 of MYT Order | construction of 132/33 KV 3x50 MVA Jamui and Banka GSS against NIT 86/PR/BSPTCL/2015 | DCB | 3 | 2015-12-31 | 2015-12-31 | 2016-12-30 | 52.29 | 52.29 | State Plan | 59.8 | 61.2244 | 0.88727 | 0.0944 | 0.0944 |  | 61.3188 | 0.88727 |  | 0.076347 |  | 61.3951 | 0.81092 |  |  |  | 61.3951 | 0.81092 |  |  |  | 61.3951 | 0.81092 |  |  |  | 61.3951 | 0.81092 |  | 0 | 0 |  | 0 | 0
346 | 131/PR/BSPTCL/2018 | P2 | 13th Plan Other Project | Page No. 218, Sl. No. 234 of MYT Order | construction of 01 no 132 KV line bay at GSS Sabour for Railway TSS on turnkey basis, NIT- 131/2018 |  |  | 08.03.2019 | 08.03.2019 | 08.12.2019 | 2.37 | 0 | Deposit Work | 2.37 | 2.3718 | 0.0003348 |  |  |  | 2.3718 | 0.0003348 |  |  |  | 2.3718 | 0.0003348 |  |  |  | 2.3718 | 0.0003348 |  |  |  | 2.3718 | 0.0003348 |  |  |  | 2.3718 | 0.0003348 | 0
347 | 24/PR/BSPTCL/2015 | P1 | 12th Plan Ongoing Project | Page No. 168, Sl. No. 25 of MYT Order | Strengthening of 132 KV & 33 KV main bus and transfer bus by double moose &quad moose respectively of different GSS of BSPTCL NIT no. 24 /PR/BSPTCL/2015 | DCB |  |  |  |  | 61.57 | 67.17 | State Plan | 64.62 | 66.9796 | 0 |  |  |  | 66.9796 | 0 |  |  |  | 66.9796 | 0 |  |  |  | 66.9796 | 0 |  |  |  | 66.9796 | 0 |  |  |  | 66.9796 | 0 |  | 0 | 0 |  | 0 | 0
348 | 126/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 191, Sl. No. 262 of MYT Order | For Supply,Erection,testing and commissioning of 06 Nos.of 50 MVA Power Transformer with Construction/Modification of foundation in Transmission Circle Saran, Koshi & Darbhanga NIT 126/PR/BSPTCL/2018 | DCB | 4 | 2019-02-25 | 2019-02-25 | 24.02.2020 | 23.36 | 22.05 | State Plan | 21.55 | 21.7449 | 0.02667 |  |  |  | 21.7449 | 0.02667 |  |  |  | 21.7449 | 0.02667 |  |  |  | 21.7449 | 0.02667 |  |  |  | 21.7449 | 0.02667 |  |  |  | 21.7449 | 0.02667 |  | 0 | 0 |  | 0 | 0
349 | 61/PR/BSPTCL/2015 | P2 | 12th Plan Ongoing Project | Page No. 199, Sl. No. 51 of MYT Order | Renovation & Up gradation of Protection and Control Systems of 220/132KV Grid Substation at Biharsharif, Fatuha, Bodhgaya, Dehri On Sone, Khagaul and 132/33KV Grid Substation Kataiya on turnkey basis 61/2015 | DCB | 4 | 2015-12-31 | 2015-12-31 | 2016-12-30 | 69.66 | 69.66 | PSDF | 67.82 | 66.7775 | 2.5714 |  |  |  | 66.7775 | 2.5714 |  |  |  | 66.7775 | 2.5714 |  |  |  | 66.7775 | 2.5714 |  |  |  | 66.7775 | 2.5714 |  |  |  | 66.7775 | 2.5714
350 | 61/PR/BSPTCL/2015 | P2 | 12th Plan Ongoing Project | Page No. 199, Sl. No. 51 of MYT Order | Capicity Augmentation of biharshariff, Fatuha, Bodhgaya, Dehri on Sone , Khagaul and GSS kataiya | DCB | 4 | 2015-12-31 | 2015-12-31 | 2016-12-30 | 69.66 | 69.66 | State Plan | 67.82 | 1.0042 | -1.0042 |  |  |  | 1.0042 | -1.0042 |  |  |  | 1.0042 | -1.0042 |  |  |  | 1.0042 | -1.0042 |  |  |  | 1.0042 | -1.0042 |  |  |  | 1.0042 | -1.0042 |  | 0 | 0 |  | 0 | 0
351 | 30/PR/BSPTCL/2015 | P1 | 13th Plan Other Project | Page No. 211, Sl. No. 153 of MYT Order | work of capicity augmentation by addition of 50 MVA, 132/33 KV Power Transformer at GSS Jakkanpur, Bariparahi, Chandauti, Jehanabad,Sitamarhi & Begusarai and replacement of 20 MVA, 132/33 KV Power transformer at GSS Dumraon, Raxaul & Purnea with construction/modification of associated 132 KV & 33 KV Transformer bays | [5 empty] | 0 | 0 | BRGF | 43.52 | 7.3186 | 0.21937 |  |  |  | 7.3186 | 0.21937 |  |  |  | 7.3186 | 0.21937 |  |  |  | 7.3186 | 0.21937 |  |  |  | 7.3186 | 0.21937 |  |  |  | 7.3186 | 0.21937 |  |  | 0 |  |  | 0
352 | 48/PR/BSPTCL/2015 | P2 | 12th Plan Old Projects | Page No. 268, Sl. No. 83 of MYT Order | R&M Work of 132/33 KV GSS Rajgir & Gaighat, NIT-48/2015 | DCB | [5 empty] | 18.04 | State Plan | 18.04 | 19.3673 | 0 |  |  |  | 19.3673 | 0 |  |  |  | 19.3673 | 0 |  |  |  | 19.3673 | 0 |  |  |  | 19.3673 | 0 |  |  |  | 19.3673 | 0 |  | 0 | 0 |  | 0 | 0
353 | 427/PR/BSPTCL/2013 Package F | P1 | 12th Plan Ongoing Project | Page No. 291, Sl. No. 164 of MYT Order | R&M of 132/33 Kv GSS Lakhisarai,Jamui & Hathidah , NIT-427/2013 F | DCB | 1 | 04.03.2014 | 04.03.2014 | 03.03.2015 | 16.94 |  | BRGF | 19.69 | 19.7497 | 0.045181 |  |  |  | 19.7497 | 0.045181 |  |  |  | 19.7497 | 0.045181 |  |  |  | 19.7497 | 0.045181 |  |  |  | 19.7497 | 0.045181 |  |  |  | 19.7497 | 0.045181 |  |  | 0 |  |  | 0
354 | 62/PR/BSPTCL/2014 pkg B | P1 | 12th Plan Ongoing Project | Page No. 197, Sl. No. 36 of MYT Order | Construction of 132/33 KV Grid Sub-station, Belsand (2X10MVA), Shahpur Patori (2X20MVA) and Benipur (2X10MVA), NIT- 62/BSPTCL/2014 Pkg-B under state plan on turnkey basis against NIT No.-62/PR/BSPTCL/2014 | DCB | 2 | 2015-03-21 | 2015-03-21 | 2016-03-20 | 55.51 | 55.51 | State Plan | 59.61 | 62.969 | -2.0047 | 1.9173 | 4.1175 |  | 67.0865 | -4.2049 | 0.37 | 0.046615 |  | 67.1331 | -3.8815 |  |  |  | 67.1331 | -3.8815 |  |  |  | 67.1331 | -3.8815 |  |  |  | 67.1331 | -3.8815 |  | 0 | 0 |  | 0 | 0 |  | 0.296 | 0.074
355 | 94/PR/BSPTCL/2014 | - | 12th Plan Old Projects | Page No. 212, Sl. No. 170 of MYT Order | 132/33Kv GSS Rosera NIT No. 94/2014 | DCB |  | 20.05.15 | 20.05.15 | 04.07.16 | 82.10 Cr | 668.72 | State Plan | 88.7 | 3.3708 | -3.3708 |  |  |  | 3.3708 | -3.3708 |  |  |  | 3.3708 | -3.3708 |  |  |  | 3.3708 | -3.3708 |  |  |  | 3.3708 | -3.3708 |  |  |  | 3.3708 | -3.3708 |  | 0 | 0 |  | 0 | 0
356 | 34/PR/BSPTCL/2015 Package B | P1 | 12th Plan Old Projects | Page No. 274, Sl. No. 103 of MYT Order | Work of construction of Trans. Lines for Connecting to upcoming new 132 kv line bay 01 no. each at Musrakh, Benipatti & Jandaha GSS | DCB |  |  |  |  | 0 | 0 | State Plan | 6.22 | 7.1009 | -0.00132 |  |  |  | 7.1009 | -0.00132 | 0.01 |  |  | 7.1009 | 0.00868 |  |  |  | 7.1009 | 0.00868 |  |  |  | 7.1009 | 0.00868 |  |  |  | 7.1009 | 0.00868 |  | 0 | 0 |  | 0 | 0 |  | 0.008 | 0.002
357 | 33/PR/BSPTCL/2014 | P1 | 12th Plan Ongoing Project | Page No. 198, Sl. No. 42 of MYT Order | Construction of 2 x160+2x50 MVA ,220/132/33KV GSS Laukahi, NIT-33/2014, | [7 empty] | BRGF | 67.23 | 72.458 | -0.010413 |  |  |  | 72.458 | -0.010413 |  |  |  | 72.458 | -0.010413 |  |  |  | 72.458 | -0.010413 |  |  |  | 72.458 | -0.010413 |  |  |  | 72.458 | -0.010413 |  |  | 0 |  |  | 0
358 | 98/PR/BSPTCL/2014 | P1 | 12th Plan Old Projects | Page No. 213, Sl. No. 176 of MYT Order | Construction of 132 kv 2 no Bays each at 132kv GSS DARBGANGA & Gangwra NIT No.- 98/2014 | DCB |  | 21.03.2015 | 21.03.2015 | 21.12.15 | 6.04 Cr | 1370.02 | BRGF | 6.06 | 0.52759 | 0.19642 |  |  |  | 0.52759 | 0.19642 |  |  |  | 0.52759 | 0.19642 |  |  |  | 0.52759 | 0.19642 |  |  |  | 0.52759 | 0.19642 |  |  |  | 0.52759 | 0.19642 |  |  | 0 |  |  | 0
359 | 46/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 183, Sl. No. 216 of MYT Order | for Capacity augmentation of GSS Hajipur,Gopalganj & Darbhanga by replacement of power Transformer. NIT 46/PR/BSPTCL/2018 | DCB | 4 | 2019-01-21 | 2019-01-21 | 20.01.2020 | 69.57 | 67.08 | State Plan | 69.57 | 29.6779 | -0.44081 |  |  |  | 29.6779 | -0.44081 |  |  |  | 29.6779 | -0.44081 |  |  |  | 29.6779 | -0.44081 |  |  |  | 29.6779 | -0.44081 |  |  |  | 29.6779 | -0.44081 |  | 0 | 0 |  | 0 | 0
360 | 39/PR/BSPTCL/2017 | - | 12th Plan Old Projects | Page No. 223, Sl. No. 308 of MYT Order | Const of 220/132/33Kv GSS Darbhanga, 39/PR/BSPTCL/2017 | DCB | [6 empty] | State Plan | 0 | 0.044036 | 1.266 |  |  |  | 0.044036 | 1.266 |  |  |  | 0.044036 | 1.266 |  |  |  | 0.044036 | 1.266 |  |  |  | 0.044036 | 1.266 |  |  |  | 0.044036 | 1.266 |  | 0 | 0 |  | 0 | 0
361 | 04/PR/BSPTCL/2016 | P1 | 12th Plan Ongoing Project | Page No. 249, Sl. No. 33 of MYT Order | Construction of 8 Nos. 132KV line bays at Pandaul-01Nos., Madhubani-02Nos, Jainagar-02, Phulparas-01Nos, Ekma-01Nos and Kusheshwarsthan-01Nos under state plan against NIT No. 04/PR/BSPTCL/2016 | DCB | 3 | 2016-03-02 | 2016-03-02 | 2016-09-01 | 11.41 | 12.58 | State Plan | 11.93 | 12.869 | 0 |  |  |  | 12.869 | 0 |  |  |  | 12.869 | 0 |  |  |  | 12.869 | 0 |  |  |  | 12.869 | 0 |  |  |  | 12.869 | 0 |  | 0 | 0 |  | 0 | 0
362 | 91/PR/BSPTCL/2014 | P1 | 12th Plan Ongoing Project | Page No. 158, Sl. No. 7 of MYT Order | Construction of 2 x20MVA , 132/33KV GSS Tarapur, Teghra and Simri Bakhtiyarpur against NIT 91/2014. | DCB | 2 | 2015-03-21 | 2015-03-21 | 2016-03-20 | 80.6 | 67.03 | State Plan | 63.2 | 69.6014 | 0 |  |  |  | 69.6014 | 0 |  |  |  | 69.6014 | 0 |  |  |  | 69.6014 | 0 |  |  |  | 69.6014 | 0 |  |  |  | 69.6014 | 0 |  | 0 | 0 |  | 0 | 0
363 | 90/PR/BSPTCL/2014 | P2 | 12th Plan Ongoing Project | Page No. 211, Sl. No. 158 of MYT Order | 132/33Kv GSS Bhabhua | [7 empty] | State Plan | 0 | 0.025267 | 0 |  |  |  | 0.025267 | 0 | 0.07 |  |  | 0.025267 | 0.07 |  |  |  | 0.025267 | 0.07 |  |  |  | 0.025267 | 0.07 |  |  |  | 0.025267 | 0.07 |  | 0 | 0 |  | 0 | 0 |  | 0.056 | 0.014
364 | 08/PR/BSPTCL/2017 | P1 | 12th Plan Ongoing Project | Page No. 262, Sl. No. 62 of MYT Order | 3X50 MVA,132/33 KV GSS Kerpa, 08/PR/BSPTCL/2017 | DCB | 6 | 2018-02-12 | 2018-02-12 | 2019-02-11 | 31.69 | 31.69 | State Plan | 31.69 | 30.9028 | 0 |  |  |  | 30.9028 | 0 |  |  |  | 30.9028 | 0 |  |  |  | 30.9028 | 0 |  |  |  | 30.9028 | 0 |  |  |  | 30.9028 | 0 |  | 0 | 0 |  | 0 | 0
365 | 61/PR/BSPTCL/2014 | P1 | 12th Plan Old Projects | Page No. 170, Sl. No. 52 of MYT Order | Construction of 132/33KV Grid Sub-Station At Piro(Bhojpur) ( 2X20MVA) NIT No.- 61/PR/BSPTCL/2014 | DCB | [6 empty] | State Plan | 0 | 0.23634 | 0 |  |  |  | 0.23634 | 0 |  |  |  | 0.23634 | 0 |  |  |  | 0.23634 | 0 |  |  |  | 0.23634 | 0 |  |  |  | 0.23634 | 0 |  | 0 | 0 |  | 0 | 0
366 | 95/PR/BSPTCL/2018 | P2 | 13th Plan Other Project | Page No. 189, Sl. No. 245 of MYT Order | Capacity augmentation by addition of 3rd 160 MVA,220/132/ KV ICT along with associated transformer bays at Sonenagar (New) GSS NIT 95/PR/BSPTCL/2018 | DCB | 3 | 2019-01-15 | 2019-01-15 | 14.10.2019 | 12.04 | 13.21 | State Plan | 11.34 | 12.4034 | -0.60987 |  |  |  | 12.4034 | -0.60987 |  |  |  | 12.4034 | -0.60987 |  |  |  | 12.4034 | -0.60987 |  |  |  | 12.4034 | -0.60987 |  |  |  | 12.4034 | -0.60987 |  | 0 | 0 |  | 0 | 0
367 | 84/PR/BSPTCL/2015 | P2 | 12th Plan Ongoing Project | Page No. 201, Sl. No. 57 of MYT Order | Construction of 3x50MVA, 132/33KV GSS Ramgarh (Kaimur dist.) and Warislaiganj (Nawada Dist.) on turnkey basis against NIT No.- 84/PR/BSPTCl/15 | DCB | 4 | 2016-02-04 | 2016-02-04 | 2017-02-03 | 64.96 | 64.97 | State Plan | 65.37 | 68.5545 | 0 |  |  |  | 68.5545 | 0 |  |  |  | 68.5545 | 0 |  |  |  | 68.5545 | 0 |  |  |  | 68.5545 | 0 |  |  |  | 68.5545 | 0 |  | 0 | 0 |  | 0 | 0
368 | 68/PR/BSPTCL/2014 | P2 | 12th Plan Ongoing Project | Page No. 259, Sl. No. 55 of MYT Order | Construction of 11 Nos. of line bays at Sherghati - 01,Imamganj - 01, Sonenagar-02, Aurangaba-02, Ara-02, Jagdishpur-03 & 1 No. of T/F bay at Sherghati agaisnt NIT No.-68/PR/BSPTCL/14 | DCB | 2 | 2015-03-09 | 2015-03-09 | 2015-12-08 | 20.83 | 11.42 | BRGF | 24.34 | 22.5629 | 1.6 |  |  |  | 22.5629 | 1.6 |  |  |  | 22.5629 | 1.6 |  |  |  | 22.5629 | 1.6 |  |  |  | 22.5629 | 1.6 |  |  |  | 22.5629 | 1.6 |  |  | 0 |  |  | 0
369 | 120/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 191, Sl. No. 258 of MYT Order | for construction of 05 No’s of 132/33 KV transformer bays in Gaya transmission circle on turnkey basis NIT 120/PR/BSPTCL/2018 | DCB | 7 | 2019-02-25 | 2019-02-25 | 24.11.2019 | 10.53 | 13.32 | State Plan | 10.18 | 10.2665 | -0.096925 | 0.8171 | 0.8171 | 0.013245 | 11.0968 | -0.11017 |  |  |  | 11.0968 | -0.11017 |  |  |  | 11.0968 | -0.11017 |  |  |  | 11.0968 | -0.11017 |  |  |  | 11.0968 | -0.11017 |  | 0 | 0 |  | 0 | 0
370 | 62/PR/BSPTCL/2013 | P2 | 12th Plan Ongoing Project | Page No. 197, Sl. No. 36 of MYT Order | Construction of (2X160 MVA+2X50 MVA),220/132/33 KV GSS at Bihta(Patna) & associated 220,132 & 33 kv bays extension at remote end on turnkey basis, NIT-62/2013 | DCB | 4 | 2013-08-26 | 2013-08-26 | 2014-08-25 | 59.15 | 59.15 | State Plan | 63.91 | 67.2884 | -0.0020049 |  |  |  | 67.2884 | -0.0020049 |  |  |  | 67.2884 | -0.0020049 |  |  |  | 67.2884 | -0.0020049 |  |  |  | 67.2884 | -0.0020049 |  |  |  | 67.2884 | -0.0020049 |  | 0 | 0 |  | 0 | 0
371 | 01/PR/BSPTCL/2016 | P2 | 12th Plan Ongoing Project | Page No. 200, Sl. No. 53 of MYT Order | Construction of 08 nos. 132 KV Line bays each at -Belaganj 01no. , Hulasganj-01 no., Jehanabad -01 no., Tekari-02 no., Ataula-01 no. ,Chandauti-01 no., Nawada-01 no. under Trans. Circle, Gaya for 2nd ckt. stringing of existing 132 KV DCSS, NIT- 01/2016 | DCB | 4 | 2016-03-02 | 2016-03-02 | 2016-12-01 | 20.34 | 20.34 | State Plan | 20.34 | 4.1661 | -0.090137 |  |  |  | 4.1661 | -0.090137 |  |  |  | 4.1661 | -0.090137 |  |  |  | 4.1661 | -0.090137 |  |  |  | 4.1661 | -0.090137 |  |  |  | 4.1661 | -0.090137 |  | 0 | 0 |  | 0 | 0
372 | 127/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 234, Sl. No. 384 of MYT Order | For Supply of 6 Nos of 50MVA Transformer with Construction/modification of foundations in transmission Circle NIT 127/PR/BSPTCL/2018 | DCB | 6 | 2019-02-25 | 2019-02-25 | 24.02.2020 | 20.49 | 22.05 | State Plan | 19.22 | 19.2798 | 0 |  |  |  | 19.2798 | 0 |  |  |  | 19.2798 | 0 |  |  |  | 19.2798 | 0 |  |  |  | 19.2798 | 0 |  |  |  | 19.2798 | 0 |  | 0 | 0 |  | 0 | 0
373 | 125/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 234, Sl. No. 382 of MYT Order | For Supply of 6 Nos 50MVA Power Transformer with Construction/Modification of Foundation in Transmission Circle, Muzaffarpur NIT 125/PR/BSPTCL/2018 | DCB | 5 | 2019-02-25 | 2019-02-25 | 24.02.2020 | 22.01 | 22.05 | State Plan | 20.84 | 20.9505 | 0 |  |  |  | 20.9505 | 0 |  |  |  | 20.9505 | 0 |  |  |  | 20.9505 | 0 |  |  |  | 20.9505 | 0 |  |  |  | 20.9505 | 0 |  | 0 | 0 |  | 0 | 0
374 | 54/PR/BSPTCL/2015 | P1 | 12th Plan Old Projects | Page No. 281, Sl. No. 123 of MYT Order | Construction of 02 nos. 220 KV line bays at 220 KV Darbhanga GSS, NIT-54/2015 | [6 empty] | 1370.02 | BRGF | 4.96 | 4.5626 | 0 |  |  |  | 4.5626 | 0 |  |  |  | 4.5626 | 0 |  |  |  | 4.5626 | 0 |  |  |  | 4.5626 | 0 |  |  |  | 4.5626 | 0 |  |  | 0 |  |  | 0
375 | 36/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 323, Sl. No. 319 of MYT Order | Augmentation of Existing gSS Ekma ( 1x20MVA+1x50MVA) by 3x50MVA capacity against NIT-36/PR/BSPTCL/2018 | DCB | 6 | 2019-01-16 | 2019-01-16 | 15.04.2020 | 26.31 | 38.19 | State Plan | 26.31 | 20.443 | -0.23881 |  | 0.028289 | 0.00020506 | 20.4715 | -0.26731 |  |  |  | 20.4715 | -0.26731 | 5.8385 | 5.5712 |  | 26.0427 | 0 |  |  |  | 26.0427 | 0 |  |  |  | 26.0427 | 0 |  | 4.6708 | 1.1677 |  | 0 | 0
376 | 24/PR/BSPTCL/2014 | P1 | 12th Plan Ongoing Project | Page No. 198, Sl. No. 41 of MYT Order | Construction of 2x160 MVA + 2X50 MVA,220/132/33 KV Sub Station at Motipur | DCB |  | 2015-02-16 | 2015-02-16 | 2015-11-17 | 69.54 | 75.42 | BRGF | 77.59 | 80.5489 | 0 |  |  |  | 80.5489 | 0 |  |  |  | 80.5489 | 0 |  |  |  | 80.5489 | 0 |  |  |  | 80.5489 | 0 |  |  |  | 80.5489 | 0 |  |  | 0 |  |  | 0
377 | 85/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 230, Sl. No. 358 of MYT Order | Construction of 02 nos. 132KV Line bays each at 132/33KV Grid- Substation Mahnar & Shahpurpatori and Construction of 02nos. 220KV Line bays at 220/132/33KV GSS Samastipur(New) on Turnkey basis under State Plan against NIT No. 85/PR/BSPTCL/2018. | DCB | 3 | 14.01.2019 | 14.01.2019 | 13.10.2019 | 13.92 | 14.83 | State Plan | 13.07 | 12.3753 | -0.62394 | 0.74438 | 0.74438 | 0.003313 | 13.123 | -0.62725 |  |  |  | 13.123 | -0.62725 |  |  |  | 13.123 | -0.62725 |  |  |  | 13.123 | -0.62725 |  |  |  | 13.123 | -0.62725 |  | 0 | 0 |  | 0 | 0
378 | 07/PR/BSPTCL/2015 | P1 | 12th Plan Ongoing Project | Page No. 197, Sl. No. 34 of MYT Order | Construction Of 2 Nos.132 KV Line Bays each at 132/33 KV GSS,SKMCH & SITAMARHI(Total 4 Nos of 132 KV Line Bays) | [7 empty] | BRGF | 0 | 0.019148 | 0 |  |  |  | 0.019148 | 0 |  |  |  | 0.019148 | 0 |  |  |  | 0.019148 | 0 |  |  |  | 0.019148 | 0 |  |  |  | 0.019148 | 0 |  |  | 0 |  |  | 0
379 | 06/PR/BSPTCL/2016 | P1 | 12th Plan Old Projects | Page No. 165, Sl. No. 3 of MYT Order | work of R&M of 04 nos of 132/33 KV Grid Substations Muzaffarpur, Darbhanga, Bettiah and Motihari on turnkey basis on Firm price against NIT No :- 06/PR/BSPTCL/2016 under state plan. | DCB | [6 empty] | State Plan | 32.86 | 34.8995 | 0 |  |  |  | 34.8995 | 0 |  |  |  | 34.8995 | 0 |  |  |  | 34.8995 | 0 |  |  |  | 34.8995 | 0 |  |  |  | 34.8995 | 0 |  | 0 | 0 |  | 0 | 0
380 | 63/PR/BSPTCL/2014-Pkg-A | P1 | 12th Plan Ongoing Project | Page No. 198, Sl. No. 43 of MYT Order | Construction of 132/33kV GSS at Manjhaul , Ballia and Bakhari against NIT- 63/PR/BSPTCL/2014, Package- (A) | DCB | 3 | 2015-02-11 | 2015-02-11 | 2016-02-11 | 54.4 | 64.24 | State Plan | 59.96 | 62.3306 | 0 |  |  |  | 62.3306 | 0 |  |  |  | 62.3306 | 0 |  |  |  | 62.3306 | 0 |  |  |  | 62.3306 | 0 |  |  |  | 62.3306 | 0 |  | 0 | 0 |  | 0 | 0
381 | 05/PR/BSPTCL/2014 Pkg A | P1 | 12th Plan Old Projects | Page No. 166, Sl. No. 13 of MYT Order | construction of 2 Nos. 132 KV Line Bay at 132/33 KV Udakishanj GSS, Construction of 4 Nos. of 132 KV Line bay at 132/33 KV Kusheshwarsthan GSS, Construction of 4 Nos. of 132 KV Line bay at 132/33 KV Sonebersa GSS, Construction of 1 No 132/33 KV Transformer Bay at 132/33 KV Kataiya GSS, NIT-05/2014, Pkg A | DCB |  |  |  |  | 0 | 371.98 | BRGF | 20.5 | 21.6087 | 0.15063 |  |  |  | 21.6087 | 0.15063 |  |  |  | 21.6087 | 0.15063 |  |  |  | 21.6087 | 0.15063 |  |  |  | 21.6087 | 0.15063 |  |  |  | 21.6087 | 0.15063 |  |  | 0 |  |  | 0
382 | 05/PR/BSPTCL/2016 | P1 | 12th Plan Ongoing Project | Page No. 206, Sl. No. 107 of MYT Order | Construction of Associated 132KV Line bays for Second Circuit Stringing of Existing double circuit Single strung at Begusarai, NIT- 5/2016 | DCB | 2 | 02.03.2016 | 02.03.2016 | 01.09.2016 | 7.25 |  | State Plan | 7.39 | 8.1355 | 0 |  |  |  | 8.1355 | 0 |  |  |  | 8.1355 | 0 |  |  |  | 8.1355 | 0 |  |  |  | 8.1355 | 0 |  |  |  | 8.1355 | 0 |  | 0 | 0 |  | 0 | 0
383 | 37/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 224, Sl. No. 320 of MYT Order | Construction of 132/33KV (2X50 MVA) GSS at Palasi (Dist. Araria) on turnkey basis. NIT No.- 37/PR/BSPTCL/18 | DCB |  | 2019-01-21 | 2019-01-21 |  | 39.8 | 39.8 | State Plan | 35.99 | 25.2477 | 6.2322 | 0.24464 | 7.253 | 0.092797 | 32.5935 | -0.86894 |  |  |  | 32.5935 | -0.86894 |  |  |  | 32.5935 | -0.86894 |  |  |  | 32.5935 | -0.86894 |  |  |  | 32.5935 | -0.86894 |  | 0 | 0 |  | 0 | 0
384 | 86/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 230, Sl. No. 359 of MYT Order | Construction of 220/132 KV (2x100) MVA GSS at Korha with SAS and additional / augmentation of 160 MVA, 220/132 KV Transformer at 220/132/33 KV GSS Kishanganj (new) on turnkey basis NIT 86/PR/BSPTCL/2018 | DCB |  | 2019-01-21 | 2019-01-21 |  | 71.93 | 63.09 | State Plan | 71.3 | 12.5398 | -0.25343 | 0.043399 | 0.043399 | 0.00020803 | 12.5834 | -0.25364 | 0.08 |  |  | 12.5834 | -0.17364 |  |  |  | 12.5834 | -0.17364 |  |  |  | 12.5834 | -0.17364 |  |  |  | 12.5834 | -0.17364 |  | 0 | 0 |  | 0 | 0 |  | 0.064 | 0.016
385 | 85/PR/BSPTCL/2015 | P1 | 13th Plan Other Project | Page No. 242, Sl. No. 9 of MYT Order | Construction of 132/33KV GSS Siwan-New, NIT-85/2015 | DCB | 2 | 2016-02-03 | 2016-02-03 | 2017-02-03 | 23.51 | 23.51 | State Plan | 26.35 | 26.1804 | 0 | 0.16786 | 0.16786 |  | 26.3483 | 0 |  |  |  | 26.3483 | 0 |  |  |  | 26.3483 | 0 |  |  |  | 26.3483 | 0 |  |  |  | 26.3483 | 0 |  | 0 | 0 |  | 0 | 0
386 | 06/PR/BSPTCL/2017 | P1 | 12th Plan Old Projects | Page No. 231, Sl. No. 365 of MYT Order | Capacitor bank 36KV for improvement of voltage | [7 empty] | PSDF Cap. | 0 | 20.7738 | -0.0037898 |  |  |  | 20.7738 | -0.0037898 |  |  |  | 20.7738 | -0.0037898 |  |  |  | 20.7738 | -0.0037898 |  |  |  | 20.7738 | -0.0037898 |  |  |  | 20.7738 | -0.0037898
387 | 34/PR/BSPTCL/2015 Package A | P1 | 12th Plan Old Projects | Page No. 206, Sl. No. 102 of MYT Order | Construction of 132Kv Line Bay at GSS Dhaka and Motipur. NIT-34/2015, Pkg A | DCB |  |  |  |  | 0 | 0 | State Plan | 8.16 | 8.2082 | 0.00132 |  |  |  | 8.2082 | 0.00132 | 0.19 |  |  | 8.2082 | 0.19132 |  |  |  | 8.2082 | 0.19132 |  |  |  | 8.2082 | 0.19132 |  |  |  | 8.2082 | 0.19132 |  | 0 | 0 |  | 0 | 0 |  | 0.152 | 0.038
388 | 113/PR/BSPTCL/2018 | P2 | 13th Plan Other Project | Page No. 224, Sl. No. 324 of MYT Order | Re-Conductring of (i) 132KV S/C Kahalgaon(BSPTCL)- Kahalgaon (NTPC) Trans. Line (CKM-7KM) (ii) 132 KV S/C Kahalgaon- Sabour Trans. Line(CKM-27KM transmission line with HTLS(equivalent to panther) Conductor(Approx CKM=27KM). NIT 113/PR/BSPTCL/2018 | DCB | 3 | 05.02.2019 | 05.02.2019 | 04.02.2020 | 20.85 | 19.43 | State Plan | 16.74 | 21.9098 | -2.8715 |  |  |  | 21.9098 | -2.8715 |  |  |  | 21.9098 | -2.8715 |  |  |  | 21.9098 | -2.8715 |  |  |  | 21.9098 | -2.8715 |  |  |  | 21.9098 | -2.8715 |  | 0 | 0 |  | 0 | 0
389 | 32/PR/BSPTCL/2016 Gr. No.-01 | Civil | 12th Plan Old Projects | Page No. 180, Sl. No. 176 of MYT Order | Double storied control room building at 132/33 KV GSS Siwan | DCB |  | As per Reconciliati on |  |  |  |  | State Plan | 0 | 2.364 | -0.084046 |  |  |  | 2.364 | -0.084046 |  |  |  | 2.364 | -0.084046 |  |  |  | 2.364 | -0.084046 |  |  |  | 2.364 | -0.084046 |  |  |  | 2.364 | -0.084046 |  | 0 | 0 |  | 0 | 0
390 | 468/PR/BSPTCL/2013 | Civil | 12th Plan Old Projects | Page No. 205, Sl. No. 97 of MYT Order | Earth Filling & Construction of boundary wall of proposed land for 220/132/33 KV GSS Mushahari ,Muzaffarpur(Under BRGF Ph-III Part-I), NIT-468/2013 | DCB | [6 empty] | BRGF | 0 | 6.3714 | -0.14141 |  |  |  | 6.3714 | -0.14141 |  |  |  | 6.3714 | -0.14141 |  |  |  | 6.3714 | -0.14141 |  |  |  | 6.3714 | -0.14141 |  |  |  | 6.3714 | -0.14141 |  |  | 0 |  |  | 0
391 | 13/PR/BSPTCL/2020 | Civil | 13th Plan Other Project | Page No. 180, Sl. No. 176 of MYT Order | Construction and renovation of Store shed, PCC Road, Sump Room, Landscaping, Open Platform, Drainage System, Height raising of Boundary Wall etc. at GSS Jakkanpur | [7 empty] | IRF | 0 | 1.2452 | 0.80572 |  |  |  | 1.2452 | 0.80572 |  |  |  | 1.2452 | 0.80572 |  |  |  | 1.2452 | 0.80572 |  |  |  | 1.2452 | 0.80572 |  |  |  | 1.2452 | 0.80572 |  |  | 0 |  |  | 0
392 | 01/PR/BSPTCL/2021 | P1 | 13th Plan Other Project | Page No. 106, Sl. No. 4 of MYT Order | Construction of 04 Nos of 132Kv Line Bay with SAS and construction of S/Y Control Panel Room at 400/220/132 Kv GSS Saharsha(New) |  |  | 05.07.2021 |  | 04.07.22 | 0 | 0 | State Plan | 0 | 0 | 6.4127 | 0.29096 |  |  | 0 | 7.3436 | 1.35 | 8.6899 |  | 8.6899 | 0.0037494 |  |  |  | 8.6899 | 0.0037494 |  |  |  | 8.6899 | 0.0037494 |  |  |  | 8.6899 | 0.0037494 |  | 0 | 0 |  | 0 | 0 |  | 1.08 | 0.27
393 | 02/PR/BSPTCL/2020 | P2 | 13th Plan Other Project | Page No. 160, Sl. No. 24 of MYT Order | construction of D/C transmission line for river crossing (Ganga) with 03 no’s pile foundation & 220 KV transmission tower for connectivity of 33 KV line for Raghopur PSS near Kachchi Dargah on turnkey basis under Deposit scheme | DCB | 2 | 05.05.2020 | 05.05.2020 | 05.11.2020 | 19.29 | 0 | Deposit Work | 18.76 | 18.7579 | 0.000446 | 0.0053801 |  |  | 18.7579 | 0.0058261 |  | 0 |  | 18.7579 | 0.0058261 |  |  |  | 18.7579 | 0.0058261 |  |  |  | 18.7579 | 0.0058261 |  |  |  | 18.7579 | 0.0058261 | 0
394 | 03/PR/BSPTCL/2021 | P2 | 13th Plan Other Project | Page No. 107, Sl. No. 12 of MYT Order | construction of 02 no’s 220 KV AIS line bays at GSS Fatuha BSPTCL & 02 no’s 132 KV AIS line bays at GSS Harnaut BSPTCL on turnkey basis |  |  | 05.07.2021 | 05.07.2021 | 04.07.2021 | 8.35 | 0 | State Plan | 8.35 | 0 | 5.9428 | 0.9508 |  |  | 0 | 6.8936 | 0.31 | 0 |  | 0 | 7.2036 |  |  |  | 0 | 7.2036 |  |  |  | 0 | 7.2036 |  |  |  | 0 | 7.2036 |  | 0 | 0 |  | 0 | 0 |  | 0.248 | 0.062
395 | 04/PR/BSPTCL/2020 | P1 | 13th Plan Other Project | Page No. 176, Sl. No. 120 of MYT Order | construction of 132 KV D/C transmission line with 05 no’s of pile foundation for river crossing (Koshi)(Route length-03RKM) require for 33 KV feeder from 132/33 KV Simri Bakhtiyarpur GSS to U/C Alani PSS(Block-Salkhua) at Saharsa district on turnkey basis under Deposit Scheme |  | 3 | 08.05.2020 | 08.05.2020 | 07.11.2020 | 10.51 | 0 | Deposit Work | 18.82 | 0 | 7.1499 | 7.6756 | 18.7539 |  | 18.7539 | -3.9284 | 0 | 0.0071683 |  | 18.7611 | -3.9356 |  |  |  | 18.7611 | -3.9356 |  |  |  | 18.7611 | -3.9356 |  |  |  | 18.7611 | -3.9356 | 0
396 | 04/PR/BSPTCL/2021 | P1 | 13th Plan Other Project | Page No. 237, Sl. No. 403 of MYT Order | Construction of 01 no of 132 KV line bay at 132/33 GSS Kataiya & stringing of 2nd circuit on DCSS of 132 KV Kataiya-Kusaha transmission line on turnkey basis. |  |  | 08.07.2021 |  | 07.04.2022 | 2.71 | 0 | Deposit Work | 0 | 0 | 1.9362 | 0.30864 | 2.2448 |  | 2.2448 | 0 | 0.14 | 0.1418 |  | 2.3866 | -0.0018034 |  |  |  | 2.3866 | -0.0018034 |  |  |  | 2.3866 | -0.0018034 |  |  |  | 2.3866 | -0.0018034 | 0.14 | [8 empty] | 0.14
397 | 08/PR/BSPTCL/2020 | Civil | 13th Plan Other Project | Page No. 160, Sl. No. 24 of MYT Order | Reconstruction of Boundary Wall at 132/33 KV GSS Supaul | [7 empty] | IRF | 0 | 0 | 0.79472 |  |  |  | 0 | 0.79472 |  |  |  | 0 | 0.79472 |  |  |  | 0 | 0.79472 |  |  |  | 0 | 0.79472 |  |  |  | 0 | 0.79472 |  |  | 0 |  |  | 0
398 | 09/PR/BSPTCL/2020 | Civil | 13th Plan Other Project | Page No. 283, Sl. No. 129 of MYT Order | Construction of Retaining wall and Boundary Wall at 132/33KV GSS Campus Jaynagar | [7 empty] | IRF | 0 | 0.47857 | 0 |  |  |  | 0.47857 | 0 |  |  |  | 0.47857 | 0 |  |  |  | 0.47857 | 0 |  |  |  | 0.47857 | 0 |  |  |  | 0.47857 | 0 |  |  | 0 |  |  | 0
399 | 10/PR/BSPTCL/2016 | P1 | 12th Plan Ongoing Project | Page No. 164, Sl. No. 50 of MYT Order | Construction of 132/33 KV GSS at Korha & Nathnagar. | DCB | 3 | 42432 | 42432 | 42797 | 26.49 | 57.04 | State Plan | 55.63 | 0 | 27.2813 | 0.95316 |  |  | 0 | 28.2345 |  |  |  | 0 | 28.2345 |  |  |  | 0 | 28.2345 |  |  |  | 0 | 28.2345 |  |  |  | 0 | 28.2345 |  | 0 | 0 |  | 0 | 0
400 | 11/PR/BSPTCL/2021 | P2 | 13th Plan Other Project | Page No. 238, Sl. No. 413 of MYT Order | Construction of 132/33 KV 2X50 MVA GSS Barachatti(Dist.-Gaya) along with construction of 02 Nos. of 132 KV Line bays at GSS Chandauti & 132/33 KV 2X50 MVA Bhore(Dist-Gaya). |  |  | 17.08.2021 | 17.08.2021 | 16.11.2022 | 91.25 | 0 | State Plan | 91.25 | 0 | 15.0165 | 35.7823 |  |  | 0 | 50.7988 | 20.92 | 71.7281 |  | 71.7281 | -0.0092882 | 19.52 | 19.52 |  | 91.2481 | -0.0092882 |  |  |  | 91.2481 | -0.0092882 |  |  |  | 91.2481 | -0.0092882 |  | 15.616 | 3.904 |  | 0 | 0 |  | 16.736 | 4.184
401 | 111/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 325, Sl. No. 326 of MYT Order | Construction 132 KV transmission line from Laukahi to Phulparas with HTLS Conductor NIT 111/PR/BSPTCL/2018 | DCB | 4 | 07.02.2019 | 07.02.2019 | 06.02.2020 | 42.79 | 42.69 | State Plan | 35.48 | 0 | 34.3751 |  | 34.3825 | 9.8505 | 44.233 | -9.8579 | 0.35 | 0.35982 |  | 44.5928 | -9.8677 |  |  |  | 44.5928 | -9.8677 |  |  |  | 44.5928 | -9.8677 |  |  |  | 44.5928 | -9.8677 |  | 0 | 0 |  | 0 | 0 |  | 0.28 | 0.07
402 | 114/PR/BSPTCL/2018 | P1 | 13th Plan Other Project | Page No. 345, Sl. No. 364 of MYT Order | Reconductoring of (i) 132Kv Muzaffarpur - SKMCH S/C Transmission Line with HTLS conductor (line length 20.5RKM) along with invovment 01 no. of Pile foundation . (ii) 132Kv Kanti- SKMCH D/C transmission line with HTLS conductor (line length 14.28 RKM) -NIT 114/PR/BSPTCL/2018 | DCB | 4 | 05.01.2019 | 04.10.2019 | 04.10.2019 | 21.13 | 31.04 | State Plan | 33.45 | 0 | 21.0665 | 0.25321 | 27.4432 | 1.2046 | 28.6479 | -7.3282 |  |  |  | 28.6479 | -7.3282 |  |  |  | 28.6479 | -7.3282 |  |  |  | 28.6479 | -7.3282 |  |  |  | 28.6479 | -7.3282 |  | 0 | 0 |  | 0 | 0
403 | 12/PR/BSPTCL/2020 | P2 | 13th Plan Other Project | Page No. 171, Sl. No. 67 of MYT Order | for construction of 132 KV D/C transmission line(01RKM) with ACSR panther conductor for crossing of falgu river with 03 no’s of pile foundation for connectivity of 33 KV line for PSS Bhusunda (Distt-Gaya) on turnkey basis under Deposit Scheme of SBPDCL |  |  | 11.12.2020 | 11.12.2020 | 10.06.2021 | 6.2 | 0 | Deposit Work | 4.55 | 4.5515 | -1.1688 |  |  |  | 4.5515 | -1.1688 |  |  |  | 4.5515 | -1.1688 |  |  |  | 4.5515 | -1.1688 |  |  |  | 4.5515 | -1.1688 |  |  |  | 4.5515 | -1.1688 | 0
404 | 16/PR/BSPTCL/2021 | P1 | 13th Plan Other Project | Page No. 106, Sl. No. 3 of MYT Order | Re-conductoring of 132 kv Transmission Line from 400/132 Kv GIS Motihari (DMTCL) to 132/33 Kv GSS Motihari with HTLS (equivalent to panther) except GAP conductor |  |  | 13.08.2021 |  |  | 42.63 | 0 | State Plan | 40.04 | 0 | 40.0492 | 0.1329 | 40.1821 | 0.18125 | 40.3633 | -0.18125 |  |  |  | 40.3633 | -0.18125 |  |  |  | 40.3633 | -0.18125 |  |  |  | 40.3633 | -0.18125 |  |  |  | 40.3633 | -0.18125 |  | 0 | 0 |  | 0 | 0
405 | 17/PR/BSPTCL/2021 | P1 | 13th Plan Other Project | Page No. 105, Sl. No. 2 of MYT Order | re-conductoring of 132Kv Transmission Line from GSS Kishanganj (New) to GSS Kishanganj (Old) with HTLS (equivalent to Panther) except GAP Conductor (Approx route Length-9.7 RKM) |  |  | 06.08.2021 |  | 05.02.2022 | 12.8694 | 0 | State Plan | 0 | 0 | 11.3675 | 0.44624 | 11.8137 | 0.081666 | 11.8954 | -0.081666 |  |  |  | 11.8954 | -0.081666 |  |  |  | 11.8954 | -0.081666 |  |  |  | 11.8954 | -0.081666 |  |  |  | 11.8954 | -0.081666 |  | 0 | 0 |  | 0 | 0
406 | 19/PR/BSPTCL/2021 | P2 | 13th Plan Other Project | Page No. 107, Sl. No. 16 of MYT Order | construction of 04 no’s 220 KV line bays, Its erection, testing & commissioning at GSS Bodhgaya with associated works mentioned in scope of works |  |  | 22.09.2021 | 22.09.2021 | 21.06.2022 | 6.82 | 0 | State Plan | 6.82 | 0 | 5.5487 | 0.84107 | 6.3898 | 0.47784 | 6.8676 | -0.47784 | 0.19 | 0.18702 |  | 7.0546 | -0.47486 |  |  |  | 7.0546 | -0.47486 |  |  |  | 7.0546 | -0.47486 |  |  |  | 7.0546 | -0.47486 |  | 0 | 0 |  | 0 | 0 |  | 0.152 | 0.038
407 | 23/PR/BSPTCL/2021 | P2 | 13th Plan Other Project | Page No. 109, Sl. No. 23 of MYT Order | For 1) Construction of DCDS 400KV from Buxar Thermal Power Plant to Naubatpur (BGCL) with twin Moose conductor.(RL-123KM) 2) Construction of DCDS 220KV from Buxar Thermal Power Plant to GSS Karamnasa with twin Moose conductor.(RL-90KM) 3) Construction of DCDS 220KV from Buxar Thermal Power Plant to GSS Dehri- on -Sone with single Zebra conductor.(RL- 120KM) on turnkey basis |  |  | 08.12.2021 | 08.12.2021 | 08.06.2023 | 529.55 | 0 | State Plan | 416.52 | 0 | 373.8455 | 29.0435 |  |  | 0 | 402.889 | 0.08 | 398.0729 | 1.7503 | 399.8232 | 3.1458 |  |  |  | 399.8232 | 3.1458 |  |  |  | 399.8232 | 3.1458 |  |  |  | 399.8232 | 3.1458 |  | 0 | 0 |  | 0 | 0 |  | 0.064 | 0.016
408 | 24/PR/BSPTCL/2020 | P1 | 13th Plan Other Project | Page No. 237, Sl. No. 405 of MYT Order | Construction of 02 no’s of 220 KV line bay, demolish of old quarters and construction of new quarters along with extension of control room and associated civil works at 220/132/33 KV GSS Begusarai. |  |  | 23.03.2021 |  | 22.03.2022 | 12.92 | 0 | Deposit Work | 15.39 | 0 | 7.7714 | 1.7193 |  |  | 0 | 9.4907 | 0.07 | 0 |  | 0 | 9.5607 |  |  |  | 0 | 9.5607 |  |  |  | 0 | 9.5607 |  |  |  | 0 | 9.5607 | 0.07 | [8 empty] | 0.07
409 | 24/PR/BSPTCL/2021 | P2 | 13th Plan Other Project | Page No. 110, Sl. No. 24 of MYT Order | for Construction of DCDS 220 KV T/L from Buxar thermal power plant to GSS Dumraon (New),BGCL with twin moose conductor(RL-72 Km) on Turnkey. |  |  | 23.11.2021 | 23.11.2021 | 23.02.2023 | 124.68 | 0 | State Plan | 124.68 | 0 | 83.4367 | 11.8539 |  |  | 0 | 95.2906 | 0.45 | 96.1597 |  | 96.1597 | -0.41914 |  |  |  | 96.1597 | -0.41914 |  |  |  | 96.1597 | -0.41914 |  |  |  | 96.1597 | -0.41914 |  | 0 | 0 |  | 0 | 0 |  | 0.36 | 0.09
410 | 25/PR/BSPTCL/2021 | P2 | 13th Plan Other Project | Page No. 110, Sl. No. 25 of MYT Order | Construction of 02 no’s 220 KV AIS line bays at Dehri on Sone BSPTCL with associated work mentioned in the scope of works on turnkey basis under |  |  | 02.11.2021 | 02.11.2021 | 01.11.2022 | 8.11 | 0 | State Plan | 8.11 | 0 | 5.0384 | 1.2742 |  |  | 0 | 6.3127 | 0.31 | 8.081 |  | 8.081 | -1.4583 |  | 8.11 |  | 16.191 | -9.5683 |  |  |  | 16.191 | -9.5683 |  |  |  | 16.191 | -9.5683 |  | 0 | 0 |  | 0 | 0 |  | 0.248 | 0.062
411 | 27/PR/BSPTCL/2019 | O&M |  | - | For Design, Manufacture, assdemble, testing, Supply, erection, testing and commissioning of 04 sets of 220V, 60/50 A and 29 sets of 220V, 45/30 A automatic float & float cum boost battery chargers for VRLA type 10 sets of 220 V, 45/30 A automatic float & float cum boost battery chargers for tubular type battery sets | [7 empty] | IRF | 0 | 0 | 0.0295 |  |  |  | 0 | 0.0295 |  |  |  | 0 | 0.0295 |  |  |  | 0 | 0.0295 |  |  |  | 0 | 0.0295 |  |  |  | 0 | 0.0295 |  |  | 0 |  |  | 0
412 | 28/PR/BSPTCL/2019 | O&M | 13th Plan Other Project | Page No. 176, Sl. No. 117 of MYT Order | For Height raising of tower/Conductor of 132 KV D/C Biharsharif –Hathidah transmission line between tower location no-323 to 326 and 220 KV D/C Biharsharif – Begusarai transmission line between location no-105 to 108 under Deposit | [5 empty] | 0 | 0 | Deposit Work | 0 | 1.7852 | 0.0026864 | 0.079234 |  |  | 1.7852 | 0.081921 |  |  |  | 1.7852 | 0.081921 |  |  |  | 1.7852 | 0.081921 |  |  |  | 1.7852 | 0.081921 |  |  |  | 1.7852 | 0.081921 | 0
413 | 28/PR/BSPTCL/2020 | P2 | 13th Plan Other Project | Page No. 107, Sl. No. 14 of MYT Order | Construction of BSPTCL (Re-conductoring of following transmission lines with HTLS (equivalent to Panther) conductor on turnkey basis under state plan:- 1. 132 KV D/C Barauni TPS - Begusarai Trans Line (CKM- 24KM) 2. 132 KV D/C Lakhisarai (PGCIL) – Lakhisarai Trans Line (CKM-32KM)) |  |  | 31.03.2021 | 31.03.2021 | 30.12.2021 | 33.91 | 0 | State Plan | 33.91 | 30.7612 | -0.71904 | 1.1061 | 1.1061 | 0.014921 | 31.8822 | -0.73396 |  |  |  | 31.8822 | -0.73396 |  |  |  | 31.8822 | -0.73396 |  |  |  | 31.8822 | -0.73396 |  |  |  | 31.8822 | -0.73396 |  | 0 | 0 |  | 0 | 0
414 | 31/PR/BSPTCL/2018 | P2 | 13th Plan Other Project | Page No. 175, Sl. No. 114 of MYT Order | construction of 132 KV, 2-Phase, single circuit transmission line on double circuit tower between GSS Sheikhpura (Line-length-15KM) & TSS Sheikhpura and corresponding 132 KV line bay at 132/33KV GSS Sheikhpura on turnkey basis |  |  | 09.10.2018 | 09.10.2018 | 08.07.2019 | 7.32 | 0 | Deposit Work | 8.94 | 0 | 7.8879 |  | 7.9562 |  | 7.9562 | -0.068316 | 0.5 | 0.50297 |  | 8.4592 | -0.071282 |  |  |  | 8.4592 | -0.071282 |  |  |  | 8.4592 | -0.071282 |  |  |  | 8.4592 | -0.071282 | 0.5 | [8 empty] | 0.5
415 | 32/PR/BSPTCL/2018 | O&M |  | - | Work order for supply, erection, testing & commissioning of 07 sets of 220V, 300Ah & 01 set of 220V, 200Ah Tubular Acid Type sub station battery sets against NIT No. 32/PR/BSPTCL/2018 under Trans. O&M Head on FIRM Prices. | [7 empty] | IRF | 0 | 0 | 0.0236 |  |  |  | 0 | 0.0236 |  |  |  | 0 | 0.0236 |  |  |  | 0 | 0.0236 |  |  |  | 0 | 0.0236 |  |  |  | 0 | 0.0236 |  |  | 0 |  |  | 0
416 | 37/PR/BSPTCL/2021 | P1 | 13th Plan Other Project | Page No. 106, Sl. No. 5 of MYT Order | for Restoration of 220KV BTPS -Hajipur D/C Trans line with invironment of 07 nos. pile foundation and all associated work. |  |  | 07.04.2021 |  |  | 30.13 | 0 | IRF | 33.9 | 0 | 29.719 |  |  |  | 0 | 29.719 |  |  |  | 0 | 29.719 |  |  |  | 0 | 29.719 |  |  |  | 0 | 29.719 |  |  |  | 0 | 29.719 |  |  | 0 |  |  | 0
417 | 39/PR/BSPTCL/2019 | O&M |  |  | For supply, erection, testing & commissioning of 01 sets of 220V, 200 AH, 11 sets of 220V, 300AH & 1 set of 220 V, 500 AH Tubular Acid Type sub- station battery sets including dismantling works wherever applicable under Trans. O&M Head on FIRM Prices. | [7 empty] | IRF | 0 | 0 | 1.0675 |  |  |  | 0 | 1.0675 |  |  |  | 0 | 1.0675 |  |  |  | 0 | 1.0675 |  |  |  | 0 | 1.0675 |  |  |  | 0 | 1.0675 |  |  | 0 |  |  | 0
418 | 40/PR/BSPTCL/2021 | O&M |  | - | For Design, manufacture, assembely, testing, Supply and delivery of 175 nos. of contactless type potential detector under Trans. (O&M) Plant & Machinery Head, on FIRM Prices. | [7 empty] | IRF | 0 | 0 | 0.46463 |  |  |  | 0 | 0.46463 |  |  |  | 0 | 0.46463 |  |  |  | 0 | 0.46463 |  |  |  | 0 | 0.46463 |  |  |  | 0 | 0.46463 |  |  | 0 |  |  | 0
419 | 31/PKG-K-1/BSPTCL/ADB/2016 | P2 | 12th Plan Ongoing Project | Page No. 163, Sl. No. 40 of MYT Order | Procurement & Construction for Reconductoring of 132KV Transmission lines on Turnkey Basis under ADB Funded Package K-1 | ICB | 3 | 2016-10-31 | 2016-10-31 | 2018-01-31 | 44 | 44 | ADB | 44.39 | 45.73 | 4.0501 |  |  |  | 45.73 | 4.0501 |  |  |  | 45.73 | 4.0501 |  |  |  | 45.73 | 4.0501 |  |  |  | 45.73 | 4.0501 |  |  |  | 45.73 | 4.0501
420 | 32/PKG-L-1/BSPTCL/ADB/2016 | P2 |  | - | Procurement & Construction for Reconductoring of 220KV & 132KV Transmission lines on Turnkey Basis under ADB Funded Package L-1. | [7 empty] | ADB | 0 | 0 | 0.72056 |  |  |  | 0 | 0.72056 |  |  |  | 0 | 0.72056 |  |  |  | 0 | 0.72056 |  |  |  | 0 | 0.72056 |  |  |  | 0 | 0.72056
421 | 12/PR/BSPTCL/2021 | P2 | 13th Plan Other Project | Page No. 108, Sl. No. 18 of MYT Order | I. LILO of 132 KV Barhi- Rajgir (L-29) and Barhi-Nalanda (L-28) Transmission line each at GSS Bhore (Each line length -1 KM) NIT No-12/PR/BSPTCL/2021 II. LILO of 132 KV Sonenagar - Chandauti (LL-38 RKM) NIT No-12/PR/BSPTCL/2021 III. 132 KV D/C Chandauti (New) to GSS Barachatti Transmission Line (RL-35 RKM) NIT No-12/PR/BSPTCL/2021 |  |  | 17.08.2021 | 17.08.2021 | 16.11.2022 | 34.6 | 0 | BRGF | 34.6 | 0 | 9.1059 | 5.0373 |  |  | 0 | 14.1432 | 8.33 | 22.218 | 0.36905 | 22.587 | -0.11384 |  |  |  | 22.587 | -0.11384 |  |  |  | 22.587 | -0.11384 |  |  |  | 22.587 | -0.11384 |  |  | 0 |  |  | 0 |  |  | 8.33
422 | 05/PR/BSPTCL/2021 | P1 | 13th Plan Other Project | Page No. 106, Sl. No. 10 of MYT Order | Construction of 132KV D/C Raxaul (New) to Raxaul (old) Transmission line (Line length-20 RKM), 2nd Ckt Stringing of 132 KV Raxaul(Old) -Parwanipur line (07 RKM) & construction of 2 nos. 132 KV Line Bays at 220/132/33 KV GSS Raxaul (Under Principal Funding of MEAagaisnt NIT No:-05/PR/BSPTCL/2021 |  |  | 09.07.2021 |  | 08.07.2022 | 0 | 0 | Deposit Work | 0 | 0 | 16.9057 | 2.4039 | 19.1211 |  | 19.1211 | 0.18855 | 0.7 | 0 |  | 19.1211 | 0.88855 |  |  |  | 19.1211 | 0.88855 |  |  |  | 19.1211 | 0.88855 |  |  |  | 19.1211 | 0.88855 | 0.7 | [8 empty] | 0.7
423 | 40/PR/BSPTCL/2020 | P1 | 13th Plan Other Project | Page No. 237, Sl. No. 404 of MYT Order | Construction of 220 KV double circuit transmission line from GSS Begusarai to IOCL Barauni Refinery (15 RKM) partly on monopole tower and shifting of 4 nos. of 220 KV Towers of existing transmission line required for M/s IOCL on M/C monopole Towers agaainst NIT NO:-40/PR/BSPTCL/2020 |  |  | 30.06.2021 |  | 29.06.2022 | 43.54 | 0 | Deposit Work |  | 0 | 43.0961 | 3.5517 | 43.0807 |  | 43.0807 | 3.567 | 0.41 | 0.41492 |  | 43.4957 | 3.5621 |  |  |  | 43.4957 | 3.5621 |  |  |  | 43.4957 | 3.5621 |  |  |  | 43.4957 | 3.5621 | 0.41 | [8 empty] | 0.41
424 | 38/PR/BSPTCL/2020 | P1 | 13th Plan Other Project | - | Work for restoration of 132 KV Kishanganj (New) - Barsoi Transmission line with involvement of 06 nos. pile foundation & its associated works. 38/PR/BSPTCL/2020 |  |  | 07.04.2021 |  | Revised SDOC: 30.06.2022 | 0 | 0 | IRF | 17.4 | 0 | 8.5742 | 8.022 | 16.5963 |  | 16.5963 | 0 | 0.11 | 0.074748 |  | 16.671 | 0.035251 |  |  |  | 16.671 | 0.035251 |  |  |  | 16.671 | 0.035251 |  |  |  | 16.671 | 0.035251 |  |  | 0 |  |  | 0 |  |  | 0.11
425 | 13/PR/BSPTCL/2021 | P2 | 13th Plan Other Project | Page No. 108, Sl. No. 19 of MYT Order | I. Construction of 132/33 KV 3x MVA GSS Nabinagar (Dist.: - Aurangabad) II. Construction of 132/33 KV 2x50 GSS Daudnagar (Dist.: - Aurangabad) NIT No-13/PR/BSPTCL/2021 NIT No-13/PR/BSPTCL/2021 |  |  | 17.08.2021 | 17.08.2021 | 16.11.2022 | 89.65 | 0 | BRGF | 89.65 | 0 | 28.9941 | 42.721 |  |  | 0 | 71.7151 | 3.7 | 41.715 |  | 41.715 | 33.7001 |  | 89.65 |  | 131.365 | -55.9499 |  |  |  | 131.365 | -55.9499 |  |  |  | 131.365 | -55.9499 |  |  | 0 |  |  | 0 |  |  | 3.7
426 | 72/PR/BSPTCL/2015 | P2 | 12th Plan Ongoing Project | Page No. 200, Sl. No. 56 of MYT Order | Second Circuit Stringing of Existing 03 Nos. of 132 KV Double Circuit Single Strung Transmission Line: i) GSS Belagunj to tapping point of L-32 & L-33 Trans. Line 2.5 CKM ii)132 KV Gaya-Tekari and 132 KV Tekari-Goh 51.8 CKM iii)132 KV Jehanabad-Ataula (Karpi) 22.57 CKM Under Transmission Circle Gaya on Turnkey Basis under State Plan on FIRM prices against NIT No.- 72/PR/BSPTCL/15 | DCB | 4 | 2016-03-02 | 2016-03-02 | 2016-12-01 | 7.41 | 7.41 | State Plan | 7.93 | 8.002 | 0 |  |  |  | 8.002 | 0 |  |  |  | 8.002 | 0 |  |  |  | 8.002 | 0 |  |  |  | 8.002 | 0 |  |  |  | 8.002 | 0 |  | 0 | 0 |  | 0 | 0
427 | 87/2015 | P1 | 12th Plan Ongoing Project | Page No. 266, Sl. No. 73 of MYT Order | Construction of 132 KV Transmission Lines required for the connectivity of power to upcoming new 132/33 KV Grid Sub Stations at Korha (Distt- Katihar),Nathnagar (Distt.- Bhagalpur) and Jamui(new) on turnkey basis under State Plan (R.L.=190 CKM) against NIT No.-87/PR/BSPTCL/2015 | DCB | 3 | 2015-12-30 | 2015-12-30 | 2016-12-30 | 63.1 | 63.1 | State Plan | 69.55 | 50.3654 | 0 |  |  |  | 50.3654 | 0 |  |  |  | 50.3654 | 0 |  |  |  | 50.3654 | 0 |  |  |  | 50.3654 | 0 |  |  |  | 50.3654 | 0 |  | 0 | 0 |  | 0 | 0
428 |  | - | New Project | - | Civil Works Buildings at various Location (TCC Bhagalpur, Dharbhanga, Madhepura, Muz, Purnea, Patna) | [7 empty] | IRF | 0 | 0.75562 | -0.75562 |  |  |  | 0.75562 | -0.75562 |  |  |  | 0.75562 | -0.75562 |  |  |  | 0.75562 | -0.75562 |  |  |  | 0.75562 | -0.75562 |  |  |  | 0.75562 | -0.75562 |  |  | 0 |  |  | 0
429 |  | P1 | New Project | - | Training institute at 132/33 KV GSS Gaurichak and Various Location TCC Bhagalpur, TCC Patna, TCC Chapra) | [7 empty] | IRF | 0 | 0.46589 | -0.46589 |  |  |  | 0.46589 | -0.46589 |  |  |  | 0.46589 | -0.46589 |  |  |  | 0.46589 | -0.46589 |  |  |  | 0.46589 | -0.46589 |  |  |  | 0.46589 | -0.46589 |  |  | 0 |  |  | 0
430 |  | - | New Project | - | Furniture & Fixture | [7 empty] | IRF | 0 | 0.64054 | -0.64054 | 0.25687 | 0.50438 |  | 1.1449 | -0.88805 |  | 0.076209 |  | 1.2211 | -0.96426 |  |  |  | 1.2211 | -0.96426 |  |  |  | 1.2211 | -0.96426 |  |  |  | 1.2211 | -0.96426 |  |  | 0 |  |  | 0
431 |  | - | New Project | - | Land Owned Under Full Title | [7 empty] | IRF | 0 | 20.1988 | -20.1988 |  |  |  | 20.1988 | -20.1988 |  |  |  | 20.1988 | -20.1988 |  |  |  | 20.1988 | -20.1988 |  |  |  | 20.1988 | -20.1988 |  |  |  | 20.1988 | -20.1988 |  |  | 0 |  |  | 0
432 |  | - | New Project | - | Land Owned Under Full Title | [7 empty] | State Plan | 0 | 0 | 0 |  | 14.823 |  | 14.823 | -14.823 |  |  |  | 14.823 | -14.823 |  |  |  | 14.823 | -14.823 |  |  |  | 14.823 | -14.823 |  |  |  | 14.823 | -14.823 |  | 0 | 0 |  | 0 | 0
433 |  | - | New Project | - | IB Guest House at 132/33 KV GSS Phulparas | [7 empty] | IRF | 0 | 0 | 0 |  | 0.428 |  | 0.428 | -0.428 |  |  |  | 0.428 | -0.428 |  |  |  | 0.428 | -0.428 |  |  |  | 0.428 | -0.428 |  |  |  | 0.428 | -0.428 |  |  | 0 |  |  | 0
434 |  | P1 | New Project | - | Rooftaop Solar Power Plant Panel | [7 empty] | IRF | 0 | 0 | 0 | 8.9074 | 8.4368 |  | 8.4368 | 0.47061 |  |  |  | 8.4368 | 0.47061 |  |  |  | 8.4368 | 0.47061 |  |  |  | 8.4368 | 0.47061 |  |  |  | 8.4368 | 0.47061 |  |  | 0 |  |  | 0
435 |  | - | 13th Plan Other Project | - | Land Owned Under Full Title | [7 empty] | BRGF | 0 | 10.4768 | -10.4768 | 1.978 | 2.8194 |  | 13.2962 | -11.3181 |  |  |  | 13.2962 | -11.3181 |  |  |  | 13.2962 | -11.3181 |  |  |  | 13.2962 | -11.3181 |  |  |  | 13.2962 | -11.3181 |  |  | 0 |  |  | 0
436 |  | P1 | New Project | - | Misc. Line Works | [7 empty] | IRF | 0 | 0.31714 | -0.31714 |  |  |  | 0.31714 | -0.31714 |  | 0.1287 |  | 0.44584 | -0.44584 |  |  |  | 0.44584 | -0.44584 |  |  |  | 0.44584 | -0.44584 |  |  |  | 0.44584 | -0.44584 |  |  | 0 |  |  | 0
437 |  | - | New Project | - | Office Equipments | [7 empty] | IRF | 0 | 3.1221 | -3.1221 | 0.19845 | 1.4337 |  | 4.5557 | -4.3573 |  |  |  | 4.5557 | -4.3573 |  |  |  | 4.5557 | -4.3573 |  |  |  | 4.5557 | -4.3573 |  |  |  | 4.5557 | -4.3573 |  |  | 0 |  |  | 0
438 |  | - | New Project | - | Other Misc. Civil Works | [7 empty] | IRF | 0 | 1.178 | -1.178 |  | 0.8118 |  | 1.9898 | -1.9898 |  |  |  | 1.9898 | -1.9898 |  |  |  | 1.9898 | -1.9898 |  |  |  | 1.9898 | -1.9898 |  |  |  | 1.9898 | -1.9898 |  |  | 0 |  |  | 0
439 |  | - | New Project | - | Reconductoring of 132KV Tr. Lines(ADB & IRF) | [7 empty] | IRF | 0 | 0 | 0 |  | 0.14018 |  | 0.14018 | -0.14018 |  |  |  | 0.14018 | -0.14018 |  |  |  | 0.14018 | -0.14018 |  |  |  | 0.14018 | -0.14018 |  |  |  | 0.14018 | -0.14018 |  |  | 0 |  |  | 0
440 |  | - | New Project | - | Other Office Equipments | [7 empty] | IRF | 0 |  |  |  | 0.7563 |  | 0.7563 | -0.7563 |  | 0.16578 |  | 0.92207 | -0.92207 |  |  |  | 0.92207 | -0.92207 |  |  |  | 0.92207 | -0.92207 |  |  |  | 0.92207 | -0.92207 |  |  | 0 |  |  | 0
441 | 14/PR/BSPTCL/2023 | - | 13th Plan Other Project | - | Irrigation Canal bridge(Culvert) for 2X50 MVA, 132/33 KV GSS Daudnagar | [7 empty] | BRGF | 0 |  |  | 0.2801 | 0.2801 |  | 0.2801 | 0 |  |  |  | 0.2801 | 0 |  |  |  | 0.2801 | 0 |  |  |  | 0.2801 | 0 |  |  |  | 0.2801 | 0 |  |  | 0 |  |  | 0
442 |  | P1 | New Project | - | Plant & Machinery | [7 empty] | IRF | 0 | 4.7456 | -4.7456 |  | 3.0017 |  | 7.7473 | -7.7473 |  | 6.395 |  | 14.1424 | -14.1424 |  |  |  | 14.1424 | -14.1424 |  |  |  | 14.1424 | -14.1424 |  |  |  | 14.1424 | -14.1424 |  |  | 0 |  |  | 0
443 |  | - | 12th Plan Ongoing Project | Page No. 163, Sl. No. 46 of MYT Order | Supply, Installation, Implementation, Configuration and Integration of ERP system in BSPTCL | [7 empty] | IRF | 0 | 17.1514 | -6.1714 |  | 1.5732 |  | 18.7246 | -7.7446 |  |  |  | 18.7246 | -7.7446 |  |  |  | 18.7246 | -7.7446 |  |  |  | 18.7246 | -7.7446 |  |  |  | 18.7246 | -7.7446 |  |  | 0 |  |  | 0
444 | - | P1 | 13th Plan Other Project |  | Construction of 02 nos. of 220 KV GIS line bays (related with Garaul GSS) | [7 empty] | State Plan | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
438 | - | P2 | 13th Plan Other Project |  | Construction of 220 KV& 132 KV transmission line by monopole/ narrow base tower for interconnectivity/ redundancy of GSS in and around Patna | [5 empty] | 85 |  | State Plan | 0 | 0 | 0 |  |  |  | 0 | 0 | 26.93 |  |  | 0 | 26.93 |  |  |  | 0 | 26.93 |  |  |  | 0 | 26.93 |  |  |  | 0 | 26.93 |  | 0 | 0 |  | 0 | 0 |  | 21.544 | 5.386
439 | - | P2 | 13th Plan Other Project |  | Reconductoring of Chandauti-Tekari 132 KVD/CTransmission line by HTLS | [5 empty] | 50.5 |  | State Plan | 0 | 0 | 0 |  |  |  | 0 | 0 | 22.4 |  |  | 0 | 22.4 |  |  |  | 0 | 22.4 |  |  |  | 0 | 22.4 |  |  |  | 0 | 22.4 |  | 0 | 0 |  | 0 | 0 |  | 17.92 | 4.48
440 | 14/PR/BSPTCL/2021 | P2 | 13th Plan Other Project | Page No. 239, Sl. No. 416 of MYT Order | LILO of 132 KV Sonenagar - Rihand (Ckt-I) Transmission line at GSS Nabinagar (RL-15 RKM) NIT No-14/PR/BSPTCL/2021 |  |  | 12.08.2021 | 12.08.2021 | 11.11.2022 | 75.69 |  | BRGF | 0 | 0 | 1.1275 | 17.9511 |  |  | 0 | 19.0786 |  | 6.9047 | 0.69092 | 7.5956 | 11.483 | 16.5914 | 75.69 |  | 83.2856 | -47.6156 |  |  |  | 83.2856 | -47.6156 |  |  |  | 83.2856 | -47.6156 |  |  | 16.5914 |  |  | 0
441 | - | CIVIL |  | - | Work order for supply & installation of optimizer storage in accounts wing and corridor west Block of BSPTCL, Vidyut Bhawan-II, Patna. | [7 empty] | IRF | 0 | 0 | 0.11056 |  |  |  | 0 | 0.11056 |  |  |  | 0 | 0.11056 |  |  |  | 0 | 0.11056 |  |  |  | 0 | 0.11056 |  |  |  | 0 | 0.11056 |  |  | 0 |  |  | 0
442 | 44/PR/BSPTCL/2021 | P1 | 13th Plan Other Project | Page No. 236, Sl. No. 397 of MYT Order | Construction of 2 nos. of 220KV GIS bays at GSS Dumraon (BGCL) & 01 no of 220KV GIS bay at Darbhanga (DMTCL) on turnkey basis against NIT No.:- 44/PR/BSPTCL/20221 |  | 2 | 12.07.2022 | 12.07.2022 | 12 (Twelev) months from the date of issue of NOA | 30.92 | 0 | State Plan | 30.92 | 0 | 0 | 17.614 |  |  | 0 | 17.614 | 0.8 |  |  | 0 | 18.414 | 7.706 | 0 |  | 0 | 26.12 | 23.21 | 30.92 |  | 30.92 | 18.41 |  |  |  | 30.92 | 18.41 |  | 6.1648 | 1.5412 |  | 18.568 | 4.642 |  | 0.64 | 0.16
443 | 10/PR/BSPTCL/2021 | P2 | 13th Plan Other Project | Page No. 239, Sl. No. 417 of MYT Order | Construction of 132/33 KV 2X50 MVA GSS Barari (Dist.-Bhagalpur), 132/33 KV 2X50 MVA GSS Bagha (Dist.-West Champaran) & 132/33 KV 2X50 MVA GSS Murliganj (Dist.- | DCB |  | 17.08.2021 | 17.08.2021 | 16.11.2022 | 141.87 | 150.72 | State Plan | 141.87 | 0 | 4.629 | 11.3319 |  |  | 0 | 15.9609 | 8.97 | 22.5257 | 0.14846 | 22.6742 | 2.2567 | 44.96 | 44.96 |  | 67.6342 | 2.2567 |  |  |  | 67.6342 | 2.2567 |  |  |  | 67.6342 | 2.2567 |  | 35.968 | 8.992 |  | 0 | 0 |  | 7.176 | 1.794
444 | 15/PR/BSPTCL/2021 | P1 | 13th Plan Other Project | Page No. 239, Sl. No. 418 of MYT Order | 132 Kv D/C Murliganj-Udaikishanganj T/L, LILO of one circuit of 132 KV D/C Ramnagar-Dhanha T/L & LILO of both circuit of 132 KV GIS Goradih-GSS Sabour T/L(15/PR/BSPTCL/2021)(BRGF) |  | 11 | 16.08.2021 | 16.08.2021 | 15.11.2022 | 164.77 |  | BRGF | 154.26 | 0 | 15.0172 | 23.8079 |  |  | 0 | 38.8251 | 2.15 |  |  | 0 | 40.9751 | 48.45 | 48.45 |  | 48.45 | 40.9751 |  |  |  | 48.45 | 40.9751 |  |  |  | 48.45 | 40.9751 |  |  | 48.45 |  |  | 0 |  |  | 2.15
445 | 46/PR/BSPTCL/2021 | P1 | New Project | Case 17 of 2023 | Construction of following on turnkey basis under IRF (i) Construction of 01 Nos. of 132/33 KV Transformer bays each at GSS Nirmali & GSS Rosera (ii) Construction of 01 No. 220/132 KV transformer bay at GSS Pusauli & (iii) Construction of new transformer foundation for 50 MVA Power Transformer at 03 locations for transformers against NIT No: - 46/PR/BSPTCL/2021 |  | 5 | 13.06.2022 | 13.06.2022 | 12.06.2023 | 9.89 | 9.89 | IRF | 9.89 | 0 | 0 | 0.68373 |  |  | 0 | 0.68373 | 0.42 |  |  | 0 | 1.1037 | 7.8563 | 9.89 |  | 9.89 | -0.93 |  |  |  | 9.89 | -0.93 |  |  |  | 9.89 | -0.93 |  |  | 7.8563 |  |  | 0 |  |  | 0.42
446 | 09/PR/BSPTCL/2022 | P1 | New Project | Case 17 of 2023 | Supply, installation, testing & commissioning of Device Language Message Specification (DLMS) compliant 0.2s class ABT type energy meter with implementation of 100% metering, data acquisition and ABT monitoring for the transmission & sub-transmission substations from 220 KV level to 33KV level, Monthly Energy Accounting and Service Maintenance for a period of 5 years under “Assistance to States for Capital Investment 2022-23” Scheme against NIT No.:- 09/PR/BSPTCL/2022 |  | 1 |  |  | 08 (Eight) months from the date of issue of NOA | 78.39 | 0 | Special Central Funded Scheme | 78.39 | 0 | 48.0659 | 12.1778 | 60.2437 |  | 60.2437 | 0 |  | 0.66356 |  | 60.9072 | -0.66356 |  |  |  | 60.9072 | -0.66356 |  |  |  | 60.9072 | -0.66356 |  |  |  | 60.9072 | -0.66356 |  |  | 0 |  |  | 0
447 | 14/PR/BSPTCL/2022 | P1 | New Project | Case 17 of 2023 | Re-conductoring of following 12 Nos. 132 KV Transmission Lines with HTLS equivalent to ACSR Panther :- (i) 132 kV Gopalganj to Mashrakh, (ii) 132 kV Mashrakh to Siwan, (iii) 132 kV Siwan to Hathua (iv) 132 kV Hatuha to Gopalganj, (v) 132 kV Samastipur to Darbhanga, (vi) 132 Kv Gangwara to Pandaul, (vii) 132 kV Purnea to Katihar, (viii) 132 kV Chhapra to Hajipur, (ix) 132 kV Kataiya to Supaul , (x) 132 kV Madhepura to Supaul, (xi) 132 kV Hajipur (New) to Hajipur & (xii) 132 kV Samastipur(New) to Samastipur under “Assistance to States for Capital Investment 2022-23” Scheme against NIT No.:- 14/PR/BSPTCL/2022 |  | 4 | 02.08.2022 | 02.08.2022 | 07 (Seven) months from the date of issue of NOA | 333.05 | 0 | Special Central Funded Scheme | 333.05 | 334.0462 | 14.1065 | 61.4721 | 10.2853 |  | 344.3315 | 65.2933 | 0.24 | 0.24452 |  | 344.576 | 65.2888 |  |  |  | 344.576 | 65.2888 |  |  |  | 344.576 | 65.2888 |  |  |  | 344.576 | 65.2888 |  |  | 0 |  |  | 0 |  |  | 0.24
448 | 33/PR/BSPTCL/2021 | P1 | New Project | Case 17 of 2023 | 1.construction of 05 nos. of 132 KV Transmission tower (including 03 nos. of pile foundation) ,stringing with ACSR panther conductor for crossing of 33 KV line from GSS Ramnagar to PSS Chautarava over Massan River near Dainmarwa Village 2. Construction of 02 nos. of 132 KV Transmission tower , stringing with ACSR panther conductor for crossing of 33 KV line from GSS Ramnagar to PSS Bagha over Masssan River near Juda Village under deposit head on turnkey basis against NIT No.-33/PR/BSPTCL/2021 |  | 4 | 09.03.2022 | 09.03.2022 | 2022-12-08 | 6.74 | 0 | Deposit Work | 6.01 | 0 | 0 | 6.0556 | 6.0556 |  | 6.0556 | 0 |  |  |  | 6.0556 | 0 |  |  |  | 6.0556 | 0 |  |  |  | 6.0556 | 0 |  |  |  | 6.0556 | 0 | 0
449 | 24/PR/BSPTCL/2022 | P2 | New Project | Case 17 of 2023 | R&M of 02 nos. 220/132/33KV GSS Bodhgaya and Khagaul on turnkey basis against NIT No.-24/PR/BSPTCL/2022 | [5 empty] | 21.39 |  | State Plan | 0 | 0 | 0 | 15.8219 |  |  | 0 | 15.8219 | 5.19 |  |  | 0 | 21.0119 |  | 21.39 |  | 21.39 | -0.37814 |  |  |  | 21.39 | -0.37814 |  |  |  | 21.39 | -0.37814 |  | 0 | 0 |  | 0 | 0 |  | 4.152 | 1.038
450 | 25/PR/BSPTCL/2022 | P2 | New Project | Case 17 of 2023 | R&M of 04 nos. 132/33KV GSS Jehanabad, Banjari, Shekhpura & Hajipur on turnkey basis against NIT No.-25/PR/BSPTCL/2022 | [5 empty] | 36.28 |  | State Plan | 0 | 0 | 0 | 17.7914 |  |  | 0 | 17.7914 | 15 |  |  | 0 | 32.7914 |  | 36.28 |  | 36.28 | -3.4886 |  |  |  | 36.28 | -3.4886 |  |  |  | 36.28 | -3.4886 |  | 0 | 0 |  | 0 | 0 |  | 12 | 3
451 | 15/PR/BSPTCL/2022 | P2 | New Project | Case 17 of 2023 | Re-conductoring of 01 no. 220kV trans. Line with HTLS Conductor(Zebra equivalent) & 05 nos. trans. Lines with HTLS conductor(Panther equivalent) at 220KV BTPS-Biharsharif, BTPS- Begusarai & 132KV Patna-Sipra, Bikramganj to Dumraon, Dehri to Bikarmaganj, Dehri-Sasaram, Sonenagar to Lilo Nabinagar & Bakhtiyarpur-Baripahari against NIT No. 15/PR/BSPTCL/2022 | DCB |  | 02.08.2022 | 02.08.2022 | 01.03.2023 | 138.87 | - | Special Central Funded Scheme | 138.87 | 81.1287 | 46.8136 | 15.5692 | 64.9123 |  | 146.041 | -2.5295 | 0.14 | 0.12743 |  | 146.1684 | -2.5169 |  |  |  | 146.1684 | -2.5169 |  |  |  | 146.1684 | -2.5169 |  |  |  | 146.1684 | -2.5169 |  |  | 0 |  |  | 0 |  |  | 0.14
452 | - | - | New Project | - | Building | [7 empty] | IRF | 0 | 0.5033 | -0.5033 |  | 0.46825 |  | 0.97155 | -0.97155 |  |  |  | 0.97155 | -0.97155 |  |  |  | 0.97155 | -0.97155 |  |  |  | 0.97155 | -0.97155 |  |  |  | 0.97155 | -0.97155 |  |  | 0 |  |  | 0
453 | - | - | New Project | - | Civil Works | [7 empty] | IRF | 0 | 2.0794 | -2.0794 |  | 1.7202 |  | 3.7996 | -3.7996 |  | 9.4264 |  | 13.2261 | -13.2261 |  |  |  | 13.2261 | -13.2261 |  |  |  | 13.2261 | -13.2261 |  |  |  | 13.2261 | -13.2261 |  |  | 0 |  |  | 0
454 | - | - | New Project | - | Computer & Accessories | [7 empty] | IRF | 0 | 3.18 | -3.18 | 0.18164 | 0.31367 |  | 3.4937 | -3.3121 |  | 0.83938 |  | 4.3331 | -4.1514 |  |  |  | 4.3331 | -4.1514 |  |  |  | 4.3331 | -4.1514 |  |  |  | 4.3331 | -4.1514 |  |  | 0 |  |  | 0
455 | 26/PR/BSPTCL/2018 | - |  | - | Tr. Line Runnisaidpur & TSS Bajpatti, Narkatiyaganj-TSS Raxaul & GSS Dhaka - TSS Bairgania | [7 empty] | Deposit Work | 0 | 35.4501 | -33.6384 |  |  |  | 35.4501 | -33.6384 |  |  |  | 35.4501 | -33.6384 |  |  |  | 35.4501 | -33.6384 |  |  |  | 35.4501 | -33.6384 |  |  |  | 35.4501 | -33.6384 | 0
456 | ICB No. 23/Package C-1/ BSPTCL/ADB/2016 | P2 |  | - | Capacity augmentation Under ICB No. 23/Package C-1/ BSPTCL/ADB/2016 | [7 empty] | ADB | 0 | 0.10253 | 0.60544 |  |  |  | 0.10253 | 0.60544 |  |  |  | 0.10253 | 0.60544 |  |  |  | 0.10253 | 0.60544 |  |  |  | 0.10253 | 0.60544 |  |  |  | 0.10253 | 0.60544
457 | 07/PR/BSPTCL/2023 | P1 | New Project | Case 17 of 2023 | Construction of 2 No. of 400 KV GIS Bays at GSS Naubatpur (BGCL) & Construction of 2 No. of 220 KV GIS Bays at GSS Goradih (BGCL) against NIT No. 07/PR/BSPTCL/2023 | [6 empty] | 60.81 | State Plan | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  | 0 | 0 |  | 0 | 0
458 | 51/PR/BSPTCL/2022 | P1 | New Project | Case 17 of 2023 | Completion of leftover portion of works for capacity augmentation of various GSS by replacement of transformers as detailed below: - (i) 02 No. 100 MVA transformer by 200 MVA transformer at GSS Hajipur (ii) 02 No. 100 MVA transformer by 200 MVA transformer at GSS Gopalganj (iii) 01 No. 160 MVA transformer by 200 MVA transformer at GSS Darbhanga against NIT No. 51/PR/BSPTCL/2022 | [6 empty] | 82.73 | Special Central Funded Scheme | 0 | 0 | 0 | 14.8208 |  |  | 0 | 14.8208 | 59.36 | 44.0848 |  | 44.0848 | 30.096 | 0 | 0 |  | 44.0848 | 30.096 |  |  |  | 44.0848 | 30.096 |  |  |  | 44.0848 | 30.096 |  |  | 0 |  |  | 0 |  |  | 59.36
459 | 49/PR/BSPTCL/2022 | P1 | New Project | Pending | Construction of 220 KV D/C Transmission Line from PGCIL Banka to BGCL Goradih with ACSR Zebra Conductor (Line Length - 39 KM) against NIT No. 49/PR/BSPTCL/2022 | [6 empty] | 55.2 | State Plan | 0 | 0 | 0 | 60.664 |  |  | 0 | 60.664 | 150.73 |  | 0.76844 | 0.76844 | 210.6255 |  |  |  | 0.76844 | 210.6255 |  |  |  | 0.76844 | 210.6255 |  |  |  | 0.76844 | 210.6255 |  | 0 | 0 |  | 0 | 0 |  | 120.584 | 30.146
460 | 40/PR/BSPTCL/2022 | P1 | New Project | Case 17 of 2023 | Supply, Erection, Testing and Commissioning of 20 Nos. of 50 MVA, 132/33 KV, Power Transformer and its associated works by Manufacturers in Different GSSs of BSPTCL on turnkey basis against NIT No. 40/PR/BSPTCL/2022 | [6 empty] | 98.34 | Special Central Funded Scheme | 0 | 0 | 0 | 86.9853 |  |  | 0 | 86.9853 | 11.13 | 85.6953 |  | 85.6953 | 12.42 |  |  |  | 85.6953 | 12.42 |  |  |  | 85.6953 | 12.42 |  |  |  | 85.6953 | 12.42 |  |  | 0 |  |  | 0 |  |  | 11.13
461 | 17/PR/BSPTCL/2023 | P1 | New Project | Case 17 of 2023 | Construction of 07 Nos. towers (including 05 Nos. Pile foundation) for crossing of 33 KV line on 132 KV tower over Ghaghara River near Manjhi Village, Sitab Diyara, Block - Rivilganj, Distt. - Saran on turnkey basis under deposit head of NBPDCL against NIT No. 17/PR/BSPTCL/2023. | [6 empty] | 17.57 | Deposit Work | 0 | 0 | 0 |  |  |  | 0 | 0 | 11.61 |  |  | 0 | 11.61 |  |  |  | 0 | 11.61 |  |  |  | 0 | 11.61 |  |  |  | 0 | 11.61 | 11.61 | [8 empty] | 11.61
462 | 13/PR/BSPTCL/2023 | P1 | New Project | Case 17 of 2023 | Construction of 132 KV D/C Transmission line with HTLS conductor for interconnection of Stage - I & Stage - II at NTPC, Barauni against NIT No. 13/PR/BSPTCL/2023 | [6 empty] | 9.6 | Deposit Work | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0
463 | 10/PR/BSPTCL/2023 | P1 | New Project | Case 17 of 2023 | Construction of 2X50 MVA, 132/33 KV GSS Bhorey (Dist. Gopalganj) with Construction of associated 02 Nos. 132 KV Line bays at GSS Hathua & Construction of its associated 132 KV D/C BhoreyHathua Tr. Line with ACSR Panther Conductor (Line Length - 60 RKM) on Turnkey Basis under State Plan against NIT No. 10/PR/BSPTCL/2023 | [6 empty] | 123.83 | State Plan | 0 | 0 | 0 |  |  |  | 0 | 0 | 61.35 |  |  | 0 | 61.35 |  |  |  | 0 | 61.35 |  |  |  | 0 | 61.35 |  |  |  | 0 | 61.35 |  | 0 | 0 |  | 0 | 0 |  | 49.08 | 12.27
464 | 11/PR/BSPTCL/2023 | P1 | New Project | Case 17 of 2023 | Renovation of 04 different existing T/L of BSPTCL by construction of Pile foundation (05) No. open foundations (03) Nos. and including associated works on trunkey basis against NIT No. 11/PR/BSPTCL/2023 1) 220 KV Kishanganj (New) - Madhepura Line 2) 220 KV Laukahi - Darbhanga (DMTCL) line 3) 132 KV Kishanganj (New) - Kishanganj line 4) 132 KV Motihari - Dhaka Line | [6 empty] | 18.2 | IRF | 0 | 0 | 0 | 2.5532 |  |  | 0 | 2.5532 | 6.93 |  |  | 0 | 9.4832 |  |  |  | 0 | 9.4832 |  |  |  | 0 | 9.4832 |  |  |  | 0 | 9.4832 |  |  | 0 |  |  | 0 |  |  | 6.93
465 | 22/PR/BSPTCL/2023 23/PR/BSPTCL/2023 | P1 | New Project | Case 17 of 2023 | Construction of 400/220/132 KV AIS Sub-Station at Chhapra (New) alongwith construction of associated 400 KV, 220 KV, 132 KV transmission lines and 220 KV & 132 KV bays. | [6 empty] | 998.39 | State Plan | 0 | 0 | 0 |  |  |  | 0 | 0 | 55.47 |  |  | 0 | 55.47 |  |  |  | 0 | 55.47 |  |  |  | 0 | 55.47 |  |  |  | 0 | 55.47 |  | 0 | 0 |  | 0 | 0 |  | 44.376 | 11.094
466 | 25/PR/BSPTCL/2023 | P2 | New Project | Case 17 of 2023 | Construction of 2X50 MVA 132/33 KV GSS Chandi (Dist. - Nalanda) with Construction of 02 Nos. of 132 KV Line Bays at GSS Harnaut along with construction of 132 KV D/C Transmission Line from GSS Chandi to GSS Asthawan (40 RKM) & Construction of 132 KV D/C Transmission Line from GSS Chandi to GSS Harnaut (20 RKM). | [6 empty] | 129.75 | State Plan | 0 | 0 | 0 |  |  |  | 0 | 0 | 11.05 |  |  | 0 | 11.05 |  |  |  | 0 | 11.05 |  |  |  | 0 | 11.05 |  |  |  | 0 | 11.05 |  | 0 | 0 |  | 0 | 0 |  | 8.84 | 2.21
467 | 08/PR/BSPTCL/2023 | P2 | New Project | Case 17 of 2023 | Implementation of SAS for control & monitoring of existing 12 Nos. of 220/132/33 KV Susstations (Hajipur, Khagaul, Fatuha, Gaurichak, Begusarai, Bodhgaya, Dehi-on-Sone, Pusauli, Darbhanga, Gopalganj, Madhepura & Bihta (New) including modification of existing IEDs and field equipment of BSPTCL against NIT No. 08/PR/BSPTCL/2023 | [6 empty] | 99.61 | PSDF | 0 | 0 | 0 | 27.5719 |  |  | 0 | 27.5719 | 62.11 |  |  | 0 | 89.6819 |  | 99.61 |  | 99.61 | -9.9281 |  |  |  | 99.61 | -9.9281 |  |  |  | 99.61 | -9.9281 | 55.899 | [7 empty] | 6.211 | 55.899
468 | 24/PR/BSPTCL/2023 | P2 | New Project | Case 17 of 2023 | Construction of 2X80 MVA, 132/33 KV Gas Insulated SubStation at PMCH, Patna alongwith 2 Nos. of 132 KV GIS Line Bay Extention at 220/132/33 KV GIS Digha on turnkey basis alongwith Construction of 132 KV D/C ACSR Moose Conductor Transmission Line with Pile foundation from 220/132/33 KV GIS Digha (New) to 132/33 KV GIS PMCH | [6 empty] | 255.9 | Deposit Work | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 0
469 | 54/PR/BSPTCL/2022 | P2 | New Project | Case 17 of 2023 | Construction of single phase 132 KV Transmission line through underground XLPE cable from GSS Jamalpur to TSS Jamalpur as a spare cable under deposit head of Railway against NIT No. 54/PR/BSPTCL/2022. | [6 empty] | 4.85 | Deposit Work | 0 | 0 | 0 |  |  |  | 0 | 0 | 3.17 |  |  | 0 | 3.17 |  |  |  | 0 | 3.17 |  |  |  | 0 | 3.17 |  |  |  | 0 | 3.17 | 3.17 | [8 empty] | 3.17
470 | ICB No. 25/Package E-1/BSPTCL/ADB/2016 | P2 |  | - | 33KV Line Bays in Form of Indoor VCB Panel under TC Purnea(ICB No. 25/Package E-1/ BSPTCL/ADB/2016) | [6 empty] | 3.25 |  | 0 | 0 | 2.1269 |  |  |  | 0 | 2.1269 |  |  |  | 0 | 2.1269 |  |  |  | 0 | 2.1269 |  |  |  | 0 | 2.1269 |  |  |  | 0 | 2.1269 |  | 0 | 0 |  | 0 | 0
471 | ICB 24/Package-D-1/BSPTCL/ADB/2016 | P2 |  | MYT order FY 2020-22 page 92, Sl. 58 | 33KV Line Bays in Form of Indoor VCB Panel at 06 nos. AIS Substation Under Transmission Circle Bhagalpur( ICB 24/Package-D-1/BSPTCL/ADB/2016) | [8 empty] | 0 | 0 | 1.5248 |  |  |  | 0 | 1.5248 |  |  |  | 0 | 1.5248 |  |  |  | 0 | 1.5248 |  |  |  | 0 | 1.5248 |  |  |  | 0 | 1.5248 |  | 0 | 0 |  | 0 | 0
472 | 59/PR/BSPTCL/2014 Pkg B | P1 |  | - | 220/132/33 KV Transformer bays at GSS Katra, Masaurahi,Digha and Khagaul(59/PR/BSPTCL/2014 Pkg B) | [8 empty] | 0 | 0 | 0.33601 |  |  |  | 0 | 0.33601 |  |  |  | 0 | 0.33601 |  |  |  | 0 | 0.33601 |  |  |  | 0 | 0.33601 |  |  |  | 0 | 0.33601 |  | 0 | 0 |  | 0 | 0
473 | ICB 28/Package-H-1/BSPTCL/ADB/2016 | P2 |  | - | 33KV Line Bays in Form of Indoor VCB Panel at 14 Nos. AIS Substation Under Transmission Circle Dehri-On-Sone( ICB 28/Package-H-1/BSPTCL/ADB/2016) | [8 empty] | 0 | 0 | 1.3376 |  |  |  | 0 | 1.3376 |  |  |  | 0 | 1.3376 |  |  |  | 0 | 1.3376 |  |  |  | 0 | 1.3376 |  |  |  | 0 | 1.3376 |  | 0 | 0 |  | 0 | 0
474 | 18/PR/BSPTCL/2022-1 | - | New Project | - | Reconst. of Broken Boundary Wall along roadside & switchyard at GSS Harnaut(18/PR/BSPTCL/2022-1) | [7 empty] | IRF | 0 | 0 | 0.44061 | 0.57793 | 1.0185 |  | 1.0185 | 0 |  |  |  | 1.0185 | 0 |  |  |  | 1.0185 | 0 |  |  |  | 1.0185 | 0 |  |  |  | 1.0185 | 0 |  |  | 0 |  |  | 0
475 | 39/PR/BSPTCL/2021 | - |  | - | Reconstruction of Boundary wall, earth filing and RCC Road for TSS Bay at 132/33 KV GSS,Dhaka(39/PR/BSPTCL/2021) | [8 empty] | 0 | 0 | 0.15644 |  |  |  | 0 | 0.15644 |  |  |  | 0 | 0.15644 |  |  |  | 0 | 0.15644 |  |  |  | 0 | 0.15644 |  |  |  | 0 | 0.15644 |  | 0 | 0 |  | 0 | 0
476 | 18/PR/BSPTCL/2022 | - | New Project | - | Boundary wall at 132/33 KV GSS, Hajipur(18/PR/BSPTCL/2022) | [7 empty] | IRF | 0 | 0 | 1.0995 | 1.0109 | 2.1104 |  | 2.1104 | 0 |  |  |  | 2.1104 | 0 |  |  |  | 2.1104 | 0 |  |  |  | 2.1104 | 0 |  |  |  | 2.1104 | 0 |  |  | 0 |  |  | 0
477 | 38/PR/BSPTCL/2021 | P2 | New Project | MYT Order FY 2023-26 page 249, Sl. 422 | Construction of Construction of new 3x180MVA, 132KV GIS GSS Mithapur at Agriculture Research Institute Mithapur, 2) Construction of 132 KV transmission line from Gis GSS Mithapur to GSS Karbigahia through 1200sqm XLPE underground cable with associated work including dismantling of existing cable system (RL-2.7 KM) | [5 empty] | 136.13 |  | State Plan | 0 | 0 | 96.0728 | 25.6593 |  |  | 0 | 121.7322 | 3.51 |  |  | 0 | 125.2422 | 14.3978 | 136.13 |  | 136.13 | 3.51 |  |  |  | 136.13 | 3.51 |  |  |  | 136.13 | 3.51 |  | 11.5183 | 2.8796 |  | 0 | 0 |  | 2.808 | 0.702
478 | 18/PR/BSPTCL/2023 | P1 | New Project | - | Reconductoring work of 02 Nos. 220 KV & 06 Nos. 132 KV Transmission Line with HTLS Conductor project against NIT 18/PR/BSPTCL/2023 | [5 empty] | 282.62 |  | Special Central Funded Scheme | 338.11 | 0 | 0 | 205.908 | 58.1578 |  | 58.1578 | 147.7501 | 158.64 |  |  | 58.1578 | 306.3901 |  |  |  | 58.1578 | 306.3901 |  |  |  | 58.1578 | 306.3901 |  |  |  | 58.1578 | 306.3901 |  |  | 0 |  |  | 0 |  |  | 158.64
479 | 02/PR/BSPTCL/2022-02 |  |  |  | Work order for ''Construction of Transmission office (G+2) building at GSS Madhepura' | [7 empty] | IRF | 0 | 0 | 0 | 0.46842 |  |  | 0 | 0.46842 | 1.17 |  |  | 0 | 1.6384 |  |  |  | 0 | 1.6384 |  |  |  | 0 | 1.6384 |  |  |  | 0 | 1.6384 |  |  | 0 |  |  | 0 |  |  | 1.17
480 | 02/PR/BSPTCL/2023-01 |  |  |  | Work order for ''Construction of Transmission office (G+2) building at GSS Chhapra'' | [7 empty] | IRF | 0 | 0 | 0 | 0.85207 |  |  | 0 | 0.85207 | 1.09 |  |  | 0 | 1.9421 |  |  |  | 0 | 1.9421 |  |  |  | 0 | 1.9421 |  |  |  | 0 | 1.9421 |  |  | 0 |  |  | 0 |  |  | 1.09
481 | 02/PR/BSPTCL/2024 |  |  |  | Work order for ''Construction of Transmission office (G+2) building at GSS Madhepura'' | [7 empty] | IRF | 0 | 0 | 0 | 0.50092 |  |  | 0 | 0.50092 | 1.83 |  |  | 0 | 2.3309 |  |  |  | 0 | 2.3309 |  |  |  | 0 | 2.3309 |  |  |  | 0 | 2.3309 |  |  | 0 |  |  | 0 |  |  | 1.83
482 | 04/PR/BSPTCL/2023 |  |  |  | Work order for ''Construction of control Room Building at 220/132/33 KV GSS Biharsharif''. | [7 empty] | IRF | 0 | 0 | 0 | 0.5513 |  |  | 0 | 0.5513 | 0.66 |  |  | 0 | 1.2113 |  |  |  | 0 | 1.2113 |  |  |  | 0 | 1.2113 |  |  |  | 0 | 1.2113 |  |  | 0 |  |  | 0 |  |  | 0.66
483 | 09/PR/BSPTCL/2023 |  |  |  | PO for Supply contract for design, manufacture, testing at manufacture's works and delivery of equipments required for restoration of collapsed towers at loc. No- 92 & 93 along with other necessary modification at some towers and conductoring of panther conductor and earth wire for 02 km of 132 kv Jamui- Lakhisarai Trans. Line. | [7 empty] | IRF | 0 | 0 | 0 | 0.70016 |  |  | 0 | 0.70016 | 2.16 |  |  | 0 | 2.8602 |  |  |  | 0 | 2.8602 |  |  |  | 0 | 2.8602 |  |  |  | 0 | 2.8602 |  |  | 0 |  |  | 0 |  |  | 2.16
484 | 15/PR/BSPTCL/2023 |  |  |  | Work order for ''Providing Cement concrete and Gravel spreading at 220/132/33 KV GSS, Gopalganj''. | [7 empty] | IRF | 0 | 0 | 0 | 0.7563 |  |  | 0 | 0.7563 | 0.84 |  |  | 0 | 1.5963 |  |  |  | 0 | 1.5963 |  |  |  | 0 | 1.5963 |  |  |  | 0 | 1.5963 |  |  | 0 |  |  | 0 |  |  | 0.84
485 | 21/PR/BSPTCL/2023-5 |  | 13th Plan ongoing Projects |  | Reconstruction of fallen and damaged boundary wall at 132/33 KV GSS , Dumraon | [7 empty] | IRF | 0 | 0 | 0 | 0.49728 |  |  | 0 | 0.49728 |  | 0.59249 |  | 0.59249 | -0.095212 |  |  |  | 0.59249 | -0.095212 |  |  |  | 0.59249 | -0.095212 |  |  |  | 0.59249 | -0.095212 |  |  | 0 |  |  | 0
486 | 29/PR/BSPTCL/2022 |  |  |  | PO for supply of 11 nos. of capacitance and Tan Delta test Kit against NIT-29/PR/BSPTCL/2022 under O&M IRF head. | [7 empty] | IRF | 0 | 0 | 0 | 3.9459 |  |  | 0 | 3.9459 |  |  |  | 0 | 3.9459 |  |  |  | 0 | 3.9459 |  |  |  | 0 | 3.9459 |  |  |  | 0 | 3.9459 |  |  | 0 |  |  | 0
487 | 30/PR/BSPTCL/2022 |  |  |  | PO for Supply of 57 nos. of control & relay panels (220/132 KV transformer-06 nos., 132/33 KV transformer 29 nos., 220Kv line -02nos., 220 kv B/C-02 nos., 132 KV B/C-09 nos., 33 kv B/C-07 nos. and 132/25 kv transformer-02 nos.). | [7 empty] | IRF | 0 | 0 | 0 | 6.6656 |  |  | 0 | 6.6656 |  |  |  | 0 | 6.6656 |  |  |  | 0 | 6.6656 |  |  |  | 0 | 6.6656 |  |  |  | 0 | 6.6656 |  |  | 0 |  |  | 0
488 | 31/PR/BSPTCL/2021 |  |  |  | Purchase Order (PO) & Work Order (WO) for supply of 34 nos. of 40 KVA Diesel Generator sets along with 2.72 Km of 3.5 Cx 150mm2 XLPE cable and 29 nos. of change-over switches against NIT- 31/PR/BSPTCL/2021 under IRF (O&M) Plant &Machinery Head, on FIRM Prices. | [7 empty] | IRF | 0 | 0 | 0 | 3.6236 |  |  | 0 | 3.6236 |  |  |  | 0 | 3.6236 |  |  |  | 0 | 3.6236 |  |  |  | 0 | 3.6236 |  |  |  | 0 | 3.6236 |  |  | 0 |  |  | 0
489 | 31/PR/BSPTCL/2022 |  |  |  | PO for Design, manufacture and supply of 11 nos. of Transformer Turns Ratio Meter. | [7 empty] | IRF | 0 | 0 | 0 | 0.42834 |  |  | 0 | 0.42834 |  |  |  | 0 | 0.42834 |  |  |  | 0 | 0.42834 |  |  |  | 0 | 0.42834 |  |  |  | 0 | 0.42834 |  |  | 0 |  |  | 0
490 | 32/PR/BSPTCL/2020 |  |  |  | Purchase order for supply of different types of relays to be used in Grid Sub station of BSPTCL. | [7 empty] | IRF | 0 | 0 | 0 | 6.168 |  |  | 0 | 6.168 | 0.12 |  |  | 0 | 6.288 |  |  |  | 0 | 6.288 |  |  |  | 0 | 6.288 |  |  |  | 0 | 6.288 |  |  | 0 |  |  | 0 |  |  | 0.12
491 | 32/PR/BSPTCL/2022 |  |  |  | PO For Design, manufacture and supply of 11 nos. of Transformer Winding Resistance Meter. | [7 empty] | IRF | 0 | 0 | 0 | 0.26709 |  |  | 0 | 0.26709 |  |  |  | 0 | 0.26709 |  |  |  | 0 | 0.26709 |  |  |  | 0 | 0.26709 |  |  |  | 0 | 0.26709 |  |  | 0 |  |  | 0
492 | 33/PR/BSPTCL/2022 |  |  |  | PO for design, manufacture, supply and delivery of 11 nos. of CT/PT/CVT test kit. | [7 empty] | IRF | 0 | 0 | 0 | 5.5069 |  |  | 0 | 5.5069 |  |  |  | 0 | 5.5069 |  |  |  | 0 | 5.5069 |  |  |  | 0 | 5.5069 |  |  |  | 0 | 5.5069 |  |  | 0 |  |  | 0
493 | 36/PR/BSPTCL/2022 |  |  |  | Work order for ''Construction of Back-up building (G+2) at Gaya". | [7 empty] | IRF | 0 | 0 | 0 | 2.3149 |  |  | 0 | 2.3149 | 0.95 |  |  | 0 | 3.2649 |  |  |  | 0 | 3.2649 |  |  |  | 0 | 3.2649 |  |  |  | 0 | 3.2649 |  |  | 0 |  |  | 0 |  |  | 0.95
494 | 43/PR/BSPTCL/2021 |  |  |  | Purchase order for design, manufacture, assembely, testing, supply & delivery of 40 nos. of online DC Earth fault Locator under IRF (O&M) Plant & Machinery Head. | [8 empty] | 0 | 0 | 0 | 0.1239 |  |  | 0 | 0.1239 |  |  |  | 0 | 0.1239 |  |  |  | 0 | 0.1239 |  |  |  | 0 | 0.1239 |  |  |  | 0 | 0.1239 |  | 0 | 0 |  | 0 | 0
495 | 47/PR/BSPTCL/2021 |  |  |  | Purchase Order for Supply of 230 KL of EHV Grade Transformer Oil (uninhibited, type-II) in non - returnable drums . | [7 empty] | IRF | 0 | 0 | 0 | 2.2413 |  |  | 0 | 2.2413 |  |  |  | 0 | 2.2413 |  |  |  | 0 | 2.2413 |  |  |  | 0 | 2.2413 |  |  |  | 0 | 2.2413 |  |  | 0 |  |  | 0
496 | 52/PR/BSPTCL/2021 |  |  |  | P.O. for Design, manufacture, Supply and Delivery of 04 nos. of 630KVA and 30 nos. of 315 KVA, 33/0.433 kv, 3 phase , 50 Hz, outdoor type station service transformer with 10% extra oil and accessories/fittings | [7 empty] | IRF | 0 | 0 | 0 | 0.22867 |  |  | 0 | 0.22867 |  |  |  | 0 | 0.22867 |  |  |  | 0 | 0.22867 |  |  |  | 0 | 0.22867 |  |  |  | 0 | 0.22867 |  |  | 0 |  |  | 0
497 | 52/PR/BSPTCL/2022 |  |  |  | Work order for ''Construction of IB Guest House at 132/33 KV GSS Phulparas''. | [7 empty] | IRF | 0 | 0 | 0 | 0.428 |  |  | 0 | 0.428 |  |  |  | 0 | 0.428 |  |  |  | 0 | 0.428 |  |  |  | 0 | 0.428 |  |  |  | 0 | 0.428 |  |  | 0 |  |  | 0
498 | P.O 11/06.06.23 |  |  |  | PO for design, manufacture, supply and delivery of 11 nos. of CT/PT/CVT test kit. | [7 empty] | IRF | 0 | 0 | 0 | 0.91615 |  |  | 0 | 0.91615 |  |  |  | 0 | 0.91615 |  |  |  | 0 | 0.91615 |  |  |  | 0 | 0.91615 |  |  |  | 0 | 0.91615 |  |  | 0 |  |  | 0
499 | PO No-01,dt-24.06.2021 |  |  |  | For Repair of 22 nos. offline Distance to fault locator Kits -16 kits with minor defects and 06 kits with major defect under Trans. O&M Head. | [7 empty] | IRF | 0 | 0 | 0 | 0.07788 |  |  | 0 | 0.07788 |  |  |  | 0 | 0.07788 |  |  |  | 0 | 0.07788 |  |  |  | 0 | 0.07788 |  |  |  | 0 | 0.07788 |  |  | 0 |  |  | 0
500 | W.O 06/02.06.23 |  |  |  | For unloading, loading, handling and transportation of different capacity of transformers at different GSS. | [7 empty] | IRF | 0 | 0 | 0 | 0.30356 |  |  | 0 | 0.30356 |  |  |  | 0 | 0.30356 |  |  |  | 0 | 0.30356 |  |  |  | 0 | 0.30356 |  |  |  | 0 | 0.30356 |  |  | 0 |  |  | 0
501 | 35/PR/BSPTCL/2023 | O&M |  |  | Supply & delivery of 03 sets of Hot Line Maintenance Tools for Live Maintenance of 400 KV, 220 KV & 132 KV Grid Substation and Transmission Line of BSPTCL | [5 empty] | 22.16 |  | IRF | [6 empty] | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 |  |  | 0 |  |  | 0
502 | 36/PR/BSPTCL/2023 | O&M |  |  | Design, manufacture, assembly, testing, supply & delivery of 300 sets of high pressure water mist and air foam (Compressed) 50 Ltr trolly mounted carbon composit with PET liner vessel along with 6.8 Ltr composit with PET liner air cylinder and 450 No. of 6 KG DCP type portable fire extinguisher | [5 empty] | 26.12 |  | IRF | [6 empty] | 0 | 0 | 26.13 |  |  | 0 | 26.13 |  |  |  | 0 | 26.13 |  |  |  | 0 | 26.13 |  |  |  | 0 | 26.13 |  |  | 0 |  |  | 0 |  |  | 26.13
503 | 06/PR/BSPTCL/2024 | P1 | New Project for FY 2025-28 |  | Construction of (i)2x500 MVA + 2x200 MVA, 400/220/132 KV AIS Sub-Station at Chhapra (New), (ii) 132 kV Chhapra(New) - Raghunathpur DCDS with Single Moose conductor. (line length- 80 km) & (iii) 132 kV Chhapra(New) - Maharajganj DCDS (45 km) with Single Moose conductor. (line length- 45 km) | DCB | 3 | 21.06.2024 |  | 20.06.2026 | 482.89 |  | State Plan | [6 empty] | 0 | 0 |  |  |  | 0 | 0 | 96.44 |  |  | 0 | 96.44 | 257.58 | 160.73 |  | 160.73 | 193.29 | 128.86 | 322.15 |  | 482.88 | 0 |  | 77.152 | 19.288 |  | 206.064 | 51.516
495 | 16/PR/BSPTCL/2024 | P1 | New Project for FY 2025-28 |  | Construction of 03 nos. MD+6 tower with pile foundation for shifting the existing 33KV Baruar line, 33KV Nepal (Sirha) line & 11KV Hanuman Nagar line on turnkey basis under deposit head of NBPDCL. | DCB | 2 | 14.09.2024 | 14.09.2024 | 13.06.2025 | 7.04 |  | Deposit Work | [6 empty] | 0 | 0 | 2.77 |  |  | 0 | 2.77 | 3.04 | 7.04 |  | 7.04 | -1.23 |  |  |  | 7.04 | -1.23 |  |  |  | 7.04 | -1.23 | 2.77 |  |  | 3.04 | [5 empty] | 2.77
496 | 34/PR/BSPTCL/2023 | P1 | New Project for FY 2025-28 |  | Construction of newly proposed 2x50MVA, 132/33 KV GSS Sarairanjan (Sarairanjan Block in Samastipur District) with Construction of associated 02 nos. 132KV Line bays at 220/132/33 KV GSS Tajpur & Construction of 132KV D/C Tajpur - Sarairanjan Tr. Line with ACSR Panther Conductor (Line length- 25 RKM) on Turnkey basis under State Plan | DCB | 5 | 09.02.2024 |  | 08.05.2025 | 74.43 |  | State Plan | [6 empty] | 0 | 0 |  |  |  | 0 | 0 | 52 |  |  | 0 | 52 | 14.18 | 74.43 |  | 74.43 | -8.25 |  |  |  | 74.43 | -8.25 |  | 41.6 | 10.4 |  | 11.344 | 2.836
497 | 23PR/BSPTCL/2023 | P1 | New Project for FY 2025-28 |  | Construction of 400 KV, 220 KV transmission line associated to 400/220/132 KV Chhapra (New) & Construction of 220 KV GIS Bays & 132 KV AIS Bays for power evacuation from 400/220/132 KV Chhapra (New) | DCB | 3 | 27.12.2023 | 27.12.2023 | 26.06.2025 | 452.49 |  | State Plan | [6 empty] | 0 | 0 |  |  |  | 0 | 0 | 293 |  |  | 0 | 293 | 87.49 | 452.49 |  | 452.49 | -72 |  |  |  | 452.49 | -72 |  | 234.4 | 58.6 |  | 69.992 | 17.498
498 | 40/PR/BSPTCL/2023 | P1 | New Project for FY 2025-28 |  | Construction of 02 nos. of 400KV GIS bays at GSS Naubatpur (BGCL) | DCB | 3 | 04.03.2023 | 04.03.2023 | 03.03.2025 | 34.74 |  | State Plan | [6 empty] | 0 | 0 |  |  |  | 0 | 0 | 19.74 | 34.74 |  | 34.74 | -15 |  |  |  | 34.74 | -15 |  |  |  | 34.74 | -15 |  | 15.792 | 3.948 |  | 0 | 0
499 | 24/PR/BSPTCL/2024 | P1 | New Project for FY 2025-28 |  | 2nd circuit stringing of 12 nos. of 132 KV transmission line of BSPTCL along with construction of 12 nos. of 132 KV line bays in connecting GSSs | DCB | 3 | 15.10.2024 | 15.10.2024 | 14.10.2025 | 146.03 |  | Special Central Funded Scheme | [6 empty] | 0 | 0 | 69.47 |  |  | 0 | 69.47 | 54.03 | 146.03 |  | 146.03 | -22.53 |  |  |  | 146.03 | -22.53 |  |  |  | 146.03 | -22.53 |  |  | 54.03 |  |  | 0 |  |  | 69.47
500 | 49/PR/BSPTCL/2022 | P1 | New Project for FY 2025-28 |  | (i) Construction of (2x160MVA+3x50 MVA), 220/132/33KV GSS, Tajpur (Dist.- Samastipur) with SAS including Residential Quarters under turnkey basis. (ii)Construction of (2x160MVA+3x50 MVA), 220/132/33KV GSS, Thakurganj (Dist.-Kishanganj) with SAS including Residential Quarters | DCB | 9 | 03.03.2023 | 03.03.2023 | 02.09.2024 | 241.85 |  | State Plan | [6 empty] | 0 | 0 |  | 119.3999 |  | 119.3999 | -119.3999 | 0 | 0 |  | 119.3999 | -119.3999 |  |  |  | 119.3999 | -119.3999 |  |  |  | 119.3999 | -119.3999 |  | 0 | 0 |  | 0 | 0
523 | 01/PR/BSPTCL/2024 |  | New Project for FY 2024-25 |  | payment due to m/s MODERN INSULATORS LTD against P.O 26/15.03.24, nit 01/pr/bsptcl/2024 | [7 empty] | IRF | [8 empty] | 5.41 | [27 empty] | 5.41
527 | 08/PR/BSPTCL/2024-05 |  | New Project for FY 2024-25 |  | boundary wall in remaining portion at 132/33 KV GSS Motihari (08/PR/BSPTCL/2024/05) | [7 empty] | IRF | [8 empty] | 0.15 | [27 empty] | 0.15
528 | 08/PR/BSPTCL/2024-01 |  | New Project for FY 2024-25 |  | boundary wall at 132/33 KV GSS Katra (08/PR/BSPTCL/2024-01) | [7 empty] | IRF | [8 empty] | 0.14 | [27 empty] | 0.14
529 | 08/PR/BSPTCL/2024-02 |  | New Project for FY 2024-25 |  | boundary wall (East side) at 220/132/33 KV GSS Sonenagar (New) (08/PR/BSPTCL/2024-02) | [7 empty] | IRF | [8 empty] | 0.13 | [27 empty] | 0.13
530 | 08/PR/BSPTCL/2024-06 |  | New Project for FY 2024-25 |  | Tower protection work at Loc. No.-116 of 132 KV Ramnagar- Valmikinagar-Surajpura (Nepal) (08/PR/BSPTCL/2024-06) | [7 empty] | IRF | [8 empty] | 0.12 | [27 empty] | 0.12
531 | 09/PR/BSPTCL/2024-01 |  | New Project for FY 2024-25 |  | new store shed and installation of tube well with provision of 3HP submersible pump set at 132/33 KV GSS Board Colony (09/PR/BSPTCL/2024-01) | [7 empty] | IRF | [8 empty] | 0.26 | [27 empty] | 0.26
532 | 09/PR/BSPTCL/2024-02 |  | New Project for FY 2024-25 |  | new store shed at 220/132/33 KV GSS Digha (New) (09/PR/BSPTCL/2024-02) | [7 empty] | IRF | [8 empty] | 0.28 | [27 empty] | 0.28
533 | 11/PR/BSPTCL/2024 |  | New Project for FY 2024-25 |  | TAURUS POWERTRONICS PRIVATE LIMITED, P.O 37/30.08.24, NIT 11/2024 | [7 empty] | IRF | [8 empty] | 5.72 | [27 empty] | 5.72
534 | 13/PR/BSPTCL/2024 |  | New Project for FY 2024-25 |  | Road at 132/33 KV GSS Motihari (13/PR/BSPTCL/2024) | [7 empty] | IRF | [8 empty] | 0.6 | [27 empty] | 0.6
535 | 14/PR/BSPTCL/2024 |  | New Project for FY 2024-25 |  | Tower Protection Loc. No. 25 of 132 kv Ramanagar-Bettiah- Thakrahan (14/PR/BSPTCL/2024) | [7 empty] | IRF | [8 empty] | 0.46 | [27 empty] | 0.46
536 | 16/PR/BSPTCL/2023 |  | New Project for FY 2024-25 | [9 empty] | IRF | [8 empty] | 1.71 | [27 empty] | 1.71
537 | 19/PR/BSPTCL/2023 |  | New Project for FY 2024-25 | [9 empty] | IRF | [8 empty] | 0.14 | [27 empty] | 0.14
537 | 20/PR/BSPTCL/2023 |  | New Project for FY 2024-25 | [9 empty] | IRF | [8 empty] | 1.37 | [27 empty] | 1.37
538 | 21/PR/BSPTCL/2023-01 |  | New Project for FY 2024-25 |  | office (G+2) building at GSS Chhapra(02/PR/BSPTCL/2023-01) | [7 empty] | IRF | [8 empty] | 0.1 | [27 empty] | 0.1
539 | 21/PR/BSPTCL/2023-02 |  | New Project for FY 2024-25 |  | boundary wall at 132/33 KV GSS, Sonenagar (Old)(21/PR/BSPTCL/2023-02) | [7 empty] | IRF | [8 empty] | 0.49 | [27 empty] | 0.49
540 | 21/PR/BSPTCL/2023-04 |  | New Project for FY 2024-25 |  | ''Reconstruction & repair and maintenance work of boundary wall at 132/33 KV GSS, Aurangabad''. | [7 empty] | IRF | [8 empty] | 0.55 | [27 empty] | 0.55
541 | 21/PR/BSPTCL/2023-05 |  | New Project for FY 2024-25 |  | Reconstruction of fallen and damaged boundary wall at 132/33 KV GSS , Dumraon(21/PR/BSPTCL/2023-5) | [7 empty] | IRF | [8 empty] | 0.37 | [27 empty] | 0.37
542 | 21/PR/BSPTCL/2023-09 |  | New Project for FY 2024-25 |  | hieght raising of existing boundary wall at 132/33kv GSS, Lakhisarai (21/PR/BSPTCL/2023-9) | [7 empty] | IRF | [8 empty] | 0.22 | [27 empty] | 0.22
543 | 21/PR/BSPTCL/2022 |  | New Project for FY 2024-25 | [9 empty] | IRF | [8 empty] | 0.93 | [27 empty] | 0.93
544 | 23/PR/BSPTCL/2022 |  | New Project for FY 2024-25 | [9 empty] | IRF | [8 empty] | 1.12 | [27 empty] | 1.12
545 | 29/PR/BSPTCL/2021 |  | New Project for FY 2024-25 | [9 empty] | IRF | [8 empty] | 0.06 | [27 empty] | 0.06
546 | 30/PR/BSPTCL/2023 |  | New Project for FY 2024-25 | [9 empty] | IRF | [8 empty] | 4.97 | [27 empty] | 4.97
547 | 32/PR/BSPTCL/2023 |  | New Project for FY 2024-25 | [9 empty] | IRF | [8 empty] | 0.5 | [27 empty] | 0.5
548 | 33/PR/BSPTCL/2023-.01 |  | New Project for FY 2024-25 |  | RCC retaining wall and other associated works at 220/132/33 Kv GSS Musahari (33/PR/BSPTCL/2023-01) | [7 empty] | IRF | [8 empty] | 0.81 | [27 empty] | 0.81
549 | 33/PR/BSPTCL/2023-02 |  | New Project for FY 2024-25 |  | construction of Internal road at 132/33 KV GSS Shitalpur (33/PR/BSPTCL/2023-02) | [7 empty] | IRF | [8 empty] | 0.25 | [27 empty] | 0.25
550 | 37/PR/BSPTCL/2023 |  | New Project for FY 2024-25 | [9 empty] | IRF | [8 empty] | 1.63 | [27 empty] | 1.63
551 | 43/PR/BSPTCL/2023 |  | New Project for FY 2024-25 | [9 empty] | IRF | [8 empty] | 0.22 | [27 empty] | 0.22
552 |  |  | New Project for FY 2024-25 |  | MADHAV ENGINEERS PVT LTD against P.O 21/10.11.23, | [7 empty] | IRF | [8 empty] | 6.75 | [27 empty] | 6.75
553 | 08/PR/BSPTCL/2024-06 |  | New Project for FY 2024-25 |  | Boundary wall in south side at 132/33 KV GSS Darbhanga | [7 empty] | IRF | [8 empty] | 0.16 | [27 empty] | 0.16
501 | - | P1 | New Project for FY 2025-28 | NITI Aayog Memo No. M-13099/3/1/2016-MLP dtd 20.01.2022 | 132/33kV GSS Bagha, West Champaran | [5 empty] | 67.9 |  | BRGF Special Plan | [6 empty] | 0 | 0 |  |  |  | 0 | 0 | 27.16 |  |  | 0 | 27.16 | 40.74 | 67.9 |  | 67.9 | 0 |  |  |  | 67.9 | 0 |  |  | 27.16 |  |  | 40.74
502 | - | P1 | New Project for FY 2025-28 | Submitted to Energy Dept. vide letter no. 705 dated 14.08.2024 | 132/33kV GSS Maithi, Muzaffarpur | [5 empty] | 134.42 |  | State Plan | [6 empty] | 0 | 0 |  |  |  | 0 | 0 | 26.884 |  |  | 0 | 26.884 | 107.536 | 134.42 |  | 134.42 | 0 |  |  |  | 134.42 | 0 |  | 21.5072 | 5.3768 |  | 86.0288 | 21.5072
503 | - | P1 | New Project for FY 2025-28 | Yet to be approved | 132/33kV GSS Roh, Nawada | [5 empty] | 138 |  | Yet to be decided | [6 empty] | 0 | 0 |  |  |  | 0 | 0 | 55.2 |  |  | 0 | 55.2 | 82.8 | 138 |  | 138 | 0 |  |  |  | 138 | 0 |  | 44.16 | 11.04 |  | 66.24 | 16.56
504 | - | P1 | New Project for FY 2025-28 | Yet to be approved | 132/33kV GSS Mahua, Vaishali | [5 empty] | 164 |  | Yet to be decided | [6 empty] | 0 | 0 |  |  |  | 0 | 0 | 65.6 |  |  | 0 | 65.6 | 98.4 | 164 |  | 164 | 0 |  |  |  | 164 | 0 |  | 52.48 | 13.12 |  | 78.72 | 19.68
505 | - | P1 | New Project for FY 2025-28 | Yet to be approved | 132/33kV GSS Halsi, Lakhisarai | [5 empty] | 172 |  | Yet to be decided | [6 empty] | 0 | 0 |  |  |  | 0 | 0 | 68.8 |  |  | 0 | 68.8 | 103.2 | 172 |  | 172 | 0 |  |  |  | 172 | 0 |  | 55.04 | 13.76 |  | 82.56 | 20.64
506 | - | P1 | New Project for FY 2025-28 | 2319 dated 07.07.2022 | 132/33kV GSS Barari, Bhagalpur | [5 empty] | 156.32 |  | State Plan | [6 empty] | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 62.528 |  |  | 0 | 62.528 | 93.792 | 156.32 |  | 156.32 | 0 |  | 0 | 0 |  | 50.0224 | 12.5056
507 | - | P1 | New Project for FY 2025-28 | Rajyadesh No. 2561 dated 29.08.2015 & 3489 dated 20.11.2027 | 220/132/33kV GSS Korha, Katihar | [5 empty] | 118.1 |  | State Plan | [6 empty] | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 47.24 |  |  | 0 | 47.24 | 70.86 | 118.1 |  | 118.1 | 0 |  | 0 | 0 |  | 37.792 | 9.448
508 | - | P1 | New Project for FY 2025-28 | Submitted to Energy Dept. vide letter no. 777 dated 12.09.2025 | 2nd Sorce Connectivity of existing GSS of BSPTCL | [5 empty] | 442.82 |  | State Plan | [6 empty] | 0 | 0 |  |  |  | 0 | 0 | 88.564 |  |  | 0 | 88.564 | 132.846 |  |  | 0 | 221.41 | 221.41 | 442.82 |  | 442.82 | 0 |  | 70.8512 | 17.7128 |  | 106.2768 | 26.5692
509 | - | P1 | New Project for FY 2025-28 | Submitted to Energy Dept. vide letter no. 801 dated 19.09.2024 | 33kV bay extension in existing GSS of BSPTCL | [5 empty] | 88.99 |  | State Plan | [6 empty] | 0 | 0 |  |  |  | 0 | 0 | 15 |  |  | 0 | 15 | 14.798 |  |  | 0 | 29.798 | 59.192 | 88.99 |  | 88.99 | 0 |  | 12 | 3 |  | 11.8384 | 2.9596
510 | - | P1 | New Project for FY 2025-28 | Yet to be approved | 220/132/33kV GSS Shobhan, Darbhanga | [5 empty] | 305 |  | Yet to be decided | [6 empty] | 0 | 0 |  |  |  | 0 | 0 | 61 |  |  | 0 | 61 | 91.5 |  |  | 0 | 152.5 | 152.5 | 305 |  | 305 | 0 |  | 48.8 | 12.2 |  | 73.2 | 18.3
511 | - | P1 | New Project for FY 2025-28 | Yet to be approved | 132/33kV GSS Bhawanipur, Purnea | [5 empty] | 142 |  | Yet to be decided | [6 empty] | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 56.8 |  |  | 0 | 56.8 | 85.2 | 142 |  | 142 | 0 |  | 0 | 0 |  | 45.44 | 11.36
512 | - | P1 | New Project for FY 2025-28 | Yet to be approved | 132/33kV GSS Akhgaon, Bhojpur | [5 empty] | 150 |  | Yet to be decided | [6 empty] | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0 | 0 | 60 |  |  | 0 | 60 | 90 | 150 |  | 150 | 0 |  | 0 | 0 |  | 48 | 12
513 | - | P1 | New Project for FY 2025-28 | Yet to be approved | 132/33kV GSS Warisnagar, Samastipur | [5 empty] | 132 |  | Yet to be decided | [6 empty] | 0 | 0 |  |  |  | 0 | 0 | 26.4 |  |  | 0 | 26.4 | 52.8 |  |  | 0 | 79.2 | 52.8 | 132 |  | 132 | 0 |  | 21.12 | 5.28 |  | 42.24 | 10.56
514 | - | P1 | New Project for FY 2025-28 | Yet to be approved | 220/33kV GSS Bairiya, Patna | [5 empty] | 175 |  | Yet to be decided | [6 empty] | 0 | 0 |  |  |  | 0 | 0 | 35 |  |  | 0 | 35 | 70 |  |  | 0 | 105 | 70 | 175 |  | 175 | 0 |  | 28 | 7 |  | 56 | 14
515 | - | P1 | New Project for FY 2025-28 | Yet to be approved | 220/132/33kV GSS Amarpur, Banka | [5 empty] | 340 |  | Yet to be decided | [6 empty] | 0 | 0 |  |  |  | 0 | 0 | 68 |  |  | 0 | 68 | 136 |  |  | 0 | 204 | 136 | 340 |  | 340 | 0 |  | 54.4 | 13.6 |  | 108.8 | 27.2
516 | - | P1 | New Project for FY 2025-28 | Yet to be approved | 220/132/33kV GSS Begusarai | [5 empty] | 325 |  | Yet to be decided | [6 empty] | 0 | 0 |  |  |  | 0 | 0 | 65 |  |  | 0 | 65 | 130 |  |  | 0 | 195 | 130 | 325 |  | 325 | 0 |  | 52 | 13 |  | 104 | 26
517 | - | P1 | New Project for FY 2025-28 | Yet to be approved | Augmentation of 50MVA & 80MVA Power Transformer | [5 empty] | 130 |  | Yet to be decided | [6 empty] | 0 | 0 |  |  |  | 0 | 0 | 26 |  |  | 0 | 26 | 52 |  |  | 0 | 78 | 52 | 130 |  | 130 | 0 |  | 20.8 | 5.2 |  | 41.6 | 10.4
518 | 77/PR/BSPTCL/2018 | P1 | 13th Plan Other Project |  | Construction of (i) LILO of Barh-Patna 400KV D/C (Quad) Trans. Line at Bakhtiyarpur (New) (10RKM)(ii) Bakhtiyarpur (New) - Sheikhpura (new) 220 KV D/C Trans. Line (51RKM)(iii) Bakhtiyarpur (New) - Hathidah (new) 220 KV D/C Trans. Line (52RKM)(iv) Bakhtiyarpur (New) - Fatuha (BSPTCL) 220 KV D/C Trans. Line (28RKM) on turnkey basis. NIT 77/PR/BSPTCL/2018 | DCB |  |  |  |  | 139.13 | 153.68 | State Plan | 151.68 | [5 empty] | 0 | 0 |  | 155.6422 |  | 155.6422 | -155.6422 | 151.68 | 151.68 |  | 307.3222 | -155.6422 | 0 |  |  | 0 | -155.6422 | 0 | 0 |  | 0 | -155.6422 |  | 121.344 | 30.336 |  | 0 | 0
519 | 42/PR/BSPTCL/2023 | P1 | State Plan |  | Construction of newly proposed 2x80 MVA, 132/33Kv GSS Majorganj (Block- Sitamarhi) with construction of LILO of 132 Kv Sitamarhi-Dhaka Single Circuit Transmission Line (Line length-26RKM) at proposed GSS Majorganj with ACSR Panther conductor and construction of 132kv DCDS Sheohar-Majorganj Transmission line (Line Lenght-28 RKM) with ACSR Panther conductor along with 02 no. line bays at GSS Sheohar. | DCB |  |  |  |  | 148.95 |  | State Plan | [13 empty] | 60 |  |  |  | 60 | 88.95 | 148.95 |  |  | 0 |  |  |  |  | 0 |  | 48 | 12 |  | 71.16 | 17.79
520 | 23/PR/BSPTCL/2025 | P2 | State Plan |  | Construction of 2×20 MVA, 132/33 KV GSS Barahiya (Dist.–Lakhisarai) along with construction of DCDS LILO T/L from GSS Barahiya to existing 132 KV S/C Hathidah–Lakhisarai T/L with ACSR Panther conductor (RL 4.5 KM) | DCB |  |  |  |  | 54.42 |  | State Plan | [13 empty] | 30 |  |  |  | 30 | 24.42 | 54.42 |  |  | 0 |  |  |  |  | 0 |  | 24 | 6 |  | 19.536 | 4.884
521 | 45/PR/BSPTCL/2025 | P2 | IRF |  | Reconductoring of 05 Nos. 132 KV T/L with HTLS equivalent to Panther conductor 1. 132 KV S/C Chhapra–Ekma–Raghunathpur line 2. 132 KV S/C Dehri–Kochas Pusauli line 3. 132 KV S/C Bettiah–Narkatiyaganj line 4. 132 KV Purnea–Dhamdaha line 5. 132 KV D/C Darbhanga–Madhubani T/L | DCB |  |  |  |  | 256.66 |  | IRF | [13 empty] | 190 | 190 |  |  | 0 | 66.66 | 66.66 |  |  | 0 |  |  |  |  | 0 |  |  | 190 |  |  | 66.66
522 | 55/PR/BSPTCL/2025 | P2 | State Plan |  | 1. Construction of LILO DCDS Trans. Line of both ckt of 132 kV Banka PG – Sultanganj Trans. Line to Proposed 132/33kV GSS Amarpur (2×10 RKM) 2. Re-conductoring of 132kV Banka PG – Sultanganj (BSPTCL) DCDS trans. line with HTLS conductor equivalent of Panther (46.5 RKM) 3. Re-conductoring of S/C 132kV Kahalgaon (NTPC) – Sabour (BSPTCL) trans. line with HTLS conductor equivalent of Panther (34 CKM) | DCB |  |  |  |  | 138.74 |  | State Plan | [13 empty] | 100 | 100 |  |  | 0 | 38.74 | 38.74 |  |  | 0 |  |  |  |  | 0 |  | 80 | 20 |  | 30.992 | 7.748
523 | 39/PR/BSPTCL/2024 | P2 | Deposit Head |  | Construction of 132 KV DCSS transmission line from GSS Warisaliganj to M/s Ambuja Concrete North Pvt. Ltd (ACNPL) (5 RKM), Warisaliganj and its associated one no. 132 KV line bay at 132/33 KV GSS Warisaliganj on turnkey basis under deposit head against NIT No. 39/PR/BSPTCL/2024 | DCB |  |  |  |  | 9.75 |  | Deposit Work | [13 empty] | 9.75 | 9.75 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 |  |  | 9.75
520 | 23/PR/BSPTCL/2024 | P1 | Special assistance to state for capital investment |  | Construction of LILO of both Circuits of 132 kV D/C Haveli Kharagpur–Lakhisarai Transmission Line from location No. 207 to 185 MW Kajra Solar Plant (RL ≈ 4.5 KM) on turnkey basis under Special Assistance to States for Capital Investment for FY 2024-25 against NIT Number: 23/PR/BSPTCL/2024 | DCB |  |  |  |  | 10.55 |  | Special assistance to state for capital investment | [8 empty] | 1.23 |  |  |  |  | 6 | 6 |  |  | 0 | 4.55 | 4.55 |  |  | 0 |  |  |  |  | 0 |  |  | 6 |  |  | 4.55 |  |  | 1.23
521 | 38/Pr/BSPTCL/20323 | P2 | State Plan |  | 1.Construction of LILO of both ckt. of 132 kV D/C Transmission Line from PGCL Lakhisarai – BGCL Hariahi at Khagaur (RL 5 KM) 2. Construction of 02 nos of 220 KV GIS Bays at 220/132/33 kV Haveli Kharagpur (BGCL) on turnkey basis 3. Construction of 02 nos of 220 KV GIS Bays at 220/132/33 kV Goradih (BGCL) on turnkey basis | DCB |  |  |  |  | 144.98 |  | State Plan | [13 empty] | 130 | 130 |  |  | 0 | 14.98 | 14.98 |  |  | 0 |  |  |  |  | 0 |  | 104 | 26 |  | 11.984 | 2.996
522 | 50/PR/BSPTCL/2025 | P2 | IRF |  | Dismantling, Shifting, erection, testing & commissioning of panels from old control room to new control room including supply & installation of Bus bar protection system at 220/132/33 KV GSS Bhusrah with new cable trench in switchyard area against NIT No. 50/PR/BSPTCL/2023 | DCB |  |  |  |  | 21.92 |  | IRF | [17 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  | 0 |  |  | 0
523 | 37/PR/BSPTCL/2023 | P1 | State Plan |  | Construction of (2x200 MVA + 2x80 MVA), 220/132/33 KV Grid Sub-Station at GSS Mairwa (Dist:-Siwan) along with construction of 02 Nos. 132 KV line bay extension work each at 132/33 KV GSS Raghunathpur & 132/33 KV GSS Bhorey | DCB |  |  |  |  | 179.37 |  | State Plan | [13 empty] | 70 | 0 |  |  | 70 | 109.37 | 179.37 |  |  | 0 |  |  |  |  | 0 |  | 56 | 14 |  | 87.496 | 21.874
524 | 38/PR/BSPTCL/2023 | P1 | State Plan |  | Construction of 132/33 KV (2x80 MVA) , Grid Sub-Station Chausa (District-Madhepura) along with Construction of 132 KV D/C Chausa- Udakishunganj Transmission Line with ACSR Panther Conductor (Line Length - 20 RKM) , Construction of 132 KV D/C Chausa- Bhawanipur Transmission Line with ACSR Panther Conductor (Line Length - 20 RKM), Construction of 02 nos. of 132 KV Line bay at Upcoming 132/33 KV GSS Bhawanipur (District- Purnea) & Construction of 02 nos. of 132 KV Line bay at 132/33 KV GSS Udakishunganj (District-Madhepura) | DCB |  |  |  |  | 125.22 |  | State Plan | [8 empty] | 79.71 |  |  |  |  | 50 | 0 |  |  | 50 | 75.22 | 125.22 |  |  | 0 |  |  |  |  | 0 |  | 40 | 10 |  | 60.176 | 15.044 |  | 63.768 | 15.942
525 | 03/PR/BSPTCL/2024 | civil | New Project for FY 2025-28 | Yet to be approved | Construction of IB Guest House at 132/33 KV GSS, Forbesganj | Department |  | 2024-03-15 |  | 2024-12-15 | 0.44512 |  | IRF | [6 empty] | 0 | 0 | 0.15 |  |  | 0 | 0.15 | 0.45 | 0.45 |  | 0.45 | 0.15 | 0 | 0 |  | 0.45 | 0.15 |  |  |  |  | 0.15 |  |  | 0.45 |  |  | 0 |  |  | 0.15
526 | 04/PR/BSPTCL/2023 | civil | New Project for FY 2025-28 | Yet to be approved | Construction of Control Room Building at 220/132/33 KV GSS Biharsharif. | Department |  | 2023-04-17 |  | 2024-04-17 | 3.7407 |  | IRF | 4.4718 | [5 empty] | 0 | 0 |  |  |  | 0 | 0 | 4.47 | 4.47 |  | 4.47 | 0 | 0 | 0 |  | 4.47 | 0 |  |  |  |  | 0 |  |  | 4.47 |  |  | 0
527 | 02/PR/BSPTCL/2023/01 | civil | New Project for FY 2025-28 | Yet to be approved | Construction of Transmission Office (G+2) Building at GSS, Chhapra. | Department |  | 2023-04-17 |  | 2024-04-17 | 4.9043 |  | IRF | 5.4498 | [5 empty] | 0 | 0 |  |  |  | 0 | 0 | 5.45 | 5.45 |  | 5.45 | 0 | 0 | 0 |  | 5.45 | 0 |  |  |  |  | 0 |  |  | 5.45 |  |  | 0
528 | 02/PR/BSPTCL/2023/02 | civil | New Project for FY 2025-28 | Yet to be approved | Construction of Transmission office (G+2) building at GSS Madhepura. | Department |  | 2023-04-17 |  | 2024-04-17 | 4.9124 |  | IRF | 5.5371 | [5 empty] | 0 | 0 |  |  |  | 0 | 0 | 5.54 | 5.54 |  | 5.54 | 0 | 0 | 0 |  | 5.54 | 0 |  |  |  |  | 0 |  |  | 5.54 |  |  | 0
529 | 34/PR/BSPTCL/2024/02 | civil | New Project for FY 2025-28 | Yet to be approved | Construction of boundary wall, earth filling and road with culvert in acquired land (for bay extension) at 132/33 KV GSS Phulparas. | Department |  | 2025-01-24 |  | 2025-10-24 | 1.1273 |  | State Plan | [6 empty] | 0 | 0 |  |  |  | 0 | 0 | 0.25 | 0.25 |  | 0.25 | 0 | 0.88 | 0.88 |  | 1.13 | 0 |  |  |  |  | 0 |  | 0.2 | 0.05 |  | 0.704 | 0.176
526 | 05/PR/BSPTCL/2024 | civil | New Project for FY 2025-28 | Yet to be approved | Construction of IB building (G+1) at Purnea | Department |  | 2024-03-11 |  | 2025-03-11 | 2.258 |  | IRF | 1.8752 | [5 empty] | 0 | 0 | 0.77 |  |  | 0 | 0.77 | 1.88 | 1.88 |  | 1.88 | 0.77 | 0 | 0 |  | 1.88 | 0.77 |  |  |  |  | 0.77 |  |  | 1.88 |  |  | 0 |  |  | 0.77
527 | 36/PR/BSPTCL/2022 | civil | New Project for FY 2025-28 | Yet to be approved | Construction of Back-up SLDC building (G+2) at Gaya. | Department |  | 2022-12-16 |  | 2023-12-16 | 4.2249 |  | State Plan | 4.8555 | [5 empty] | 0 | 0 |  |  |  | 0 | 0 | 4.86 | 4.86 |  | 4.86 | 0 | 0 | 0 |  | 4.86 | 0 |  |  |  |  | 0 |  | 3.888 | 0.972 |  | 0 | 0
528 | 39/PR/BSPTCL/2025 | Telecom & OPGW | New Project for FY 2025-28 | Yet to be approved | Supply, Erection, Testing & Commissioning of 24-Core Armoured Underground Optical Fiber for Main SLDC, BREDA Bhawan, Patna & Back-up SLDC, Gaya along-with Associated Communication Equipment for ULDC PhaseIII SCADA/EMS Up-gradation Project | Department (NOA to be issued) |  |  |  |  | 3.4979 |  | IRF | [6 empty] | 0 | 0 |  |  |  | 0 | 0 | 2.75 | 2.75 |  | 2.75 | 0 | 0.75 | 0.75 |  | 3.5 | 0 |  |  |  |  | 0 |  |  | 2.75 |  |  | 0.75
529 | 25/PR/BSPTCL/2025 | O&M | New Project for FY 2025-28 | Yet to be approved | Design, manufacture, assembly, testing, supply & delivery of 318 sets of combo unit of 9 litre of water mist and compressed air foam fire extinguisher with self-contained breathing apparatus under SDMF scheme | Department |  | 2025-07-01 |  | 2026-01-01 | 23.8 |  | SDMF/IRF | [6 empty] | 0 | 0 |  |  |  | 0 | 0 | 23.8 | 23.8 |  | 23.8 | 0 | 0 | 0 |  | 23.8 | 0 |  |  |  |  | 0 |  |  | 23.8 |  |  | 0
530 | 24/PR/BSPTCL/2025 | O&M | New Project for FY 2025-28 | Yet to be approved | Design, manufacture, testing, supply & delivery of 01 complete set of Aluminium based re-usable ERS under SDMF scheme | Department |  | 2025-07-18 |  | 2026-01-18 | 14.83 |  | SDMF/IRF | [6 empty] | 0 | 0 |  |  |  | 0 | 0 | 14.83 | 14.83 |  | 14.83 | 0 | 0 | 0 |  | 14.83 | 0 |  |  |  |  | 0 |  |  | 14.83 |  |  | 0
531 | 27/PR/BSPTCL/2025 | O&M | New Project for FY 2025-28 | Yet to be approved | Supply, Erection, Testing & Commissioning of Modern fire detection system: 134 sets [01 set per 132KV GSS (134 nos.)] of Smoke and heat detection system with all accessories and fittings along with installation of 795 nos. [05 nos. per GSS (159 nos.)] of Fire Extinguisher Ball under SDMF scheme | Department |  | 2025-08-11 |  |  | 3.73 |  | SDMF/IRF | [6 empty] | 0 | 0 |  |  |  | 0 | 0 | 2.96 | 2.96 |  | 2.96 | 0 | 0.77 | 0.77 |  | 3.73 | 0 |  |  |  |  | 0 |  |  | 2.96 |  |  | 0.77
532 | 12/PR/BSPTCL/2023 |  |  | GoB Letter No. 2028 DATED 24/07/2018 | 02 Nos of Mobile S/Y Equipment testing Van with all accessories | Department | [15 empty] | 10.3 | [8 empty] | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 8.24 | 2.06
| Total | [13 empty] | 7246.8556 | 3206.5424 | 1014.8633 | 1337.1279 | 134.2189 | 8718.2024 | 2774.4326 | 990.22 | 1729.7909 | 4.6935 | 10297.0446 | 2054.6605 | 2196.9758 | 1495.9112 | 0 | 10936.8075 | 2545.725 | 2146.938 | 2030.18 | 0 | 12331.6975 | 2872.483 | 1342.614 | 2827.38 | 0 | 15159.0775 | 1387.717 | 75.449 | 1417.5745 | 766.6113 | 12.79 | 1626.7744 | 520.1636 | 0 | 411.416 | 503.355 | 75.449
[39 empty] | 0 | 16321.0283 | 677.9242
[39 empty] | 0 | -1161.9508 | 709.7928
Formulas:
Original Schedule Date of Completion = EDATE([Date of Award],9)
Note on R150: Madhu Dalal: Adjustment in IRF Common pool

## Capex & Capitalization_SLDC
Details of Capitalization
Sl. No. | NIT No. | Name of Element (Transmission line, Substation, Bay Extension, etc.) | CAPEX FY 2024-25 | Capitalization in FY 2024-25
1 | 01/PR/BSPTCL/2023 | Implementation of ASBM System in SLDC Bihar(01/PR/BSPTCL/2023) | 9.66 | 43.91
|  |  | 9.66 | 43.91