## F5(6)_1
Sl. No. | Name of Element (Transmission line, Substation, Bay Extension, etc.) | Awarded through ICB/DCB/ Department /Deposit Work | No. of Bids received | Date of Award | Actual date of Start of work | Original Schedule Date of Completion | Original Cost of Project | CAPEX Approved in Tariff Orders | Mode of Finance | Amended Cost of Project | Capitalized up to 31.03.2018 | Capitalization in FY 2018-19 | IDC Capitalized in FY 2018-19 | Actual Debt Addition FY 2018-19 | Actual Equity Addition FY 2018-19 | Closing CWIP as on 31.03.2019 | Actual / Scheduled Commissioning Date | Approval of Scheme
1 | Construction of 220KV D/C transmission line from BTPS to Hajipur, NIT-95/2014 | DCB | 2 | 20.03.2015 | 20.03.2015 | 20.06.2016 | 76.57 | 105.78 | BRGF | 105.4 | 0 | 106.7929 | 0 | 0 | 106.7929 | 0 | 03.09.2018 | Table 6.3 of MYT Order
2 | Construction of 132/33KV GSS Maharajganj- NIT/93/2014. | DCB | 2 | 20.03.2015 | 20.03.2015 | 20.03.2016 | 79.24 | 79.24 | State Plan | 81.69 | 39.14 | 0 | 0 | 0 | 0 | 44.26 | 24.05.2017 | Table 6.3 of MYT Order
3 | Construction of 132/33KV GSS Narkatiyaganj - NIT-93/2014 | [15 empty] | 31.05.2017
4 | Construction of 132/33KV GSS Hathua NIT-93/2014 | [15 empty] | 20.05.2017
5 | Construction of 132/33KV GSS Areraj, NIT-93/2014 | [15 empty] | 18.05.2017
6 | Construction of 132/33KV GSS Chakiya-NIT-62A/2014 | DCB | 2 | 15.03.2015 | 15.03.2015 | 15.03.2016 | 41.3 | 41.3 | State Plan | 44.21 | 12.48 | 1.56 | 0 | 0 | 1.56 | 0 | 29.12.2017 | Table 6.3 of MYT Order
7 | Construction of 132/33KV GSS Jhanjharpur | [9 empty] | 0 | 12.5445 |  |  | 12.5445 |  | 05.02.2019
8 | Construction of 132/33KV GSS Pakridayal | [9 empty] | 0 | 14.0195 |  |  | 14.0195 |  | 22.02.2019
9 | Construction of 132/33KV GSS Siwan-New | DCB | 2 | 03.02.2016 | 03.02.2016 | 03.02.2017 | 23.51 | 23.51 | State Plan | 25.53 | 0 | 0 | 0 | 0 | 0 | 23.77 | 29.05.2019 | Table 6.3 of MYT Order
10 | Construction of Loop In Loop Out arrangement of 132 KV Tx. line Madhepura- Sonebarsa 132 KV S/C Tx.line on D/C Tower at Saharsa Existing (CKM-40KM) under Special Plan of Phase-III against NIT 38/2014. | DCB | 2 | 10.02.2015 | 10.02.2015 | 09.08.2015 | 10.65 | 17.52 | BRGF | 15.21 | 0 | 0 | 0 | 0 | 0 | 13.96 | 15.07.2019 | Table 6.3 of MYT Order
11 | Construction of 132/33 KV, 2 x20MVA Nirmali, 2 x 20 MVA, 2 x 20 MVA Banmankhi, 2 x 20 MVA Manihari and 2 x 10 MVA Triveniganj against NIT 63/2014(Package B) | DCB | 3 | 11.02.2015 | 11.02.2015 | 04.04.2016(Nirmali) 04.04.2016(Triveniganaj) 09.04.2016(Banmankhi) 31.07.2016(Manihari) | 73.24 | 79.04 | State Plan | 78.88 | 0 | 0 | 0 | 0 | 0 | 83.28 | Manihari-07.12.17 Nirmali-28.12.17 Banmankhi-25.01.17 | Table 6.3 of MYT Order
12 | Construction of 2 x20MVA , 132/33KV GSS Tarapur, Teghra and Simri Bakhtiyarpur against NIT 91/2014. | DCB | 2 | 21.03.2015 | 21.03.2015 | 20.03.2016 | 80.6 | 67.03 | State Plan | 63.84 | 43.39 | 22.44 | 0 | 0 | 22.44 | 0 | GSS Tarapur:- 27.01.2017, GSS Teghra:- 12.10.2017, Simri Bakhtiyarpur:- 03.03.2017. | Table 6.3 of MYT Order
13 | Construction of 2 x50MVA , 132/33KV GSS Araria, Barsoi, Baisi and Dhamdaha AGAINST NIT 92/2014. | DCB | 2 | 12.08.2015 | 12.08.2015 | 11.08.2016 | 91.91 | 105.07 | State Plan | 105.07 | 0 | 0 | 0 | 0 | 0 | 104.7 | Araria-18.10.17 Barsoi-29.01.18 Baisi-02.05.18 Dhamdaha-15.02.18 | Table 6.3 of MYT Order
14 | R&M of 132/33KV GSS at Kishanganj, Jamalpur and Purnea against NIT no. 07/PR/BSPTCL/2016 | DCB | 2 | 02.03.2016 | 02.03.2016 | 02.03.2017 | 26.19 | 34.28 | State Plan | 30.97 | 0 | 0 | 0 | 0 | 0 | 31.02 | 2018-12-01 | Table 6.3 of MYT Order
15 | Construction of 3X50 MVA, 132/33kV Grid Sub-Station, Jagdishpur (Bhagalpur New) and Korha(Katihar)against NIT no. 10 /PR/BSPTCL/2016 | DCB | 3 | 03.03.2016 | 03.03.2016 | 03.03.2017 | 26.49 | 57.04 | State Plan | 26.49 | 0 | 0 | 0 | 0 | 0 | 13.75 | 30.11.2019 | Table 6.3 of MYT Order
16 | Strengthening of 132 KV & 33 KV main bus and transfer bus by double moose &quad moose respectively of different GSS of BSPTCL NIT no. 24 /PR/BSPTCL/2015 | DCB |  |  |  |  | 61.57 | 67.17 | State Plan | 67.17 | 0 | 0 | 0 | 0 | 0 | 56.8 | 31.12.2018 | Table 6.3 of MYT Order
17 | Second circuit stringing of Existing 03 Nos. of 132 kV Double Circuit Single Strung Transmission Lines under Transmission Circle, Purnea on Turnkey Basis against NIT No. 76/PR/BSPTCL/2015 | DCB | 4 | 02.03.2016 | 02.03.2016 | 02.12.2016 | 16.69 | 16.69 | State Plan | 16.69 | 0 | 0 | 0 | 0 | 0 | 14.91 | 07.08.2017 | Table 6.3 of MYT Order
18 | Construction of 132 KV D/C T/L from Motihari (400 KV) to Motihari (BSPTCL) NIT 403/PR/BSPTCL/2013 Pkg A | DCB | 2 | 13.02.2014 | 13.02.2014 | 12.02.2015 | 8.54 | 8.54 | BRGF | 8.54 | 6.7 | 0 | 0 | 0 | 0 | 1.79 | 25.05.2017 | Table 6.3 of MYT Order
19 | Construction of 132 KV D/C T/L from Motihari (400 KV) to Bettiah NIT 403/PR/BSPTCL/2013 Pkg B | DCB | 2 | 13.02.2014 | 13.02.2014 | 12.02.2015 | 18.69 | 18.69 | BRGF | 18.83 | 0 | 0 |  | 0 | 0 | 18.41 | 30.06.2017 | Table 6.3 of MYT Order
20 | Construction of 132 KV D/C T/L from Motihari (400 KV) to Raxaul NIT 403/PR/BSPTCL/2013 Pkg C | DCB | 2 | 13.02.2014 | 13.02.2014 | 16.03.2016 | 27.42 | 27.42 | BRGF | 28.16 | 0 | 0 | 0 | 0 | 0 | 29.83 | 31.10.2017 | Table 6.3 of MYT Order
21 | construction of two numbers of 132 KV Line bays each at Bettiah (132/33 KV) GSS and Raxaul (132/33 KV) GSS, NIT-403/2013, VSPL | DCB | 2 | 13.02.2014 | 13.02.2014 | 05.02.2016 | 7.02 | 7.02 | BRGF | 7.02 | 0 | 0 | 0 | 0 | 0 | 7.02 | 20.10.2017 | Table 6.3 of MYT Order
22 | (i) construction of 132 KV S/C transmission lines on D/C Tower from 132/33 KV Dhaka GSS to upcoming Pakridayal GSS (ii) Construction of New 132 KV S/C Transmission line on D/C Tower from 220/132 KV Motipur GSS to upcoming Chakiya GSS (iii) LILO of 132 KV S/C of Jainagar-Phulparas Transmission Line at upcoming Jhanjharpur GSS NIT No 82/PR/BSPTCL/2014 | DCB | 2 | 12.03.2015 | 12.03.2015 | 17.02.2016 | 48.16 | 48.16 | State Plan | 48.16 | 0 | 0 | 0 | 0 | 0 | 50.05 | 24.02.2018 | Table 6.3 of MYT Order
23 | Construction of 132KV D/C Udakishanganj-Sonebarsa T/L and 132KV D/C Kusheshwarsthan- Sonebarsa T/L against NIT No. 16/PR/BSPTCL/2014 | DCB | 2 | 06.01.2015 | 06.01.2015 | 05.04.2016 | 85.26 | 114.7 | BRGF | 114.7 | 66.42 | 0 | 0 | 0 | 0 | 48.71 | Udakishanganj-Sonebarsa: 13.06.2016 Kusheshwarsthan- Sonebarsa: 08.01.2018 | Table 6.3 of MYT Order
24 | Construction of 220KV D/C Transmission line Kishanganj (New) – Kishanganj (PGCIL) &132 KV D/C T.L. Kishanganj (New) – Kishanganj (existing GSS) against NIT No. 58/PR/BSPTCL/2014 | [5 empty] | 17.49 | 25.92 | BRGF | 25.92 | 0 | 0 | 0 | 0 | 0 | 25.87 | 220KV D/C Transmission line Kishanganj (New) – Kishanganj (PGCIL) charged on 5.10.2016 & 28.12.2016 and 132 KV D/C T.L. Kishanganj (New) – Kishanganj (existing GSS) has been charged 04.01.2017. | Table 6.3 of MYT Order
25 | Construction of 6 nos of 132/33KV Transformer Bay at Madhubani, Muzaffarpur, Dalsingsarai, Ramnagar, Hajipur and Jandaha , NIT- 08/2014, ABN | DCB | 2 | 09.02.2015 | 09.02.2015 | 08.02.2016 | 10.8 | 12.67 | BRGF | 12.67 | 11.62 | 0 | 0 | 0 | 0 | 0 | Madhubani- 22.02.2016, Dalsingsarai-26.09.2016, Muzaffarpur-31.07.2015, Ramnagar- 13.01.2016, Hajipur-23.06.2016 Jandaha- 22.10.2017 | Table 6.3 of MYT Order
26 | Construction of 220 KV Kishanganj New- Madhepura D/C NIT-02/2015, L&T Tx. Line | DCB | 5 | 21.03.2015 | 21.03.2015 | 20.03.2016 | 110.8 | 129.79 | BRGF | 129.79 | 0 | 136.87 | 0 | 0 | 136.87 | 0 | 24.08.2018 | Table 6.3 of MYT Order
27 | Construction of 220 KV (D/C) Line between Madhepura to Laukhi with AL-59 Conductor(75Km), NIT-03/2015, L&T | DCB | 4 | 21.03.2015 | 21.03.2015 | 20.03.2016 | 94.6 | 103.95 | BRGF | 104.01 | 0 | 107.77 | 0 | 0 | 107.77 | 0 | 07.06.2018 | Table 6.3 of MYT Order
28 | Construction of 220 KV Purnea (PG) – Begusarai D/C Tx. Line | DCB | 2 | 25.08.2015 | 25.08.2015 | 24.11.2016 | 97.2 | 125.26 | RSVY & State Plan | 122.36 | 0 | 0 | 0 | 0 | 0 | 119.72 | 09.08.2018 | Table 6.3 of MYT Order
29 | 132 KV LILO T/l on one of the CKT of 132 KV Betia--Dhanha to Ramanagar GSS against NIT No. 22/PR/BSPTCL/2015 | DCB | 2 | 13.08.2015 | 13.08.2015 | 12.08.2016 | 29.37 | 35.24 | BRGF | 35.24 | 0 | 0 | 0 | 0 | 0 | 16 | 30.06.2019 | Table 6.3 of MYT Order
30 | Construction of 3x50MVA , 132/33KV GSS Raghopur against NIT 30/PR/BSPTCL/2017. | DCB | 6 | 05.01.2018 | 05.01.2018 | 04.01.2018 | 32.3 | 32.3 | State Plan | 32.3 | 0 | 0 | 0 | 0 | 0 | 29.2 | 24.02.2019 | Table 6.3 of MYT Order
31 | Construction of LILO of one circuit of 132KV Laukahi-Supaul Transmission Line at 132/33 KV GSS Raghopur against NIT No. 31/PR/BSPTCL/2017 | DCB | 3 | 18.12.2017 | 18.12.2017 | 17.12.2018 | 14.94 | 15.28 | State Plan | 15.28 | 0 | 14.67 | 0 | 0 | 14.67 | 0 | 21.02.2019 | Table 6.3 of MYT Order
32 | Construction of 132KV S/C Transmission line on D/C Tower between 132/33KV GSS Rosera and Hasanpur Sugar Mill along- with 01 no. 132KV line bay at 132/33KV GSS Rosera against NIT No.-15/PR/BSPTCL/2017 | DCB | 2 | 11.12.2017 | 11.12.2017 | 31.10.2018 | 10.42 | 12.43 | IRF | 12.42 |  | 11.23 | 0 | 0 | 11.23 | 0 | 31.12.2018 | Table 6.3 of MYT Order
33 | Construction of 8 Nos. 132KV line bays at Pandaul-01Nos., Madhubani-02Nos, Jainagar-02, Phulparas-01Nos, Ekma-01Nos and Kusheshwarsthan-01Nos under state plan against NIT No. 04/PR/BSPTCL/2016 | DCB | 3 | 02.03.2016 | 02.03.2016 | 01.09.2016 | 11.41 | 12.58 | State plan | 16.76 | 9.75 | 4.51 | 0 | 0 | 4.51 | 2.5 | 07.06.2018 | Table 6.3 of MYT Order
34 | Construction of 02 nos. 132KV line bays each at 132/33KV GSS SKMCH & Sitamarhi under Special Plan/BRGF, Phase- III,Part-I against NIT No. 07/PR/BSPTCL/2016 | DCB | 2 | 10.06.2015 | 10.06.2015 | 09.06.2016 | 7.02 | 7.44 | BRGF | 7.02 | 0 | 0 | 0 | 0 | 0 | 6.75 | 31.03.2017 | Table 6.3 of MYT Order
35 | Construction of New 132 KV S/C Transmission Line on D/C Tower from existing Kuseshwarsthan GSS to Benipur GSS (Line length-37 Km), construction of New 132 KV S/C Transmission Line on D/C Tower from 220/132 KV Samastipur GSS to Upcoming Shahpurpatori GSS (Line Length- 31 CKM), LILO of 132 KV S/C of Muzaffarpur –Sitamarhi at Belsand GSS under State Plan on turnkey basis against NIT No.- 81/PR/BSPTCL/2014 | DCB | 2 | 21.03.2015 | 21.03.2015 | 30.09.2016 | 28.46 | 39.18 | State Plan | 39.28 | 6.17 | 17.82 | 0 | 0 | 17.82 | 15.48 | 30.09.2018 | Table 6.3 of MYT Order
36 | Construction of 132/33 KV Grid Sub-station, Belsand (2X10MVA), Shahpur Patori (2X20MVA) and Benipur (2X10MVA), NIT- 62/BSPTCL/2014 Pkg-B under state plan on turnkey basis against NIT No.-62/PR/BSPTCL/2014 | DCB | 2 | 21.03.2015 | 21.03.2015 | 20.03.2016 | 55.51 | 55.51 | State Plan | 58.1 | 0 | 38.51 | 0 | 0 | 38.51 | 4.57 | 10.05.2018 | Table 6.3 of MYT Order
37 | Construction of 2 x160+3x50 MVA GSS Musahari(New), NIT-477/2013, Techno | DCB |  | 31.01.2015 | 31.01.2015 | 04.06.2016 | 73.95 | 85.07 | BRGF | 85.07 | 76.29 | 0 | 0 | 0 | 0 | 2.39 | 17.01.2017 | Table 6.3 of MYT Order
38 | Construction of 220 KV & 132 KV D/C Transmission line for evacuation of power from upcoming Motipur GSS, NIT-01/2014, L&T | DCB |  | 27.06.2014 | 27.06.2014 | 26.09.2015 | 148.21 | 193.14 | BRGF | 193.14 | 129.84 | 0 | 0 | 0 | 0 | 0 | 21.11.2017 | Table 6.3 of MYT Order
39 | Construction of (i) 220KV D/C Line from Darbhanga 400/200 KV GSS to to Laukahi (new)GSS (ii) 220KV D/C Line from Laukahi(new) GSS to Supaul (existing) Pkg-'D' GSS, NIT-15/2014 (pkg-D),. L&T | DCB |  | 21.03.2015 | 21.03.2015 | 20.06.2016 | 126.24 | 126.24 | BRGF | 106.38 | 0 | 0 | 0 | 0 | 0 | 98.09 | 30.10.2019 | Table 6.3 of MYT Order
40 | Construction of 220 KV & 132 KV D/C Transmission line for evacuation of power from upcoming Musahari GSS | DCB |  | 29.01.2015 | 29.01.2015 | 07.03.2016 | 88.72 | 123.09 | BRGF | 123.09 | 0 | 0 | 0 | 0 | 0 | 112.46 | 15.04.2017 | Table 6.3 of MYT Order
41 | Construction of 220 /132 /33 kV Motipur GSS, NIT-24/2014, | DCB |  | 16.02.2015 | 16.02.2015 | 17.11.2015 | 69.54 | 75.42 | BRGF | 77.59 | 70.64 | 0 | 0 | 0 | 0 | 0 | 29.03.2017 | Table 6.3 of MYT Order
42 | Construction of 2 x160+2x50 MVA ,220/132/33KV GSS Laukahi, NIT-33/2014, | DCB |  | 21.03.2015 | 21.03.2015 | 07.07.2016 | 60.31 | 67.23 | BRGF | 67.02 | 0 | 61.21 | 0 | 0 | 61.21 | 0 | 21.06.2018 | Table 6.3 of MYT Order
43 | Construction of 132/33kV GSS at Manjhaul , Ballia and Bakhari against NIT- 63/PR/BSPTCL/2014, Package- (A) | DCB | 3 | 11.02.2015 | 11.02.2015 | 11.02.2016 | 54.4 | 64.24 | State Plan | 57.63 | 0 | 0 | 0 | 0 | 0 | 60.24 | 15.01.2019 | Table 6.3 of MYT Order
44 | Construction of 132KV Transmission lines connecting the revenue GSS Bakhri, Ballia, Manjhaul, Nirmali, Triveniganj, Banmankhi, Manihari and Piro against NIT No. 35/PR/BSPTCL/2015 | DCB | 2 | 12.08.2015 | 12.08.2015 | 12.08.2016 | 86.97 | 103.74 | State Plan | 97.45 | 8.75 | 93.49 | 0 | 0 | 93.49 | 0.02 | 19.11.2017 | Table 6.3 of MYT Order
45 | Construction of 220/132/33KV GSS Kishanganj (new) with bay extensions against NIT No. 03/PR/BSPTCL/2014 | DCB | 3 | 30.07.0214 | 30.07.0214 | 30.10.2015 | 84.46 | 89.51 | BRGF | 89.51 | 76.26 | 3.77 | 0 | 0 | 3.77 | 0 | 1. 220/132/33KV Kishanganj GSS - 10.10.2016 2. 2x132KV line bay extension at Kishanganj Remote site- 04.01.2017 3. 2x132KV line bay extension at Forbesganj Remote site- 20.10.2016 and 10.01.2017 4. 4x220KV line bay extension at Madhepura Remote site- 27.04.2017 5. Laukhi Bay extension on 05.06.2018 & 06.06.2018. | Table 6.3 of MYT Order
46 | Capacity augmentation of 220/132/33 kV & 132/33 kV Grid Substation Madhepura, Naugachia, Vaishali, Gangwara, Jamui, Ara and Bihta | ICB | 2 | 31.10.2016 | 31.10.2016 | 31.01.2017 | 48.13 | 48.13 | ADB | 48.65 | 0 | 0 | 0 | 0 | 0 | 44.34 | 05.04.2019 | Table 6.3 of MYT Order
47 | Procurement and construction of 33 KV line bays in form of Indoor VCB panels at 10 nos. of AIS sub-station under transmission circle, Purnea | ICB | 3 | 29.10.2016 | 29.10.2016 | 28.10.2017 | 28.28 | 28.28 | ADB | 34.57 | 0 | 0 | 0 | 0 | 0 | 32.78 | 30.06.19 | Table 6.3 of MYT Order
48 | Procurement and construction of 33 KV line bays in form of Indoor VCB panels at 21 nos. of AIS sub-station under transmission circle, Muzaffarpur | ICB | 1 | 31.10.2016 | 31.10.2016 | 31.01.2017 | 59.09 | 59.09 | ADB | 76.95 | 0 | 0 | 0 | 0 | 0 | 72.12 | 30.06.19 | Table 6.3 of MYT Order
49 | Procurement and construction of 33 KV line bays in form of Indoor VCB panels at 08 nos. of AIS sub-station under transmission circle, Biharsharif | ICB | 2 | 29.10.2016 | 29.10.2016 | 28.10.2016 | 25.2 | 25.2 | ADB | 35.65 | 0 | 0 | 0 | 0 | 0 | 31.82 | 30.06.19 | Table 6.3 of MYT Order
50 | Construction of 220 KV Bihta(new) -Sipara(Patna) D/C transmission line ,220 KV Bihta(new)-Bihta(existing) D/c Transmission line (charged at 132 KV ) and 33 Kv down linking lines from Bihta(new) 220/132/33 KV GSS on tunkey basis. | DCB | 2 | 30.01.2014 | 30.01.2014 | 29.01.2015 | 72.03 | 72.03 | State Plan | 72.03 | 0 | 0 | 0 | 0 | 0 | 75.8 | 12.04.2019 | Table 6.3 of MYT Order
51 | Renovation & Up gradation of Protection and Control Systems of 220/132KV Grid Substation at Biharsharif, Fatuha, Bodhgaya, Dehri On Sone, Khagaul and 132/33KV Grid Substation Kataiya on turnkey basis | DCB | 4 | 31.12.2015 | 31.12.2015 | 30.12.2016 | 69.66 | 69.66 | PSDF | 65.67 | 0 | 0 | 0 | 0 | 0 | 57.09 | DOS- 15.02.2019 Fatuha- 22.07.2017 Bodhgaya- 06.09.2017 Biharsharif- 19.08.2017 Khagaul- 05.07.2018 | Table 6.3 of MYT Order
52 | Second circuit stringing of existing 04 nos of 132KV Double circuit Single strung transmission line:- 1) 132KV Biharsharif- Ekangarsarai- Hulasganj(Except LILO point to Ekangarsasari)(48.14CKM) 2)132KV BIharsharif- Nawada(48.89CKM) 3)132KV BIharsharif- Sheikhpura(38.78CKM) 4)132KV Jamui- sheikhpura(51.9CKM | DCB | 4 | 02.03.2016 | 02.03.2016 | 01.12.2016 | 20.34 | 20.34 | State Plan | 20.34 | 0 | 0 | 0 | 0 | 0 | 21.1 | 10.05.2019 | Table 6.3 of MYT Order
53 | Construction of 08 nos. 132 KV Line bays each at -Belaganj 01no. , Hulasganj-01 no., Jehanabad -01 no., Tekari-02 no., Ataula-01 no. ,Chandauti-01 no., Nawada-01 no. under Trans. Circle, Gaya for 2nd ckt. stringing of existing 132 KV DCSS | DCB | 2 | 02.03.2016 | 02.03.2016 | 01.09.2016 | 12.59 | 12.59 | State Plan | 12.59 | 0 | 8.73 | 0 | 0 | 8.73 | 2.93 | Belaganj & Nawada LDOC 10.07.2019 | Table 6.3 of MYT Order
54 | Construction of 132KV S/C Transmission Line for Solar PV Project of M/s Alfa Infraprop Pvt. Ltd. at Bhagaura from 132KV GSS Rafiganj and Construction of 01 no. 132KV line bay at GSS Rafiganj against NIT No.- 02/PR/BSPTCL/17 | DCB | 2 | 27.03.2017 | 27.03.2017 | 26.09.2017 | 9.74 | 9.74 | State Plan | 9.74 | 0 | 10.25 | 0 | 0 | 10.25 | 0 | completed | Table 6.3 of MYT Order
55 | Construction of 11 Nos. of line bays at Sherghati -01,Imamganj - 01, Sonenagar-02, Aurangaba-02, Ara-02, Jagdishpur-03 & 1 No. of T/F bay at Sherghati agaisnt NIT No.-68/PR/BSPTCL/14 | DCB | 2 | 09.03.2015 | 09.03.2015 | 08.12.2015 | 20.83 | 11.42 | BRGF | 24.34 | 0 | 0 | 0 | 0 | 0 | 20.5 | TOC issued for Imamganj - 29.08.2016, Sonenagar-15.09.2016 ,Aurangabad-20.09.2016, Ara- and LDOC for Jagdishpur& Sherghati are 15.07.2019 | Table 6.3 of MYT Order
56 | Second Circuit Stringing of Existing 03 Nos. of 132 KV Double Circuit Single Strung Transmission Line: i) GSS Belagunj to tapping point of L-32 & L-33 Trans. Line 2.5 CKM ii)132 KV Gaya-Tekari and 132 KV Tekari-Goh 51.8 CKM iii)132 KV Jehanabad-Ataula (Karpi) 22.57 CKM Under Transmission Circle Gaya on Turnkey Basis under State Plan on FIRM prices against NIT No.- 72/PR/BSPTCL/15 | DCB | 4 | 02.03.2016 | 02.03.2016 | 01.12.2016 | 7.41 | 7.41 | State Plan | 7.93 | 0 | 7.93 | 0 | 0 | 7.93 | 0 | completed | Table 6.3 of MYT Order
57 | Construction of 3x50MVA, 132/33KV GSS Ramgarh (Kaimur dist.) and Warislaiganj (Nawada Dist.) on turnkey basis against NIT No.- 84/PR/BSPTCl/15 | DCB | 4 | 04.02.2016 | 04.02.2016 | 03.02.2017 | 64.96 | 64.97 | State Plan | 65.37 | 0 | 60.99 | 0 | 0 | 60.99 | 0 | warsaligang - 29.01.2019 Ramgarh - 26.05.2017 | Table 6.3 of MYT Order
58 | Procurement and Construction of 33KV line bays in form of Indoor VCB panels at 06 nos. of AIS Sub-station under Transmission Circle Bhagalpur against 24/Package D-1/ BSPTCL/ADB/16 | ICB | 3 | 29.10.2016 | 29.10.2016 | 28.10.2017 | 18.91 | 18.91 | ADB | 23.38 | 0 | 0 | 0 | 0 | 0 | 21.59 | 30.06.2019 | Table 6.3 of MYT Order
59 | Procurement and Construction for Re-conductoring of 06 nos.132KV Transmission lines against 31/Package K-1/ BSPTCL/ADB/16 | ICB | 3 | 31.10.2016 | 31.10.2016 | 31.01.2018 | 44 | 44 | ADB | 44.39 | 0 | 35.84 | 4.56 | 34.744 | 5.656 | 1.27 | 30.06.2019 | Table 6.3 of MYT Order
60 | Procurement and Construction for Re-conductoring of 06 nos.132KV Transmission lines against 33/Package M-1/ BSPTCL/ADB/16 | ICB | 3 | 31.10.2016 | 31.10.2016 | 31.01.2018 | 40.86 | 40.86 | ADB | 41.32 | 0 | 36.3 | 3.936 | 34.603 | 5.633 | 0 | 30.06.2019 | Table 6.3 of MYT Order
61 | i) LILO of one ckt. At north of muthani railway station from 132KV D/C Pusouli (New) – Mohania Trans. Line to proposed 3x50 MV Ramgarh GSS (BSPTCL of route length 20Km. ii) LILO of 132KV Line Biharsharif – Nawada D/C Trans. Line – Warsaliganj (New) GSS of Route length 40Kms.iii) LILO of one Ckt. Of 132KV Chhapra – Siwan Transmission Line – Siwan (New) GSS near Darauli of route length 45Kms. Turnkey basis under Under State Plan. | DCB | 3 | 30.12.2015 | 30.12.2015 | 30.12.2016 | 56.17 | 56.17 | State Plan | 36.91 | 10.14 | 26.61 | 0 | 0 | 26.61 | 0 | completed | Table 6.3 of MYT Order
62 | 3X50 MVA,132/33 KV GSS Kerpa | DCB | 6 | 12.02.2018 | 12.02.2018 | 11.02.2019 | 31.69 | 31.69 | State Plan | 31.69 | 0 | 0 | 0 | 0 | 0 | 15.95 | 30.09.2019 | Table 6.3 of MYT Order
63 | Construction of 132KV Lines and 33KV Lines | ICB | 2 | 22.06.2012 | 22.06.2012 | 21.12.2013 | 58.23 | 58.23 | ADB | 81.09 | 0 | 0 | 0 | 0 | 0 | 39.49 | 31.07.2019 | Table 6.3 of MYT Order
64 | Construction of 220KV Lines | ICB | 2 | 22.06.2012 | 22.06.2012 | 21.12.2013 | 41.52 | 41.52 | ADB | 41.52 | 0 | 0 | 0 | 0 | 0 | 22.22 | 31.09.2019 | Table 6.3 of MYT Order
65 | Procurement and Construction of 33KV line bays in form of Indoor VCB panels at 14 nos. of AIS Sub-station under Transmission Circle DOS | ICB | 1 | 31.10.2016 | 31.10.2016 | 30.10.2017 | 33.02 | 33.02 | ADB | 46.84 | 0 | 0 | 0 | 0 | 0 | 40.7 | 30.06.2019 | Table 6.3 of MYT Order
66 | Construction of 33 kV Line Bays in form of Indoor GIS Panel at 11 nos. of AIS Substation under Patna District of BSPTCL on Turnkey Basis. | ICB | 2 | 31.10.2016 | 31.10.2016 | 30.01.2018 | 66.79 | 66.79 | ADB | 75.46 | 0 | 0 | 0 | 0 | 0 | 70.5 | 30.06.2019 | Table 6.3 of MYT Order
67 | Re-conductoring of 05 nos. 220KV & 132KV Transmission lines -- 254.99 Ckm | ICB | 2 | 31.10.2016 | 31.10.2016 | 30.01.2018 | 35.45 | 35.45 | ADB | 35.55 | 0 | 33.98 | 4.686 | 33.2528 | 5.4132 | 0 | 30.03.2019 | Table 6.3 of MYT Order
68 | Supply, Installation, Implementation, Configuration and Integration of ERP system in BSPTCL | ICB | 1 | 18.05.2018 | 18.05.2018 | 17.05.2019 | 21.5 | 21.5 | ADB | 21.5 | 0 | 0 | 0 | 0 | 0 | 7.41 | 30.10.2019 | Table 6.3 of MYT Order
69 | Construction of LILO line on both circuits of 220 KV Begusarai- Purnea (PG)Transmission line at Khagariya new 220/132/33 KV GSS against NIT 12/PR/BSPTCL/2016 Pkg-A under state plan. | DCB | 3 | 30.08.2016 | 30.08.2016 | 30.08.2017 | 8.86 | 9.63 | State Plan | 9.14 | 0 | 0 | 0 | 0 | 0 | 9.03 | 19.05.2019 | Table 6.3 of MYT Order
70 | construction of LILO line on both circuits of 132 KV BTPS- Purnea D/C Transmission line at Khagariya new 220/132/33 KV GSS (CKM-10 KM) against NIT 12/PR/BSPTCL/2016 Pkg-B under state plan. | DCB | 3 | 30.08.2016 | 30.08.2016 | 30.08.2017 | 11.62 | 11.62 | State Plan | 10.25 | 0 | 0 | 0 | 0 | 0 | 8 | 30.06.2019 | Table 6.3 of MYT Order
71 | Construction of (2x160 + 2x50) MVA, 220/132/33KV Grid Sub- Station in KHAGARIA (New) under State Plan in between 220KV D/C Purnea (PG) – Begusarai Transmission Line. | DCB | 3 | 27.08.2015 | 23.05.2018 | 27.11.2017 | 70 | 70 | State Plan | 70 | 0 | 0 | 0 | 0 | 0 | 21.2 | 30.09.2019 | Table 6.3 of MYT Order
72 | construction of 132/33 KV 3x50 MVA Jamui and Banka GSS against NIT 86/PR/BSPTCL/2015 | DCB | 3 | 31.12.2015 | 31.12.2015 | 30.12.2016 | 52.29 | 52.29 | State Plan | 54.25 | 0 | 48.7 | 0 | 0 | 48.7 | 0.19 | Jamui- 06.11.2018 Banka- 19.02.2019 | Table 6.3 of MYT Order
73 | Construction of 132 KV Transmission Lines required for the connectivity of power to upcoming new 132/33 KV Grid Sub Stations at Korha (Distt- Katihar),Nathnagar (Distt.- Bhagalpur) and Jamui(new) on turnkey basis under State Plan (R.L.=190 CKM) against NIT No.-87/PR/BSPTCL/2015 | DCB | 3 | 30.12.2015 | 30.12.2015 | 30.12.2016 | 63.1 | 63.1 | State Plan | 69.55 | 0 | 41.74 | 0 | 0 | 41.74 | 0 | Banka(n)- jamui(N)- 15.09.2018 Jamui(n)- jamui(o) - 21.06.2018 Balance line LDOC- 31.07.2019 | Table 6.3 of MYT Order
74 | Construction of 132KV D/C Sonenagar (New)-Aurangabad Transmission Line.NIT-59/2014, | DCB | 2 | 21.03.2015 | 21.03.2015 | 20.03.2016 | 15.9 | 15.89 | BRGF | 15.9 | 0 | 0 | 0 | 0 | 0 | 13.58 | 31.07.2019 | Table 6.3 of MYT Order
75 | Construction of 132KV D/C Ara- Jagdishpur Transmission Line. | DCB | 2 | 21.03.2015 | 21.03.2015 | 20.03.2016 | 21.16 | 21.16 | BRGF | 21.07 | 0 | 0 | 0 | 0 | 0 |  | 25.02.2019 | Table 6.3 of MYT Order
76 | Work of construction of 06 nos. of 132 KV D/C towers from Ara (PG) to tower loc. No. 1 with ACSR Panther Conductor for connectivity of 2nd circuit of 132 KV D/C Ara (PG)- Jagdishpur Transmission line on turnkey basis. | DCB | 3 | 27.03.2018 | 27.03.2018 | 26.09.2018 | 1.46 | 1.46 | BRGF | 1.46 | 0 | 0 | 0 | 0 | 0 |  | 31.07.2019 | Table 6.3 of MYT Order
77 | Replacement of 23 nos. 50 MVA and 01 no 20 MVA transformer by 24 nos. 132/33 KV, 80 MVA transformer along with associated bay work in existing GSS of Patna | DCB | 2 | 31.03.2017 | 31.03.2017 | 30.11.2018 | 107.62 | 107.62 | State Plan | 106.5 | 0 | 0 | 0 | 0 | 0 | 86.16 | 30.06.2019 | Table 6.3 of MYT Order
78 | Construction of (2X160 MVA+2X50 MVA),220/132/33 KV GSS at Bihta(Patna) & associated 220,132 & 33 kv bays extension at remote end on turnkey basis | DCB | 4 | 26.08.2013 | 26.08.2013 | 25.08.2014 | 59.15 | 59.15 | State Plan | 63.91 | 0 | 0 | 0 | 0 | 0 | 24.44 | 12.04.2019 | Table 6.3 of MYT Order
79 | Construction of 132 KV D/C Transmission Line between 220/132/33 KV Bihta (New) GSS and 132/33KV Upcoming Paliganj GSS NIT No.- 24/PR/BSPTCl/2016 | DCB | 4 | 18.11.2016 | 17.11.2017 | 28.02.2019 | 19.4 | 19.4 | State Plan | 19.4 | 0 | 0 | 0 | 0 | 0 | 13.1 | 31.12.2019 | Table 6.3 of MYT Order
80 | Capacity Augmentation at GSS Baripahari NIT-30/2015 | [6 empty] | Rs. 1370.02 Crore | BRGF |  |  | 5.608 |  | 0 | 5.608 |  |  | 12th Plan Transmission & Sub-Transmission System Strengthening in Bihar-Phase-III) Total Project cost Rs. 1370.02 Crore (Pg. 112 of FY 2015-16 Tariff Order)
| Capicity Augmentation at GSS Dumraon NIT-30/2015 | [7 empty] | BRGF |  |  | 7.5365 |  | 0 | 7.5365
| Capicity Augmentation at Gss Begusarai & Purnea NIT-30/2015 | [7 empty] | BRGF |  |  | 2.7222 |  | 0 | 2.7222
| Capacity Augmentation at Sitamarhi & Raxaul NIT-30/2015 | [7 empty] | BRGF |  |  | 16.5666 |  | 0 | 16.5666
| Cap. Augmentation at Gss Chandauti/Jehanabad NIT-30/2015 | [7 empty] | BRGF |  |  | 10.6194 |  | 0 | 10.6194
81 | Construction of 2x50 MVA, 132/33 KV GSS at Bhabhua | DCB | 3 | 21.03.2015 | 21.03.2015 | 21.03.2016 | 25.05 | Rs. 668.72 Crore | State Plan |  | 0 | 25.92 |  | 0 | 25.92 |  |  | Construction of 17 Nos. 132/33 kV GSS (Project Cost Rs. 668.72 Crore) (Pg. 60 of FY 2015-16 Tariff Order)
82 | Construction of 132/33KV Grid Sub-Station At Piro(Bhojpur) ( 2X20MVA) NIT No.- 61/PR/BSPTCL/2014 | DCB | 2 | 28.01.2015 | 28.01.2015 | 27.01.2016 | 19.17 | Rs. 555.90 Crore | State Plan |  |  | 21.13 |  | 0 | 21.13 |  |  | Installation of 14 Nos. of GSS through State plan funding (Project Cost Rs. 555.90 Crore) (Pg. 112 of FY 2015-16 Tariff Order)
83 | Construction of associated 132 KV line Bays (No. of Bays-05) for second Circuit Stringing of existing 132 KV double Circuit Single Strung NIT No. 02/PR/BSPTCL/2016/State Plan | DCB | 3 | 02.03.2016 | 02.03.2016 | 01.09.2016 | 8.4 | Rs. 123.67 Crore | State Plan |  |  | 7.78 |  | 0 | 7.78 |  |  | 132 km double circuit towers single string lines and 132/33 kV GSS (Project Cosr Rs. 123.67 Crore) (Pg. 104 of FY 2015-16 Tariff Order)
84 | Work of capacity augmentation of 132/33GSS Forbesganj,Katihar, Kishanganj , and Saharsa NIT No. 315/2013 | [6 empty] | Rs. 1370.02 Crore | BRGF |  | 31.67 | 0.57 |  | 0 | 0.57 |  |  | 12th Plan Transmission & Sub-Transmission System Strengthening in Bihar-Phase-III) Total Project cost Rs. 1370.02 Crore (Pg. 112 of FY 2015-16 Tariff Order)
85 | R&M Work of 132/33 Kv GSS Saharsha and Katihar NIT No. 47/2013 Pkg-E | [7 empty] | BRGF |  | 0 | 11.33 |  | 0 | 11.33
86 | Construction of Tr Ln Purnea - Saharsha NIT No. 31/2015 | [6 empty] | Rs. 668.72 Crore | State Plan |  | 0.65 | 0.08 |  | 0 | 0.08 |  |  | Construction of 17 Nos. 132/33 kV GSS (Project Cost Rs. 668.72 Crore) (Pg. 60 of FY 2015-16 Tariff Order)
87 | Earth Filling and Construction Of Boundary wall of Proposed land for 220/132/33KV GSS Supaul (Laukahi) | [6 empty] | Rs. 1370.02 Crore | BRGF |  | 0 | 9.12 |  | 0 | 9.12 |  |  | 12th Plan Transmission & Sub-Transmission System Strengthening in Bihar-Phase-III) Total Project cost Rs. 1370.02 Crore (Pg. 112 of FY 2015-16 Tariff Order)
| Earth Filling and Construction Of Boundary wall of Proposed land for 220/132/33KV GSS Samastipur | [7 empty] | BRGF |  | 0 | 8.84 |  | 0 | 8.84
88 | 132/33Kv GSS Rosera NIT No. 94/2014 | [6 empty] | Rs. 668.72 Crore | State Plan |  | 0 | 21.4699 |  | 0 | 21.4699 |  |  | Construction of 17 Nos. 132/33 kV GSS (Project Cost Rs. 668.72 Crore) (Pg. 60 of FY 2015-16 Tariff Order)
| 132/33Kv GSS Pupuri NIT No. 94/2014 | [7 empty] | State Plan |  | 0 | 21.8246 |  | 0 | 21.8246
| 132/33 kV GSS Benipatti NIT No. 94/2014 | [7 empty] | State Plan |  | 0 | 26.1588 |  | 0 | 26.1588
| 132/33kv GSS Mahnar NIT No. 94/2014 | [7 empty] | State Plan |  | 0 | 19.4252 |  | 0 | 19.4252
89 | Construction of drain along road and expended metalfencing in area of proposed 132 KV line Kv GSS jandaha NIT No. 28/2016 | [6 empty] | Rs. 76.83 Crore | State Plan |  | 0 | 0.27 |  | 0 | 0.27 |  |  | Construction of control room building, residential complex and building, boundary wall, internal road, etc. at old GSS (Project Cost Rs. 76.83 Crore) but in State Plan (Pg. 103 of FY 2015-16 Tariff Order)
90 | Construction Of 132 KV bay Extension at remote at GSS samastipur NIT No.- 482/PR/BSPTCL/2013 | DCB | 3 | 01.03.2014 | 01.03.2014 | 30.04.2015 | 74.69 | Rs. 1370.02 Crore | BRGF |  | 0 | 1.77 |  | 0 | 1.77 |  |  | 12th Plan Transmission & Sub-Transmission System Strengthening in Bihar-Phase-III) Total Project cost Rs. 1370.02 Crore (Pg. 112 of FY 2015-16 Tariff Order)
91 | Construction of 132 kv 2 no Bays each at 132kv GSS DARBGANGA & Gangwra NIT No.- 98/2014 | [6 empty] | Rs. 472.53 Crore |  |  |  | 6.03 |  | 0 | 6.03 |  |  | 12th Plan Transmission & Sub-Transmission System Strengthening in Bihar-Phase-II) Total Project cost Rs. 472.53 Crore (Pg. 59 of FY 2015-16 Tariff Order)
92 | Construction of (2X160+3X50)MVA 220/132/33 kv Grid Sub-Station Muasahri With UG-Station Automation System(SAS) | DCB |  | 31.01.2015 | 31.01.2015 | 04.06.2016 | 73.96 |  | BRGF |  | 76.29 | 2.39 |  | 0 | 2.39
93 | Construction of Bays at GSS Gaihat | DCB | 2 | 10.06.2016 | 10.06.2016 | 09.12.2016 | 4.33 | Rs. 291.84 Crore | BRGF |  | 0 | 4.36 |  | 0 | 4.36 |  |  | BRGF Scheme Phase III (N-1) compliance (Total Project cost Rs. 291.84 Crore) (Pg. 107 of FY 2015-16 Tariff Order, Table 6.6)
94 | Being consultancy charge paid to PGCIL for towards construction of 02 nos. 132 KV bays at 400/220 KV GSS Banka (PG) for evacuation of power from 400/220 KV Banka (PG) | [6 empty] | Rs. 112.31 Crore | IRF |  | 3.68 | 4.28 |  | 0 | 4.28 |  |  | Capital expenditure schemes through Internal Resources (Total Project cost Rs. 112.31 Crore, Table 6.6 on Pg. 107 of FY 2015-16 Tariff Order)
| Capital Expenditure - Deposit Works | [14 empty] | 121.82
| Capital Expenditure - IRF | [14 empty] | 39.45
| Other Capital Expenditure - Common Pool | [14 empty] | 531.83
| TOTAL | [5 empty] | 3638.73 | 3761.75 |  | 3789.5 | 679.88 | 1194.078 | 13.182 | 102.5997 | 1104.6602 | 2481.96
Note: Actual Capitalization in respective year is more than the amended project cost due to addition of Entry Tax not considered

## F5(6)_2
Sl. No. | Name of Element (Transmission line, Substation, Bay Extension, etc.) | Awarded through ICB/DCB/ Department /Deposit Work | No. of Bids received | Date of Award | Actual date of Start of work | Original Schedule Date of Completion | Original Cost of Project | CAPEX Approved in Tariff Orders | Mode of Finance | Amended Cost of Project | Capitalized up to 31.03.2019 | Capitalization in FY 2019-20 | IDC Capitalized in FY 2019-20 | Actual Debt Addition FY 2019-20 | Actual Equity Addition FY 2019-20 | Capitalization in FY 2020-21 | IDC Capitalized in FY 2020-21 | Actual Debt Addition FY 2020-21 | Actual Equity Addition FY 2020-21
Schemes considered by Commission in Table no. 6.3 of MYT Tariff Order for FY 2019-20 to FY 2021-22
1 | Construction of 220KV D/C transmission line from BTPS to Hajipur, NIT-95/2014 | DCB | 2 | 20.03.2015 | 20.03.2015 | 20.06.2016 | 76.57 | 105.78 | BRGF | 105.4 | 106.7929 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Construction of 132/33KV GSS Maharajganj- NIT/93/2014. | DCB | 2 | 20.03.2015 | 20.03.2015 | 20.03.2016 | 79.24 | 79.24 | State Plan | 81.69 | 39.14 | 21.28 | 0 | 0 | 42.56 | 0 | 0 | 0 | 0
3 | Construction of 132/33KV GSS Narkatiyaganj - NIT-93/2014 | [10 empty] | 21.28
4 | Construction of 132/33KV GSS Hathua NIT-93/2014 | [10 empty] | 0
5 | Construction of 132/33KV GSS Areraj, NIT-93/2014 | [10 empty] | 0
6 | Construction of 132/33KV GSS Chakiya-NIT-62A/2014 | DCB | 2 | 15.03.2015 | 15.03.2015 | 15.03.2016 | 41.3 | 41.3 | State Plan | 44.21 | 14.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Construction of 132/33KV GSS Jhanjharpur | [9 empty] | 12.5445 | 0 |  |  | 0
8 | Construction of 132/33KV GSS Pakridayal | [9 empty] | 14.0195 | 0 |  |  | 0
9 | Construction of 132/33KV GSS Siwan-New | DCB | 2 | 03.02.2016 | 03.02.2016 | 03.02.2017 | 23.51 | 23.51 | State Plan | 25.53 | 0 | 25.53 | 0 | 0 | 25.53 | 0 | 0 | 0 | 0
10 | Construction of Loop In Loop Out arrangement of 132 KV Tx. line Madhepura- Sonebarsa 132 KV S/C Tx.line on D/C Tower at Saharsa Existing (CKM-40KM) under Special Plan of Phase-III against NIT 38/2014. | DCB | 2 | 10.02.2015 | 10.02.2015 | 09.08.2015 | 10.65 | 17.52 | BRGF | 15.21 | 0 | 0 | 0 | 0 | 0 | 15.21 | 0 | 0 | 15.21
11 | Construction of 132/33 KV, 2 x20MVA Nirmali, 2 x 20 MVA, 2 x 20 MVA Banmankhi, 2 x 20 MVA Manihari and 2 x 10 MVA Triveniganj against NIT 63/2014(Package B) | DCB | 3 | 11.02.2015 | 11.02.2015 | 04.04.2016(Nirmali) 04.04.2016(Triveniganaj) 09.04.2016(Banmankhi) 31.07.2016(Manihari) | 73.24 | 79.04 | State Plan | 78.88 | 0 | 83.41 | 0 | 0 | 83.41 | 0 | 0 | 0 | 0
12 | Construction of 2 x20MVA , 132/33KV GSS Tarapur, Teghra and Simri Bakhtiyarpur against NIT 91/2014. | DCB | 2 | 21.03.2015 | 21.03.2015 | 20.03.2016 | 80.6 | 67.03 | State Plan | 63.84 | 65.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Construction of 2 x50MVA , 132/33KV GSS Araria, Barsoi, Baisi and Dhamdaha AGAINST NIT 92/2014. | DCB | 2 | 12.08.2015 | 12.08.2015 | 11.08.2016 | 91.91 | 105.07 | State Plan | 105.07 | 0 | 108.85 |  | 0 | 108.85 | 0 | 0 | 0 | 0
14 | R&M of 132/33KV GSS at Kishanganj, Jamalpur and Purnea against NIT no. 07/PR/BSPTCL/2016 | DCB | 2 | 02.03.2016 | 02.03.2016 | 02.03.2017 | 26.19 | 34.28 | State Plan | 30.97 | 0 | 32.49 |  | 0 | 32.49 | 0 | 0 | 0 | 0
15 | Construction of 3X50 MVA, 132/33kV Grid Sub-Station, Jagdishpur (Bhagalpur New) and Korha(Katihar)against NIT no. 10 /PR/BSPTCL/2016 | DCB | 3 | 03.03.2016 | 03.03.2016 | 03.03.2017 | 26.49 | 57.04 | State Plan | 26.49 | 0 | 0 | 0 | 0 | 0 | 26.49 | 0 | 0 | 26.49
16 | Strengthening of 132 KV & 33 KV main bus and transfer bus by double moose &quad moose respectively of different GSS of BSPTCL NIT no. 24 /PR/BSPTCL/2015 | DCB |  |  |  |  | 61.57 | 67.17 | State Plan | 67.17 | 0 | 0 | 0 | 0 | 0 | 67.17 | 0 | 0 | 67.17
17 | Second circuit stringing of Existing 03 Nos. of 132 kV Double Circuit Single Strung Transmission Lines under Transmission Circle, Purnea on Turnkey Basis against NIT No. 76/PR/BSPTCL/2015 | DCB | 4 | 02.03.2016 | 02.03.2016 | 02.12.2016 | 16.69 | 16.69 | State Plan | 16.69 | 0 | 0 | 0 | 0 | 0 | 16.69 | 0 | 0 | 16.69
18 | Construction of 132 KV D/C T/L from Motihari (400 KV) to Motihari (BSPTCL) NIT 403/PR/BSPTCL/2013 Pkg A | DCB | 2 | 13.02.2014 | 13.02.2014 | 12.02.2015 | 8.54 | 8.54 | BRGF | 8.54 | 6.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Construction of 132 KV D/C T/L from Motihari (400 KV) to Bettiah NIT 403/PR/BSPTCL/2013 Pkg B | DCB | 2 | 13.02.2014 | 13.02.2014 | 12.02.2015 | 18.69 | 18.69 | BRGF | 18.83 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
20 | Construction of 132 KV D/C T/L from Motihari (400 KV) to Raxaul NIT 403/PR/BSPTCL/2013 Pkg C | DCB | 2 | 13.02.2014 | 13.02.2014 | 16.03.2016 | 27.42 | 27.42 | BRGF | 28.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | construction of two numbers of 132 KV Line bays each at Bettiah (132/33 KV) GSS and Raxaul (132/33 KV) GSS, NIT-403/2013, VSPL | DCB | 2 | 13.02.2014 | 13.02.2014 | 05.02.2016 | 7.02 | 7.02 | BRGF | 7.02 | 0 | 7.02 |  | 0 | 7.02 | 0 | 0 | 0 | 0
22 | (i) construction of 132 KV S/C transmission lines on D/C Tower from 132/33 KV Dhaka GSS to upcoming Pakridayal GSS (ii) Construction of New 132 KV S/C Transmission line on D/C Tower from 220/132 KV Motipur GSS to upcoming Chakiya GSS (iii) LILO of 132 KV S/C of Jainagar-Phulparas Transmission Line at upcoming Jhanjharpur GSS NIT No 82/PR/BSPTCL/2014 | DCB | 2 | 12.03.2015 | 12.03.2015 | 17.02.2016 | 48.16 | 48.16 | State Plan | 48.16 | 0 | 50.05 | 0 | 0 | 50.05 | 0 | 0 | 0 | 0
23 | Construction of 132KV D/C Udakishanganj-Sonebarsa T/L and 132KV D/C Kusheshwarsthan- Sonebarsa T/L against NIT No. 16/PR/BSPTCL/2014 | DCB | 2 | 06.01.2015 | 06.01.2015 | 05.04.2016 | 85.26 | 114.7 | BRGF | 114.7 | 66.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Construction of 220KV D/C Transmission line Kishanganj (New) – Kishanganj (PGCIL) &132 KV D/C T.L. Kishanganj (New) – Kishanganj (existing GSS) against NIT No. 58/PR/BSPTCL/2014 | [5 empty] | 17.49 | 25.92 | BRGF | 25.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Construction of 6 nos of 132/33KV Transformer Bay at Madhubani, Muzaffarpur, Dalsingsarai, Ramnagar, Hajipur and Jandaha , NIT- 08/2014, ABN | DCB | 2 | 09.02.2015 | 09.02.2015 | 08.02.2016 | 10.8 | 12.67 | BRGF | 12.67 | 11.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | Construction of 220 KV Kishanganj New- Madhepura D/C NIT-02/2015, L&T Tx. Line | DCB | 5 | 21.03.2015 | 21.03.2015 | 20.03.2016 | 110.8 | 129.79 | BRGF | 129.79 | 136.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | Construction of 220 KV (D/C) Line between Madhepura to Laukhi with AL-59 Conductor(75Km), NIT-03/2015, L&T | DCB | 4 | 21.03.2015 | 21.03.2015 | 20.03.2016 | 94.6 | 103.95 | BRGF | 104.01 | 107.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | Construction of 220 KV Purnea (PG) – Begusarai D/C Tx. Line | DCB | 2 | 25.08.2015 | 25.08.2015 | 24.11.2016 | 97.2 | 125.26 | RSVY & State Plan | 122.36 | 0 | 122.36 | 0 | 0 | 122.36 | 0 | 0 | 0 | 0
29 | 132 KV LILO T/l on one of the CKT of 132 KV Betia--Dhanha to Ramanagar GSS against NIT No. 22/PR/BSPTCL/2015 | DCB | 2 | 13.08.2015 | 13.08.2015 | 12.08.2016 | 29.37 | 35.24 | BRGF | 35.24 | 0 | 0 | 0 | 0 | 0 | 35.24 | 0 | 0 | 35.24
30 | Construction of 3x50MVA , 132/33KV GSS Raghopur against NIT 30/PR/BSPTCL/2017. | DCB | 6 | 05.01.2018 | 05.01.2018 | 04.01.2018 | 32.3 | 32.3 | State Plan | 32.3 | 0 | 32.3 | 0 | 0 | 32.3 | 0 | 0 | 0 | 0
31 | Construction of LILO of one circuit of 132KV Laukahi-Supaul Transmission Line at 132/33 KV GSS Raghopur against NIT No. 31/PR/BSPTCL/2017 | DCB | 3 | 18.12.2017 | 18.12.2017 | 17.12.2018 | 14.94 | 15.28 | State Plan | 15.28 | 14.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | Construction of 132KV S/C Transmission line on D/C Tower between 132/33KV GSS Rosera and Hasanpur Sugar Mill along- with 01 no. 132KV line bay at 132/33KV GSS Rosera against NIT No.-15/PR/BSPTCL/2017 | DCB | 2 | 11.12.2017 | 11.12.2017 | 31.10.2018 | 10.42 | 12.43 | IRF | 12.42 | 11.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | Construction of 8 Nos. 132KV line bays at Pandaul-01Nos., Madhubani-02Nos, Jainagar-02, Phulparas-01Nos, Ekma-01Nos and Kusheshwarsthan-01Nos under state plan against NIT No. 04/PR/BSPTCL/2016 | DCB | 3 | 02.03.2016 | 02.03.2016 | 01.09.2016 | 11.41 | 12.58 | State plan | 16.76 | 14.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | Construction of 02 nos. 132KV line bays each at 132/33KV GSS SKMCH & Sitamarhi under Special Plan/BRGF, Phase- III,Part-I against NIT No. 07/PR/BSPTCL/2016 | DCB | 2 | 10.06.2015 | 10.06.2015 | 09.06.2016 | 7.02 | 7.44 | BRGF | 7.02 | 0 | 7.02 |  | 0 | 7.02 | 0 | 0 | 0 | 0
35 | Construction of New 132 KV S/C Transmission Line on D/C Tower from existing Kuseshwarsthan GSS to Benipur GSS (Line length-37 Km), construction of New 132 KV S/C Transmission Line on D/C Tower from 220/132 KV Samastipur GSS to Upcoming Shahpurpatori GSS (Line Length- 31 CKM), LILO of 132 KV S/C of Muzaffarpur –Sitamarhi at Belsand GSS under State Plan on turnkey basis against NIT No.- 81/PR/BSPTCL/2014 | DCB | 2 | 21.03.2015 | 21.03.2015 | 30.09.2016 | 28.46 | 39.18 | State Plan | 39.28 | 23.99 | 16.97 |  | 0 | 16.97 | 0 | 0 | 0 | 0
36 | Construction of 132/33 KV Grid Sub-station, Belsand (2X10MVA), Shahpur Patori (2X20MVA) and Benipur (2X10MVA), NIT- 62/BSPTCL/2014 Pkg-B under state plan on turnkey basis against NIT No.-62/PR/BSPTCL/2014 | DCB | 2 | 21.03.2015 | 21.03.2015 | 20.03.2016 | 55.51 | 55.51 | State Plan | 58.1 | 38.51 | 19.59 |  | 0 | 19.59 | 0 | 0 | 0 | 0
37 | Construction of 2 x160+3x50 MVA GSS Musahari(New), NIT-477/2013, Techno | DCB |  | 31.01.2015 | 31.01.2015 | 04.06.2016 | 73.95 | 85.07 | BRGF | 85.07 | 76.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | Construction of 220 KV & 132 KV D/C Transmission line for evacuation of power from upcoming Motipur GSS, NIT-01/2014, L&T | DCB |  | 27.06.2014 | 27.06.2014 | 26.09.2015 | 148.21 | 193.14 | BRGF | 193.14 | 129.84 | 111.95 |  | 0 | 111.95 | 0 | 0 | 0 | 0
39 | Construction of (i) 220KV D/C Line from Darbhanga 400/200 KV GSS to to Laukahi (new)GSS (ii) 220KV D/C Line from Laukahi(new) GSS to Supaul (existing) Pkg-'D' GSS, NIT-15/2014 (pkg-D),. L&T | DCB |  | 21.03.2015 | 21.03.2015 | 20.06.2016 | 126.24 | 126.24 | BRGF | 106.38 | 0 | 0 | 0 | 0 | 0 | 106.38 | 0 | 0 | 106.38
40 | Construction of 220 KV & 132 KV D/C Transmission line for evacuation of power from upcoming Musahari GSS | DCB |  | 29.01.2015 | 29.01.2015 | 07.03.2016 | 88.72 | 123.09 | BRGF | 123.09 | 0 | 35.83 | 0 | 0 | 35.83 | 0 | 0 | 0 | 0
41 | Construction of 220 /132 /33 kV Motipur GSS, NIT-24/2014, | DCB |  | 16.02.2015 | 16.02.2015 | 17.11.2015 | 69.54 | 75.42 | BRGF | 77.59 | 70.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | Construction of 2 x160+2x50 MVA ,220/132/33KV GSS Laukahi, NIT-33/2014, | DCB |  | 21.03.2015 | 21.03.2015 | 07.07.2016 | 60.31 | 67.23 | BRGF | 67.02 | 61.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | Construction of 132/33kV GSS at Manjhaul , Ballia and Bakhari against NIT- 63/PR/BSPTCL/2014, Package- (A) | DCB | 3 | 11.02.2015 | 11.02.2015 | 11.02.2016 | 54.4 | 64.24 | State Plan | 57.63 | 0 | 16.6 |  | 0 | 16.6 | 0 | 0 | 0 | 0
44 | Construction of 132KV Transmission lines connecting the revenue GSS Bakhri, Ballia, Manjhaul, Nirmali, Triveniganj, Banmankhi, Manihari and Piro against NIT No. 35/PR/BSPTCL/2015 | DCB | 2 | 12.08.2015 | 12.08.2015 | 12.08.2016 | 86.97 | 103.74 | State Plan | 97.45 | 102.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | Construction of 220/132/33KV GSS Kishanganj (new) with bay extensions against NIT No. 03/PR/BSPTCL/2014 | DCB | 3 | 30.07.0214 | 30.07.0214 | 30.10.2015 | 84.46 | 89.51 | BRGF | 89.51 | 80.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | Capacity augmentation of 220/132/33 kV & 132/33 kV Grid Substation Madhepura, Naugachia, Vaishali, Gangwara, Jamui, Ara and Bihta | ICB | 2 | 31.10.2016 | 31.10.2016 | 31.01.2017 | 48.13 | 48.13 | ADB | 48.65 | 0 | 48.65 | 7.1 | 47.945 | 7.805 | 0 | 0 | 0 | 0
47 | Procurement and construction of 33 KV line bays in form of Indoor VCB panels at 10 nos. of AIS sub-station under transmission circle, Purnea | ICB | 3 | 29.10.2016 | 29.10.2016 | 28.10.2017 | 28.28 | 28.28 | ADB | 34.57 | 0 | 35.15 | 5.13 | 34.6408 | 5.6392 | 0 | 0 | 0 | 0
48 | Procurement and construction of 33 KV line bays in form of Indoor VCB panels at 21 nos. of AIS sub-station under transmission circle, Muzaffarpur | ICB | 1 | 31.10.2016 | 31.10.2016 | 31.01.2017 | 59.09 | 59.09 | ADB | 76.95 | 0 | 79.15 | 11.56 | 78.0106 | 12.6994 | 0 | 0 | 0 | 0
49 | Procurement and construction of 33 KV line bays in form of Indoor VCB panels at 08 nos. of AIS sub-station under transmission circle, Biharsharif | ICB | 2 | 29.10.2016 | 29.10.2016 | 28.10.2016 | 25.2 | 25.2 | ADB | 35.65 | 0 | 37.53 | 5.48 | 36.9886 | 6.0214 | 0 | 0 | 0 | 0
50 | Construction of 220 KV Bihta(new) -Sipara(Patna) D/C transmission line ,220 KV Bihta(new)-Bihta(existing) D/c Transmission line (charged at 132 KV ) and 33 Kv down linking lines from Bihta(new) 220/132/33 KV GSS on tunkey basis. | DCB | 2 | 30.01.2014 | 30.01.2014 | 29.01.2015 | 72.03 | 72.03 | State Plan | 72.03 | 0 | 75.8 | 0 | 0 | 75.8 | 0 | 0 | 0 | 0
51 | Renovation & Up gradation of Protection and Control Systems of 220/132KV Grid Substation at Biharsharif, Fatuha, Bodhgaya, Dehri On Sone, Khagaul and 132/33KV Grid Substation Kataiya on turnkey basis | DCB | 4 | 31.12.2015 | 31.12.2015 | 30.12.2016 | 69.66 | 69.66 | PSDF | 65.67 | 0 | 0 | 0 | 0 | 0 | 65.67 | 0 | 0 | 0
52 | Second circuit stringing of existing 04 nos of 132KV Double circuit Single strung transmission line:- 1) 132KV Biharsharif- Ekangarsarai- Hulasganj(Except LILO point to Ekangarsasari)(48.14CKM) 2)132KV BIharsharif- Nawada(48.89CKM) 3)132KV BIharsharif- Sheikhpura(38.78CKM) 4)132KV Jamui- sheikhpura(51.9CKM | DCB | 4 | 02.03.2016 | 02.03.2016 | 01.12.2016 | 20.34 | 20.34 | State Plan | 20.34 | 0 | 21.58 |  | 0 | 21.58 | 0 | 0 | 0 | 0
53 | Construction of 08 nos. 132 KV Line bays each at -Belaganj 01no. , Hulasganj-01 no., Jehanabad -01 no., Tekari-02 no., Ataula-01 no. ,Chandauti-01 no., Nawada-01 no. under Trans. Circle, Gaya for 2nd ckt. stringing of existing 132 KV DCSS | DCB | 2 | 02.03.2016 | 02.03.2016 | 01.09.2016 | 12.59 | 12.59 | State Plan | 12.59 | 8.73 | 12.59 | 0 | 0 | 12.59 | 0 | 0 | 0 | 0
54 | Construction of 132KV S/C Transmission Line for Solar PV Project of M/s Alfa Infraprop Pvt. Ltd. at Bhagaura from 132KV GSS Rafiganj and Construction of 01 no. 132KV line bay at GSS Rafiganj against NIT No.- 02/PR/BSPTCL/17 | DCB | 2 | 27.03.2017 | 27.03.2017 | 26.09.2017 | 9.74 | 9.74 | State Plan | 9.74 | 10.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | Construction of 11 Nos. of line bays at Sherghati -01,Imamganj - 01, Sonenagar-02, Aurangaba-02, Ara-02, Jagdishpur-03 & 1 No. of T/F bay at Sherghati agaisnt NIT No.-68/PR/BSPTCL/14 | DCB | 2 | 09.03.2015 | 09.03.2015 | 08.12.2015 | 20.83 | 11.42 | BRGF | 24.34 | 0 | 21.62 | 0 | 0 | 21.62 | 0 | 0 | 0 | 0
56 | Second Circuit Stringing of Existing 03 Nos. of 132 KV Double Circuit Single Strung Transmission Line: i) GSS Belagunj to tapping point of L-32 & L-33 Trans. Line 2.5 CKM ii)132 KV Gaya-Tekari and 132 KV Tekari-Goh 51.8 CKM iii)132 KV Jehanabad-Ataula (Karpi) 22.57 CKM Under Transmission Circle Gaya on Turnkey Basis under State Plan on FIRM prices against NIT No.- 72/PR/BSPTCL/15 | DCB | 4 | 02.03.2016 | 02.03.2016 | 01.12.2016 | 7.41 | 7.41 | State Plan | 7.93 | 7.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | Construction of 3x50MVA, 132/33KV GSS Ramgarh (Kaimur dist.) and Warislaiganj (Nawada Dist.) on turnkey basis against NIT No.- 84/PR/BSPTCl/15 | DCB | 4 | 04.02.2016 | 04.02.2016 | 03.02.2017 | 64.96 | 64.97 | State Plan | 65.37 | 60.99 | 4.38 |  | 0 | 4.38 | 0 | 0 | 0 | 0
58 | Procurement and Construction of 33KV line bays in form of Indoor VCB panels at 06 nos. of AIS Sub-station under Transmission Circle Bhagalpur against 24/Package D-1/ BSPTCL/ADB/16 | ICB | 3 | 29.10.2016 | 29.10.2016 | 28.10.2017 | 18.91 | 18.91 | ADB | 23.38 | 0 | 23.38 | 3.41 | 23.0394 | 3.7506 | 0 | 0 | 0 | 0
59 | Procurement and Construction for Re-conductoring of 06 nos.132KV Transmission lines against 31/Package K-1/ BSPTCL/ADB/16 | ICB | 3 | 31.10.2016 | 31.10.2016 | 31.01.2018 | 44 | 44 | ADB | 44.39 | 40.4 | 9.06 | 1.32 | 8.9268 | 1.4532 | 0 | 0 | 0 | 0
60 | Procurement and Construction for Re-conductoring of 06 nos.132KV Transmission lines against 33/Package M-1/ BSPTCL/ADB/16 | ICB | 3 | 31.10.2016 | 31.10.2016 | 31.01.2018 | 40.86 | 40.86 | ADB | 41.32 | 40.236 | 7.88 | 1.15 | 7.7658 | 1.2642 | 0 | 0 | 0 | 0
61 | i) LILO of one ckt. At north of muthani railway station from 132KV D/C Pusouli (New) – Mohania Trans. Line to proposed 3x50 MV Ramgarh GSS (BSPTCL of route length 20Km. ii) LILO of 132KV Line Biharsharif – Nawada D/C Trans. Line – Warsaliganj (New) GSS of Route length 40Kms.iii) LILO of one Ckt. Of 132KV Chhapra – Siwan Transmission Line – Siwan (New) GSS near Darauli of route length 45Kms. Turnkey basis under Under State Plan. | DCB | 3 | 30.12.2015 | 30.12.2015 | 30.12.2016 | 56.17 | 56.17 | State Plan | 36.91 | 36.75 | 10.45 |  | 0 | 10.45 | 0 | 0 | 0 | 0
62 | 3X50 MVA,132/33 KV GSS Kerpa | DCB | 6 | 12.02.2018 | 12.02.2018 | 11.02.2019 | 31.69 | 31.69 | State Plan | 31.69 | 0 | 0 |  | 0 | 0 | 31.69 | 0 | 0 | 31.69
63 | Construction of 132KV Lines and 33KV Lines | ICB | 2 | 22.06.2012 | 22.06.2012 | 21.12.2013 | 58.23 | 58.23 | ADB | 81.09 | 0 |  |  | 0 | 0 | 81.06 | 11.84 | 79.894 | 13.006
64 | Construction of 220KV Lines | ICB | 2 | 22.06.2012 | 22.06.2012 | 21.12.2013 | 41.52 | 41.52 | ADB | 41.52 | 0 |  |  | 0 | 0 | 41.52 | 6.06 | 40.9188 | 6.6612
65 | Procurement and Construction of 33KV line bays in form of Indoor VCB panels at 14 nos. of AIS Sub-station under Transmission Circle DOS | ICB | 1 | 31.10.2016 | 31.10.2016 | 30.10.2017 | 33.02 | 33.02 | ADB | 46.84 | 0 | 46.84 | 6.84 | 46.1648 | 7.5152 | 0 | 0 | 0 | 0
66 | Construction of 33 kV Line Bays in form of Indoor GIS Panel at 11 nos. of AIS Substation under Patna District of BSPTCL on Turnkey Basis. | ICB | 2 | 31.10.2016 | 31.10.2016 | 30.01.2018 | 66.79 | 66.79 | ADB | 75.46 | 0 | 75.46 | 11.02 | 74.3728 | 12.1072 | 0 | 0 | 0 | 0
67 | Re-conductoring of 05 nos. 220KV & 132KV Transmission lines -- 254.99 Ckm | ICB | 2 | 31.10.2016 | 31.10.2016 | 30.01.2018 | 35.45 | 35.45 | ADB | 35.55 | 38.666 | 1.57 | 0.23 | 1.548 | 0.252 | 0 | 0 | 0 | 0
68 | Supply, Installation, Implementation, Configuration and Integration of ERP system in BSPTCL | ICB | 1 | 18.05.2018 | 18.05.2018 | 17.05.2019 | 21.5 | 21.5 | ADB | 21.5 | 0 | 0 | 0 | 0 | 0 | 21.5 | 3.14 | 21.1904 | 3.4496
69 | Construction of LILO line on both circuits of 220 KV Begusarai- Purnea (PG)Transmission line at Khagariya new 220/132/33 KV GSS against NIT 12/PR/BSPTCL/2016 Pkg-A under state plan. | DCB | 3 | 30.08.2016 | 30.08.2016 | 30.08.2017 | 8.86 | 9.63 | State Plan | 9.14 | 0 | 9.33 | 0 | 0 | 9.33 | 0 | 0 | 0 | 0
70 | construction of LILO line on both circuits of 132 KV BTPS- Purnea D/C Transmission line at Khagariya new 220/132/33 KV GSS (CKM-10 KM) against NIT 12/PR/BSPTCL/2016 Pkg-B under state plan. | DCB | 3 | 30.08.2016 | 30.08.2016 | 30.08.2017 | 11.62 | 11.62 | State Plan | 10.25 | 0 | 10.25 | 0 | 0 | 10.25 | 0 | 0 | 0 | 0
71 | Construction of (2x160 + 2x50) MVA, 220/132/33KV Grid Sub- Station in KHAGARIA (New) under State Plan in between 220KV D/C Purnea (PG) – Begusarai Transmission Line. | DCB | 3 | 27.08.2015 | 23.05.2018 | 27.11.2017 | 70 | 70 | State Plan | 70 | 0 | 0 | 0 | 0 | 0 | 70 | 0 | 0 | 70
72 | construction of 132/33 KV 3x50 MVA Jamui and Banka GSS against NIT 86/PR/BSPTCL/2015 | DCB | 3 | 31.12.2015 | 31.12.2015 | 30.12.2016 | 52.29 | 52.29 | State Plan | 54.25 | 48.7 | 5.55 |  | 0 | 5.55 | 0 | 0 | 0 | 0
73 | Construction of 132 KV Transmission Lines required for the connectivity of power to upcoming new 132/33 KV Grid Sub Stations at Korha (Distt- Katihar),Nathnagar (Distt.- Bhagalpur) and Jamui(new) on turnkey basis under State Plan (R.L.=190 CKM) against NIT No.-87/PR/BSPTCL/2015 | DCB | 3 | 30.12.2015 | 30.12.2015 | 30.12.2016 | 63.1 | 63.1 | State Plan | 69.55 | 41.74 | 0 | 0 | 0 | 0 | 64.63 | 0 | 0 | 64.63
74 | Construction of 132KV D/C Sonenagar (New)-Aurangabad Transmission Line.NIT-59/2014, | DCB | 2 | 21.03.2015 | 21.03.2015 | 20.03.2016 | 15.9 | 15.89 | BRGF | 15.9 | 0 | 0 | 0 | 0 | 0 | 15.9 | 0 | 0 | 15.9
75 | Construction of 132KV D/C Ara- Jagdishpur Transmission Line. | DCB | 2 | 21.03.2015 | 21.03.2015 | 20.03.2016 | 21.16 | 21.16 | BRGF | 21.07 | 0 | 21.07 | 0 | 0 | 21.07 | 0 | 0 | 0 | 0
76 | Work of construction of 06 nos. of 132 KV D/C towers from Ara (PG) to tower loc. No. 1 with ACSR Panther Conductor for connectivity of 2nd circuit of 132 KV D/C Ara (PG)- Jagdishpur Transmission line on turnkey basis. | DCB | 3 | 27.03.2018 | 27.03.2018 | 26.09.2018 | 1.46 | 1.46 | BRGF | 1.46 | 0 | 1.46 | 0 | 0 | 1.46 | 0 | 0 | 0 | 0
77 | Replacement of 23 nos. 50 MVA and 01 no 20 MVA transformer by 24 nos. 132/33 KV, 80 MVA transformer along with associated bay work in existing GSS of Patna | DCB | 2 | 31.03.2017 | 31.03.2017 | 30.11.2018 | 107.62 | 107.62 | State Plan | 106.5 | 0 | 0 |  | 0 | 0 | 109.61 | 0 | 0 | 109.61
78 | Construction of (2X160 MVA+2X50 MVA),220/132/33 KV GSS at Bihta(Patna) & associated 220,132 & 33 kv bays extension at remote end on turnkey basis | DCB | 4 | 26.08.2013 | 26.08.2013 | 25.08.2014 | 59.15 | 59.15 | State Plan | 63.91 | 0 | 62.56 |  | 0 | 62.56 | 0 | 0 | 0 | 0
79 | Construction of 132 KV D/C Transmission Line between 220/132/33 KV Bihta (New) GSS and 132/33KV Upcoming Paliganj GSS NIT No.- 24/PR/BSPTCl/2016 | DCB | 4 | 18.11.2016 | 17.11.2017 | 28.02.2019 | 19.4 | 19.4 | State Plan | 19.4 | 0 | 0 |  | 0 | 0 | 19.4 | 0 | 0 | 19.4
Schemes considered by Commission in Table no. 6.4 of MYT Tariff Order for FY 2019-20 to FY 2021-22
3 | Construction of 132/33KV (2X50 MVA) GSS at Palasi (Dist. Araria) on turnkey basis. NIT No.-37/PR/BSPTCL/18 | DCB |  | 21.01.2019 | 21.01.2019 |  | 39.8 | 39.8 | State Plan | 35.99 | 0 | 0 | 0 | 0 | 0 | 35.99 | 2.62 | 30.888 | 7.722
4 | Construction of 220/132/33 KV (2X160+3x50MVA) GSS at Garaul (Dist. Vaishali) on turnkey basis NIT No 39/PR/BSPTCL/2018. | DCB |  | 21.01.2019 | 21.01.2019 |  | 98.27 | 98.27 | State Plan | 86.6 | 0 | 0 | 0 | 0 | 0 | 86.6 | 6.79 | 74.712 | 18.678
13 | 1. Construction of 220kV D/c Pusauli (PG)- Sahpuri LILO Karmnasha (new) Transmission line with single moose (Line length-12 Ckm) on turnkey basis. 2. Construction of 220kV D/c Pusauli (BSPTCL)- Karmnasha (New) Transmission Line with twin moose (Line length - 80 Ckm) on turnkey basis NIT No.-56/PR/BSPTCL/2018 | DCB |  | 21.01.2019 | 21.01.2019 |  | 87.86 | 87.86 | State Plan | 75.22 | 0 | 0 | 0 | 0 | 0 | 75.22 | 6 | 64.976 | 16.244
14 | Construction of 220 KV D/C Saharsa( New)- Khagaria(New) Transmission line with ACSR Zebra Conductor (Approx Route Length-80KM) under State Plan against NIT No. 57/PR/BSPTCL/2018 | DCB |  | 21.01.2019 | 21.01.2019 |  | 114 | 114 | State Plan | 93.37 | [5 empty] | 93.37 | 6.8 | 80.136 | 20.034
19 | Construction of 132Kv D/C Karmnasa (new)-Ramgarh Tr Line on single mooze. 2. Construction of 132KV D/c Karmnasa (new)-Karmnasa Tr line on single mooze.NIT No.-55/PR/BSPTCl/2018 | DCB |  | 21.01.2019 | 21.01.2019 |  | 40.18 | 40.18 | State Plan | 34.74 | [5 empty] | 34.74 | 2.63 | 29.896 | 7.474
22 | Construction of following Transmission lines on Turnkey basis: i) 220 KV D/C Muzaffarpur(PG)-Garaul Transmission Line with ACSR Zebra Conductor (Line Length-20 RKM) ii) 132 KV D/C Garaul-MahnarTransmission Line with ACSR Panther Conductor (Line Length- 45 RKM) iii) LILO of both circuit of 132 KV D/C Muzaffarpur-vaishali Transmission Line at Garaul GSS with ACSR Panther Conductor (Line Length- 2x15 RKM) iv) 132 KV D/C Transmission line from GSS Chhapra(New)-Ekma with ACSR Panther Conductor (Line Length - 45 RKM) NIT No- 50/PR/BSPTCL/2018 | DCB |  | 21.01.2019 | 21.01.2019 |  | 103.14 | 103.14 | State Plan | 86.24 | [5 empty] | 86.24 | 6.86 | 74.48 | 18.62
26 | Construction of 220 KV D/C Saharsa(New)- Begusarai Transmission line with ACSR Zebra Conductor (Approx Route Length-100KM) under State Plan against NIT No. 54/PR/BSPTCL/2018. | DCB |  | 21.01.2019 | 21.01.2019 |  | 165.64 | 165.64 | State Plan | 132.39 | [5 empty] | 132.39 | 8.53 | 112.736 | 28.184
33 | Construction of LILO of 132 KV DCSS Benipatti - Pupari Transmission line at Sitamarhi (new) and LILO of both ckt. of 132 KV Raxaul - Bettiah D/C Transmission line at Raxaul (new) with ACSR Panther Conductor. NIT No.-71/PR/BSPTCL/2018 | DCB |  | 21.01.2019 | 21.01.2019 |  | 52.8 | 52.8 | State Plan | 47.26 | [5 empty] | 47.26 | 3.04 | 40.24 | 10.06
47 | Capacity augmentation of different GSS by Addition /Replacement by 200 MVA Power Transformer alongwith associated bays on Turnkey Basis at GSS Khagaul & Sipara NIT No.-49/PR/BSPTCL2018 | DCB |  | 21.01.2019 | 21.01.2019 |  | 65.46 | 65.46 | State Plan | 65.41 | [5 empty] | 65.41 | 4.21 | 55.696 | 13.924
50 | Construction of (2x50) MVA, 132/33 KV GSS Paliganj (Dist.- Patna) and 02 Nos. 132 KV Line Bay Extension at remote end on turnkey basis NIT No.-03/PR/BSPTCL/2018 | DCB |  | 03.10.2018 | 03.10.2018 |  | 24.74 | 24.74 | State Plan | 24.74 | [5 empty] | 24.74 | 1.94 | 21.344 | 5.336
52 | Construction of 220/132/33 KV (2x200 MVA + 3x50MVA) GSS Karmnasha (new) NIT No.-38/PR/BSPTCL/2018 | DCB |  | 21.01.2019 | 21.01.2019 |  | 95.86 | 95.86 | State Plan | 86.67 | [5 empty] | 86.67 | 6.79 | 74.768 | 18.692
| TOTAL | [5 empty] | 4320.88 | 4649.5 |  | 4558.13 | 1539.0489 | 1333.84 | 53.24 | 359.4026 | 1027.6774 | 1556.79 | 77.25 | 801.8752 | 766.4948
Note: Actual Capitalization in respective year is more than the amended project cost due to addition of Entry Tax not considered
Note: Difference in Debt: Equity amount as compared to total Capitalization for FY 2020-21 is due to Rs. 65.67 scheme which is funded by Grant